## Table 1
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 1 CLIENT# = 1 Land Item SCHEDULE: 1 100 Description = CONSTRUCTION SURVEYING Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4SURV Surveying sub 1.00 1.00 LS 700,000.000 700,000 700,000
BID ITEM = 2 CLIENT# = 2 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | CONTRACTOR QUALITY PROGRAM PLAN (CQPP) | [24 empty] | Unit = |  |  | LS Takeoff Quan: | [14 empty] | 1 |  |  |  |  | Engr Quan: |  |  | 1
| 2.01 |  |  |  |  | QCPP PLAN DEVELOPMENT | [24 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: | [14 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
3QCPP | [5 empty] | QCPP PLAN | [12 empty] | 1 |  |  |  | 1.00 LS 10,000.000 10,000 10,000
2.02 | [5 empty] | QC MANAGER | [16 empty] | Quan: 300.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3QCMAN | [5 empty] | QC MANAGER | [12 empty] | 1 |  |  |  | 2,368.00 HR | [10 empty] | 142.500 337,440 337,440
2.03 | [5 empty] | QC INSPECTORS | [24 empty] | Quan: |  |  | 2,160.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3QCINS | [5 empty] | QC INSPECTORS | [12 empty] | 1 |  |  |  | 13,440.00 HR | [10 empty] | 95 | [13 empty] | 1276800 | [5 empty] | 1276800
3QCINSOT | [5 empty] | QC INSPECTOR OVERTI | [12 empty] | 1 |  |  |  | 1,344.00 HR | [10 empty] | 142.5 | [13 empty] | 191520 | [5 empty] | 191520
1468320 | [33 empty] | [ ] | [13 empty] | 1468320 | [5 empty] | 1468320
2.04 | [5 empty] | TESTING | [24 empty] | Quan: |  |  | 1,000.00 EA | [7 empty] | Hrs/Shft: | [5 empty] | 10.00 Cal: 510 | [5 empty] | WC: WAAVG
3QCTESTING | [5 empty] | QC TESTING | [12 empty] | 1 |  |  |  | 1,000.00 EA | [7 empty] | 1 | [10 empty] | 1000 | [11 empty] | 1000
3QCTESTLAB | [5 empty] | QC TESTING LAB | [12 empty] | 1 |  |  |  | 1.00 LS | [7 empty] | 25000 | [10 empty] | 25000 | [11 empty] | 25000
26000 | [30 empty] | [ ] | [10 empty] | 26000 | [11 empty] | 26000
2.05 | [5 empty] | QC REPORTS | [24 empty] | Quan: |  |  | 600.00 EA | [7 empty] | Hrs/Shft: | [5 empty] | 10.00 Cal: 510 | [5 empty] | WC: WAAVG
3QCREPORTS | [5 empty] | QC REPORTS | [12 empty] | 1 |  |  |  | 600.00 EA | [10 empty] | 30 | [13 empty] | 18000 | [8 empty] | 18000
2.06 | [5 empty] | PE REVIEW | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3QCREVIEW | [5 empty] | QC REVIEW | [12 empty] | 1 |  |  |  | 1.00 LS 66,000.000 66,000 66,000
2.07 | [5 empty] | QC TRAILER | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3QCTRAILER | [5 empty] | QC TRAILER | [12 empty] | 1 |  |  |  | 1.00 LS 15,000.000 15,000 15,000
=====> Item Totals: 2 - $1,940,760.00 | [18 empty] | CONTRACTOR QUALITY PROGRAM PLAN (CQPP) [ ] 1,940,760 | [34 empty] | 1940760
1940760 | [5 empty] | 1 LS | [35 empty] | 1940760 | [11 empty] | 1940760
BID ITEM = 3 CLIENT# = 3 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | VIBRATION MONITORING | [24 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
| 3.01 |  |  |  |  | VIBRATION MONITORING | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 3VIBMON VIBRATION MONITORIN 1.00 1.00 LS 15,000.000 | [36 empty] | 15000 | [14 empty] | 15000
| =====> Item Totals: 3 - VIBRATION MONITORING $15,000.00 [ ] | [36 empty] | 15000 | [14 empty] | 15000
Activity Desc Resource | [13 empty] | Pcs |  |  | Quantity | [5 empty] | Unit |  |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  |  | Total
BID ITEM = 3 CLIENT# = 3 Land Item Description = VIBRATION MONITORING Unit = | [29 empty] | SCHEDULE: 1 LS Takeoff Quan: | [13 empty] | 100 1.000 | [5 empty] | Engr Quan: |  |  |  |  | 1
15,000.000 1 LS | [43 empty] | 15000 | [10 empty] | 15000
BID ITEM = 4 CLIENT# = 4 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | NOISE MITIGATION PLAN | [23 empty] | Unit = LS
4.01 |  |  | NOISE MITIGATION PLAN | [23 empty] | Quan: 1.0
3NMP |  |  | NOISE MITIGATION PLA 1.00 | [13 empty] | 1.00 LS | [9 empty] | 2500
4.02 |  |  | NOISE VARIANCE PERMITS | [23 empty] | Quan: 80.0
3NVP |  |  | NOISE VARIANCE PERM 1.00 | [13 empty] | 50.00 EA | [9 empty] | 231
Hrs/Shft: | [48 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
[49 empty] | 2500 | [7 empty] | 2500
Hrs/Shft: | [48 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
[49 empty] | 11550 | [7 empty] | 11550
=====> Item Totals: 4 - NOISE MITIGATION PLAN $14,050.00 14,050.000 1 LS
[ ] | [39 empty] | 14050 | [12 empty] | 14050
[40 empty] | 14050 | [12 empty] | 14050
BID ITEM = 5 CLIENT# = 5 Land Item SCHEDULE: 1 100 Description = CRITICAL PATH SCHEDULE UPDATE, MIN. BID Unit = EA Takeoff Quan: 28.000 Engr Quan: 28.000
005.05 CRITICAL PATH SCHEDULE UPDATE, MIN. BID Quan: 28.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3CPM CPM SCHEDULE UPDAT 1.00 28.00 EA 2,500.000 70,000 70,000
=====> Item Totals: $70,000.00 | [10 empty] | 5 - CRITICAL PATH | [15 empty] | SCHEDULE UPDATE, M [ ] | [10 empty] | IN. BID 70,000 | [14 empty] | 70000
2500 | [10 empty] | 28 EA | [26 empty] | 2500 | [14 empty] | 2500
BID ITEM = 6 CLIENT# = 6 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MOBILIZATION-SCHEDULE 1 | [16 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
6.01 | [5 empty] | SITE SET UP | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 80 | [7 empty] | CH | Prod: | [7 empty] | 80.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 80.00 HR | [5 empty] | 51.051 | [19 empty] | 4084 | [5 empty] | 4084
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 80.00 HR | [5 empty] | 52.3 | [19 empty] | 4184 | [5 empty] | 4184
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 80.00 MH | [5 empty] | 77.06 | [10 empty] | 8052 | [14 empty] | 8052
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 160.00 MH | [5 empty] | 52.91 | [10 empty] | 11162 | [14 empty] | 11162
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 80.00 MH | [5 empty] | 74.56 | [10 empty] | 7796 | [14 empty] | 7796
35277.52 | [5 empty] | 320.0000 MH/LS | [16 empty] | 320.00 MH | [5 empty] | [ 22654.72 ] | [10 empty] | 27009 | [8 empty] | 8268 | [5 empty] | 35278
6.02 | [5 empty] | MOBILIZE EQUIPMENT | [22 empty] | Quan: 40.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3EQMOB | [5 empty] | MOBILIZE EQUIPMENT | [13 empty] | 1 |  |  | 52.00 EA | [5 empty] | 2,500.000 130,000 130,000
6.03 | [5 empty] | SUB MOBILIZATION | [22 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 1,797,000.000 1,797,000 1,797,000
4LAND $1,817,000.00 | [5 empty] | Landscape sub | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 20,000.000 20,000 20,000 [ ] 1,817,000 1,817,000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 6 CLIENT# = 6 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MOBILIZATION-SCHEDULE 1 | [16 empty] | Unit = | [10 empty] | LS Takeoff Quan: 1.000 Engr Quan: 1.000
6.04 | [5 empty] | PUNCH LIST | [16 empty] | Quan: | [10 empty] | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 160 | [7 empty] | CH |  |  | Prod: | [5 empty] | 160.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 160.00 HR | [7 empty] | 51.051 | [17 empty] | 8168 | [5 empty] | 8168
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 160.00 HR | [7 empty] | 52.3 | [17 empty] | 8368 | [5 empty] | 8368
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 160.00 MH | [7 empty] | 77.06 | [8 empty] | 16104 | [14 empty] | 16104
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 320.00 MH | [7 empty] | 52.91 | [8 empty] | 22323 | [14 empty] | 22323
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 160.00 MH | [7 empty] | 74.56 | [8 empty] | 15592 | [14 empty] | 15592
$70,555.05 640.0000 MH/LS | [22 empty] | 640.00 MH | [7 empty] | [ 45309.44 ] | [8 empty] | 54019 | [8 empty] | 16536 | [5 empty] | 70555
006.05 CIVIL SUPERINTENDENTS Quan: | [33 empty] | 1,120.00 SHIF Hrs/Shft: | [14 empty] | 10 |  |  | Cal: 510 |  | WC: WAAVG
ZSUP ==> Superintendent 1.00 8,960.00 MH | [33 empty] | 72.000 827,406 | [22 empty] | 827406
$827,405.82 8.0000 MH/SHIF 8,960.00 MH | [33 empty] | [ 576 ] 827,406 | [22 empty] | 827406
006.06 CONCRETE SUPERINTENDENTS Quan: | [33 empty] | 1,120.00 SHIF Hrs/Shft: | [14 empty] | 10 |  |  | Cal: 510 |  | WC: WAAVG
ZSUP ==> Superintendent 1.00 8,960.00 MH | [33 empty] | 72.000 827,406 | [22 empty] | 827406
$827,405.82 8.0000 MH/SHIF 8,960.00 MH | [33 empty] | [ 576 ] 827,406 | [22 empty] | 827406
006.08 ELECTRICAL SUB BOND Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [7 empty] | Electrical sub | [11 empty] | 1 |  |  | 1.00 LS 223,822.000 223,822 223,822
006.09 3VAC | [7 empty] | VACTOR TRUCKS VACTOR TRUCKS | [11 empty] | 1 |  |  | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG 1.00 LS 200,000.000 200,000 200,000
6.1 | [7 empty] | MINI EX | [22 empty] | Quan: |  |  | 560.00 DAY Hrs/Shft: | [14 empty] | 10.00 Cal: 510 WC: WAAVG
8EX035 | [7 empty] | ==> 35 Excavator | [11 empty] | 1 |  |  | 4,480.00 HR | [10 empty] | 28.83 | [14 empty] | 129,158 129,158
6.11 | [7 empty] | WATERTRUCK | [22 empty] | Quan: |  |  | 280.00 SHIF Hrs/Shft: | [14 empty] | 10.00 Cal: 510 WC: WAAVG
8TRW | [7 empty] | ==> Water Truck | [11 empty] | 1 |  |  | 1,400.00 HR | [10 empty] | 70 | [14 empty] | 98,000 98,000
6.12 | [7 empty] | MISSILANIOUS | [22 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3ECOPAN | [7 empty] | ECO PANS | [11 empty] | 1 |  |  | 1.00 LS | [7 empty] | 48000 | [17 empty] | 48000 |  |  |  | 48000
3LIGHTPLANT | [7 empty] | LIGHT PLANTS | [11 empty] | 1 |  |  | 1.00 LS | [7 empty] | 24000 | [17 empty] | 24000 |  |  |  | 24000
3PEDACSESS | [7 empty] | PED ACSESS RAMPS | [11 empty] | 1 |  |  | 1.00 LS | [7 empty] | 90000 | [17 empty] | 90000 |  |  |  | 90000
3WATERMETER | [7 empty] | WATER METER FEES | [11 empty] | 1 |  |  | 1.00 LS | [7 empty] | 30000 | [17 empty] | 30000 |  |  |  | 30000
192000 | [30 empty] | [ ] | [17 empty] | 192000 |  |  |  | 192000
006.13 OFFICE AND LAYDOWN Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3FENCE | [5 empty] | TEMP FENCE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 15000 | [8 empty] | 15000 | [12 empty] | 15000
3LAYDOWN | [5 empty] | LAYDOWN YARD | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 168000 | [8 empty] | 168000 | [12 empty] | 168000
3PROFFIC | [5 empty] | PROJECT OFFICE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 200000 | [8 empty] | 200000 | [12 empty] | 200000
383000 | [30 empty] | [ ] | [8 empty] | 383000 | [12 empty] | 383000
006.14 ATTOURNEY FEES Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3ATTOURNEY ATTOURNEY COST 1.00 1.00 LS 100,000.000 100,000 100,000
| 6.15 |  |  |  |  | CLEAN UP CREW | [24 empty] | Quan: 112.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| ZZZZZZ |  |  |  |  | CLEAN UP CREW | [16 empty] | 896 | [7 empty] | CH Prod: 896.0000 CH Lab Pcs: 2.00 Eqp Pcs: 1.00
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 6 CLIENT# = 6 Land Item SCHEDULE: 1 100 Description = MOBILIZATION-SCHEDULE 1 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 896.00 HR | [7 empty] | 81.5 | [21 empty] | 73024 |  |  |  | 73024
LAG | [5 empty] | General Laborer | [13 empty] | 1 |  |  | 896.00 MH | [7 empty] | 52.91 | [8 empty] | 62505 | [16 empty] | 62505
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 896.00 MH | [7 empty] | 74.56 | [8 empty] | 87315 | [16 empty] | 87315
$222,844.45 16.0000 MH/SHIF 1,792.00 MH | [30 empty] | [ 1121.736 ] | [8 empty] | 149820 | [12 empty] | 73024 |  |  |  | 222844
=====> Item Totals: 6 - MOBILIZATION-SCHEDULE 1
2,040,822 5,256,469 2,040,822.00 5,256,469.06
5256469.06 | [5 empty] | 20,672.0000 MH/LS | [16 empty] | 20,672.00 MH | [7 empty] | [ 1483838.6 ] 1,885,660 | [13 empty] | 1005000 | [7 empty] | 324987
5256469.06 | [5 empty] | 1 LS | [24 empty] | 1885660.42 | [13 empty] | 1005000 | [7 empty] | 324986.64
BID ITEM = 7 CLIENT# = 7 Land Item SCHEDULE: 1 100 Description = MAINTENANCE AND PROTECTION OF TRAFFIC CO Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
007.01 TRAFFIC CONTROL PLANS Quan: 200.00 EA
Hrs/Shft: | [48 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
[49 empty] | 30000 | [7 empty] | 30000
Hrs/Shft: | [48 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
[49 empty] | 65000 | [7 empty] | 65000
Hrs/Shft: | [48 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
[49 empty] | 50000 | [7 empty] | 50000
3TCP TRAFFIC CONTROL PLA 1.00 200.00 EA 150.000
0
3TRAFMAT |  |  | TRAFFIC CONTROL MA | [10 empty] | 1 |  |  | 1.00 LS 65,
7.03 |  |  | ROAD PLATES | [13 empty] | Quan:
3ROADPLAT |  |  | ROAD PLATES | [10 empty] | 1 |  |  | 1.00 LS 50,
7.04 |  |  | TCS | [13 empty] | Quan:
LAFT |  |  | ==> Traffic Control Supervi | [10 empty] | 1 |  |  | 15,680.00 MH
0
52.810 1,270,626 1,270,626 $1,270,625.54 10.0000 MH/SHIF 15,680.00 MH [ 678.978 ] 1,270,626 1,270,626
007.05 FLAGGERS Quan: 2,240.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
LAF ==> Flager 1.00 $1,331,433.93 10.0000 MH/SHIF
22,400.00 MH | [30 empty] | 44.840 1,331,434 | [21 empty] | 1331434
22,400.00 MH | [30 empty] | [ 493.24 ] 1,331,434 | [21 empty] | 1331434
=====> Item Totals: 7 - MAINTENANCE AND PROTECTION OF TRAFFIC CO
2747059.47 | [5 empty] | 38,080.0000 MH/LS | [16 empty] | 38,080.00 MH | [7 empty] | [ 2169495.37 ] 2,602,059 | [17 empty] | 145000 |  |  |  | 2747059
2747059.47 | [5 empty] | 1 LS | [24 empty] | 2602059.47 | [17 empty] | 145000 |  |  |  | 2747059.47
BID ITEM = 8 CLIENT# = 8 Land Item SCHEDULE: 1 100 Description = TRAFFIC CONTROL PEACE OFFICERS Unit = HR Takeoff Quan: 12,280.000 Engr Quan: 12,280.000
008.01 TRAFFIC CONTROL PEACE OFFICERS Quan: 12,280.00 HR Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3UPO | [5 empty] | UPO | [13 empty] | 1 |  |  | 6,140.00 HR | [7 empty] | 112.5 | [8 empty] | 690750 | [12 empty] | 690750
3UPOST | [5 empty] | STRAIGHT TIME UPO | [13 empty] | 1 |  |  | 6,140.00 HR | [7 empty] | 82.5 | [8 empty] | 506550 | [12 empty] | 506550
1197300 | [30 empty] | [ ] | [8 empty] | 1197300 | [12 empty] | 1197300
=====> Item Totals: 8 - TRAFFIC CONTROL PEACE OFFICERS
$1,197,300.00 [ ] 1,197,300 | [52 empty] | 1197300
97.500 12280 HR 97.50 | [52 empty] | 97.5
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 9 CLIENT# = 9 Land Item SCHEDULE: 1 100
Description = PORTABLE CHANGEABLE MESSAGE SIGN Unit = WK Takeoff Quan: 52.000 | [53 empty] | Engr Quan: |  |  | 52
009.01 PORTABLE CHANGEABLE MESSAGE SIGN Quan: 52.00 WK Hrs/Shft: 10.00 Cal: 510 | [53 empty] | WC: WAAVG
3VMS MESSAGE SIGN 1.00 52.00 WK 450.000 23,400 | [56 empty] | 23400
=====> Item Totals: $23,400.00 | [10 empty] | 9 - PORTABLE CHAN | [16 empty] | GEABLE MESSAGE SIGN [ ] | [11 empty] | 23400 | [13 empty] | 23400
450 | [10 empty] | 52 WK | [28 empty] | 450 | [13 empty] | 450
BID ITEM = 10 CLIENT# = 10 Land Item SCHEDULE: 1 100
Description = | [5 empty] | TEMPORARY BUSINESS, PUBLIC ACCESS AND PR Unit = | [27 empty] | LS Takeoff Quan: | [14 empty] | 1 |  |  |  |  | Engr Quan: |  |  | 1
10.01 | [5 empty] | TEMPORARY BUSINESS, PUBLIC ACCESS AND P Quan: | [27 empty] | 1.00 LS Hrs/Shft: | [14 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
3TBPAPR TEMP BUISNES ACCESS 1.00 1.00 LS 5,000.000 5,000 | [53 empty] | 5000
=====> Item Totals: 10 - TEMPORARY BUSINESS, PUBLIC ACCESS AND PR
5000 | [33 empty] | [ ] | [14 empty] | 5000 |  |  |  |  | 5000
5000 | [5 empty] | 1 LS | [42 empty] | 5000 |  |  |  |  | 5000
BID ITEM = 11 CLIENT# = 11 Land Item SCHEDULE: 1 100 Description = ENGINEER DIRECTED TEMPORARY BUSINESS AND Unit = FA Takeoff Quan: 100,000.000 Engr Quan: 100,000.000
011.01 ENGINEER DIRECTED TEMPORARY BUSINESS Quan: 100,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 100,000.00 FA 0.890 | [37 empty] | 89000 | [14 empty] | 89000
[38 empty] | SINESS AND 89,000 | [14 empty] | 89000
=====> Item Totals: 11 - ENGINEER DIRECTED TEMPORARY BU $89,000.00 [ ] 0.890 100000 FA
[38 empty] | 0.89 | [14 empty] | 0.89
BID ITEM = 12 CLIENT# = 12 Land Item SCHEDULE: 1 100 Description = CLEARING & GRUBBING Unit = SF Takeoff Quan: 29,939.000 Engr Quan: 29,939.000
012.01 CLEARING & GRUBBING Quan: 29,939.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 54 | [10 empty] | CH |  |  | Prod: | [5 empty] | 54.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02S | [5 empty] | SOD DISPOSAL | [13 empty] | 1 |  |  | 667.00 TCY | [7 empty] | 28 | [17 empty] | 18676 | [5 empty] | 18676
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 54.00 HR | [7 empty] | 51.051 | [21 empty] | 2757 |  | 2757
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 54.00 HR | [7 empty] | 52.3 | [21 empty] | 2824 |  | 2824
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 54.00 MH | [7 empty] | 77.06 | [8 empty] | 5435 | [14 empty] | 5435
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 108.00 MH | [7 empty] | 52.91 | [8 empty] | 7534 | [14 empty] | 7534
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 54.00 MH | [7 empty] | 74.56 | [8 empty] | 5262 | [14 empty] | 5262
$42,488.32 0.0072 MH/SF 216.00 MH [ 0.511 ] | [37 empty] | 18231 | [10 empty] | 18676 |  |  |  | 5581 |  | 42488
=====> Item Totals: 12 - CLEARING & GRUBBING $42,488.32 0.0072 MH/SF 216.00 MH [ 0.511 ] | [37 empty] | 18231 | [10 empty] | 18676 |  |  |  | 5581 |  | 42488
1.419 29939 SF | [37 empty] | 0.61 | [10 empty] | 0.62 |  |  |  | 0.19 |  | 1.42
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 13 CLIENT# = 13 Land Item SCHEDULE: 1 100 Description = REMOVE CEMENT CONCRETE SIDEWALK Unit = SY Takeoff Quan: 19,570.000 Engr Quan: 19,570.000
013.01 REMOVE CEMENT CONCRETE SIDEWALK Quan: 19,570.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
EA3 | [5 empty] | EARTHWORK 3 MAN CREW | [16 empty] | 900 | [7 empty] | CH |  |  | Prod: | [5 empty] | 900.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 3 |  | Eqp Pcs: |  | 2
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 4,133.40 TCY | [7 empty] | 29 | [17 empty] | 119869 | [5 empty] | 119869
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 900.00 HR | [7 empty] | 52.3 | [21 empty] | 47070 |  | 47070
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 900.00 HR | [7 empty] | 81.5 | [21 empty] | 73350 |  | 73350
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 900.00 MH | [7 empty] | 77.06 | [8 empty] | 95961 | [14 empty] | 95961
LAG | [5 empty] | General Laborer | [13 empty] | 1 |  |  | 900.00 MH | [7 empty] | 52.91 | [8 empty] | 66477 | [14 empty] | 66477
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 900.00 MH | [7 empty] | 74.56 | [8 empty] | 92909 | [14 empty] | 92909
$495,636.12 0.1379 MH/SY | [22 empty] | 2,700.00 MH | [7 empty] | [ 10.974 ] | [8 empty] | 255348 | [8 empty] | 119869 |  |  |  | 120420 |  | 495636
13.02 | [5 empty] | GRADING SIDEWALK | [16 empty] | Quan: 19,570.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EA3 | [5 empty] | EARTHWORK 3 MAN CREW | [16 empty] | 348.75 CH Prod: 348.7525 CH Lab Pcs: 3.00 Eqp Pcs: 2.00
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 348.75 HR | [7 empty] | 52.3 | [17 empty] | 18240 | [5 empty] | 18240
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 348.75 HR | [7 empty] | 81.5 | [17 empty] | 28423 | [5 empty] | 28423
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 348.75 MH | [7 empty] | 77.06 | [8 empty] | 35101 | [14 empty] | 35101
LAG | [5 empty] | General Laborer | [13 empty] | 1 |  |  | 348.75 MH | [7 empty] | 52.91 | [8 empty] | 24329 | [14 empty] | 24329
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 348.75 MH | [7 empty] | 74.56 | [8 empty] | 33986 | [14 empty] | 33986
$140,078.12 0.0534 MH/SY | [22 empty] | 1,046.25 MH | [7 empty] | [ 4.009 ] | [8 empty] | 93415 | [8 empty] | 46663 | [5 empty] | 140078
=====> Item Totals: 13 - REMOVE CEMENT CONCRETE SIDEWALK $635,714.24 0.1914 MH/SY 32.484 19570 SY
3,746.25 MH | [30 empty] | [ 14.983 ] 348,763 | [17 empty] | 119869 |  |  |  | 167083 |  |  |  | 635714
[31 empty] | 17.82 | [17 empty] | 6.13 |  |  |  | 8.54 |  |  |  | 32.48
BID ITEM = 14 CLIENT# = 14 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE PAVEMENT | [13 empty] | Unit = SY Takeoff Quan: 49,157.000 Engr Quan: 49,157.000
14.01 | [5 empty] | REMOVE PAVEMENT | [13 empty] | Quan: 49,157.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 1,520.40 CH Prod: 1,520.4039 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 38,197.00 TCY | [7 empty] | 29 | [17 empty] | 1107713 | [6 empty] | 1107713
3DEDUO2B | [5 empty] | TRUCKING BRICK MIX | [13 empty] | 1 |  |  | 4,931.00 TCY | [7 empty] | 29 | [17 empty] | 142999 | [6 empty] | 142999
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 1,520.40 HR | [7 empty] | 68.251 | [21 empty] | 103769 |  |  | 103769
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 1,520.40 HR | [7 empty] | 78 | [21 empty] | 118591 |  |  | 118591
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 1,520.40 HR | [7 empty] | 81.5 | [21 empty] | 123913 |  |  | 123913
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 1,520.40 MH | [7 empty] | 77.06 | [6 empty] | 162111 | [17 empty] | 162111
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 3,040.81 MH | [7 empty] | 52.91 | [6 empty] | 224605 | [17 empty] | 224605
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 3,040.81 MH | [7 empty] | 74.56 | [6 empty] | 313910 | [17 empty] | 313910
$2,297,610.01 0.1546 MH/SY 7,602.02 MH [ 11.98 ] | [37 empty] | 700625 | [10 empty] | 1250712 |  |  |  | 346273 |  |  | 2297610
=====> Item Totals: 14 - REMOVE PAVEMENT $2,297,610.01 0.1546 MH/SY 7,602.02 MH [ 11.98 ] | [37 empty] | 700625 | [10 empty] | 1250712 |  |  |  | 346273 |  |  | 2297610
46.740 49157 SY | [37 empty] | 14.25 | [10 empty] | 25.44 |  |  |  | 7.04 |  |  | 46.74
BID ITEM = 15 CLIENT# = 15 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC Unit = SY Takeoff Quan: 7,582.000 Engr Quan: 7,582.000
015.01 REMOVE PAVEMENT, OVER 14 INCH DEPTH, IN Quan: 7,582.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM Demo 5 Man Crew 454.37 CH Prod: 454.3799 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 3DEDU02C Concrete Trucking and Du 1.00 5,984.00 TCY 29.000 173,536 173,536
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  | Total
BID ITEM = 15 CLIENT# = 15 Land Item SCHEDULE: 1 100
Description = REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC Unit = | [33 empty] | SY | [5 empty] | Takeoff Quan: | [8 empty] | 7582 |  |  |  | Engr Quan: |  |  | 7582
3DEDUO2B TRUCKING BRICK MIX 1.00 912.00 TCY | [33 empty] | 29 | [14 empty] | 26448 | [6 empty] | 26448
3RAILDIS | [5 empty] | DISPOSAL OF RAIL | [13 empty] | 1 |  |  | 13,503.12 LF | [7 empty] | 2 | [17 empty] | 27006 | [6 empty] | 27006
3TIEDIS | [5 empty] | DISPOSAL RAIL TIE | [13 empty] | 1 |  |  | 3,375.78 LF | [7 empty] | 2 | [17 empty] | 6752 | [6 empty] | 6752
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 454.38 HR | [7 empty] | 68.251 | [21 empty] | 31012 |  |  | 31012
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 454.38 HR | [7 empty] | 78 | [21 empty] | 35442 |  |  | 35442
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 454.38 HR | [7 empty] | 81.5 | [21 empty] | 37032 |  |  | 37032
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 454.38 MH | [7 empty] | 77.06 | [8 empty] | 48448 | [15 empty] | 48448
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 908.76 MH | [7 empty] | 52.91 | [8 empty] | 67124 | [15 empty] | 67124
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 908.76 MH | [7 empty] | 74.56 | [8 empty] | 93813 | [15 empty] | 93813
546612.53 | [5 empty] | 0.2996 MH/SY | [13 empty] | 2,271.90 MH | [10 empty] | [ 23.213 ] 209,385 233,742 103,485 546,613
15.02 | [5 empty] | STELL YOKE REMOVAL | [24 empty] | Quan: 20.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
8LO950 | [5 empty] | ==> 950 Loader | [13 empty] | 1 |  |  | 80.00 HR | [7 empty] | 81.5 | [17 empty] | 6520 | [6 empty] | 6520
LAG | [5 empty] | ==> General Laborer | [13 empty] | 1 |  |  | 80.00 MH | [7 empty] | 52.91 | [8 empty] | 5581 | [15 empty] | 5581
$12,100.82 4.0000 MH/EA 80.00 MH | [30 empty] | [ 232.804 ] | [8 empty] | 5581 | [8 empty] | 6520 | [6 empty] | 12101
=====> Item Totals: 15 - REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC $558,713.35 0.3101 MH/SY 73.689 7582 SY
2,351.90 MH | [30 empty] | [ 23.827 ] 214,966 | [17 empty] | 233742 |  |  |  | 110005 |  |  |  | 558713
[31 empty] | 28.35 | [17 empty] | 30.83 |  |  |  | 14.51 |  |  |  | 73.69
BID ITEM = 16 CLIENT# = 16 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC Unit = SY Takeoff Quan: 5,742.000 Engr Quan: 5,742.000
016.01 REMOVE PAVEMENT, OVER 14 INCH DEPTH, IN Quan: 5,742.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 229.19 | [10 empty] | CH |  |  | Prod: | [5 empty] | 229.1911 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 5,001.00 TCY | [7 empty] | 29 | [17 empty] | 145029 | [5 empty] | 145029
3DEDUO2B | [5 empty] | TRUCKING BRICK MIX | [13 empty] | 1 |  |  | 741.00 TCY | [7 empty] | 29 | [17 empty] | 21489 | [5 empty] | 21489
3TIEDIS | [5 empty] | DISPOSAL RAIL TIE | [13 empty] | 1 |  |  | 2,583.24 LF | [7 empty] | 2 | [17 empty] | 5166 | [5 empty] | 5166
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 229.19 HR | [7 empty] | 68.251 | [21 empty] | 15642 |  | 15642
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 229.19 HR | [7 empty] | 78 | [21 empty] | 17877 |  | 17877
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 229.19 HR | [7 empty] | 81.5 | [21 empty] | 18679 |  | 18679
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 229.19 MH | [7 empty] | 77.06 | [8 empty] | 24437 | [14 empty] | 24437
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 458.38 MH | [7 empty] | 52.91 | [8 empty] | 33858 | [14 empty] | 33858
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 458.38 MH | [7 empty] | 74.56 | [8 empty] | 47320 | [14 empty] | 47320
$329,496.94 0.1995 MH/SY 1,145.95 MH [ 15.461 ] | [39 empty] | 105614 | [8 empty] | 171684 |  |  |  | 52198 |  | 329497
=====> Item Totals: 16 - REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC $329,496.94 0.1995 MH/SY 57.384 5742 SY
1,145.95 MH | [30 empty] | [ 15.461 ] 105,614 | [17 empty] | 171684 |  |  |  | 52198 |  |  |  | 329497
[31 empty] | 18.39 | [17 empty] | 29.9 |  |  |  | 9.09 |  |  |  | 57.38
BID ITEM = 17 CLIENT# = 17 Land Item SCHEDULE: 1 100 Description = REMOVE CURB Unit = LF Takeoff Quan: 1,489.000 Engr Quan: 1,489.000
17.01 | [5 empty] | REMOVE CURB | [24 empty] | Quan: |  |  | 1,489.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 25.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 25.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3DEDU02C | [5 empty] | Concrete Trucking and Du 1.00 | [16 empty] | 26.00 TCY | [7 empty] | 29 | [17 empty] | 754 | [7 empty] | 754
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 25.00 HR | [7 empty] | 51.051 | [21 empty] | 1276 |  |  |  | 1276
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 25.00 HR | [7 empty] | 52.3 | [21 empty] | 1307 |  |  |  | 1307
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 25.00 MH | [7 empty] | 77.06 | [10 empty] | 2516 | [14 empty] | 2516
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 50.00 MH | [7 empty] | 52.91 | [10 empty] | 3488 | [14 empty] | 3488
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 25.00 MH | [7 empty] | 74.56 | [10 empty] | 2436 | [14 empty] | 2436
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  | Total
BID ITEM = 17 CLIENT# = 17 Land Item SCHEDULE: 1 | [47 empty] | 100
Description = REMOVE CURB Unit = LF Takeoff Quan: | [47 empty] | 1489 |  |  |  |  | Engr Quan: |  |  | 1489
$11,778.22 0.0671 MH/LF 100.00 MH [ 4.755 ] | [37 empty] | 8440 | [9 empty] | 754 |  |  |  |  | 2584 |  |  | 11778
=====> Item Totals: 17 - REMOVE CURB $11,778.22 0.0671 MH/LF 100.00 MH [ 4.755 ] | [37 empty] | 8440 | [9 empty] | 754 |  |  |  |  | 2584 |  |  | 11778
7.910 1489 LF | [37 empty] | 5.67 | [9 empty] | 0.51 |  |  |  |  | 1.74 |  |  | 7.91
BID ITEM | [5 empty] | = |  | 18 | [5 empty] | CLIENT# = | [8 empty] | 18 | Land Item | [9 empty] | SCHEDULE: | [7 empty] | 1 100
Description = | [5 empty] | REMOVE PIPE | [7 empty] | Unit = | [19 empty] | LF Takeoff Quan: 2,284.000 Engr Quan: 2,284.000
18.01 | [5 empty] | REMOVE PIPE | [7 empty] | Quan: | [19 empty] | 2,284.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 153.69 | [7 empty] | CH |  |  | Prod: | [7 empty] | 153.6927 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3PIPEDIS | [5 empty] | PIPE DISPOSAL | [13 empty] | 1 |  |  | 2,284.00 LF | [7 empty] | 2 | [17 empty] | 4568 | [5 empty] | 4568
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 153.69 HR | [7 empty] | 51.051 | [21 empty] | 7846 |  | 7846
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 153.69 HR | [7 empty] | 52.3 | [21 empty] | 8038 |  | 8038
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 153.69 MH | [7 empty] | 77.06 | [6 empty] | 15469 | [16 empty] | 15469
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 153.69 MH | [7 empty] | 53.88 | [6 empty] | 10912 | [16 empty] | 10912
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 153.69 MH | [7 empty] | 74.56 | [6 empty] | 14977 | [16 empty] | 14977
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 153.69 MH | [7 empty] | 74.56 | [6 empty] | 14977 | [16 empty] | 14977
$76,786.80 0.2691 MH/LF 614.76 MH [ 20.73 ] | [37 empty] | 56335 | [10 empty] | 4568 |  |  |  | 15884 |  | 76787
=====> Item Totals: 18 - REMOVE PIPE $76,786.80 0.2691 MH/LF 614.76 MH [ 20.73 ] | [37 empty] | 56335 | [10 empty] | 4568 |  |  |  | 15884 |  | 76787
33.619 2284 LF | [37 empty] | 24.66 | [10 empty] | 2 |  |  |  | 6.95 |  | 33.62
BID ITEM = 19 CLIENT# = 19 Land Item SCHEDULE: 1 100 Description = REMOVE BRACKET ARM, ROADWAY LUMINAIRE Unit = EA Takeoff Quan: 57.000 Engr Quan: 57.000
019.01 REMOVE BRACKET ARM, ROADWAY LUMINAI Quan: 57.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 57.00 EA 210.000 11,970 11,970
BID ITEM = 20 CLIENT# = 20 Land Item SCHEDULE: 1 100 Description = REMOVE BRACKET ARM, PEDESTRIAN SCALE LUM Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
020.01 REMOVE BRACKET ARM, PEDESTRIAN SCALE Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 10.00 EA 210.000 2,100 2,100
BID ITEM = 21 CLIENT# = 21 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | REMOVE ALADDIN ARM ASSEMBLY | [24 empty] | Unit = |  |  | EA Takeoff Quan: 2.000 Engr Quan: 2.000
| 21.01 |  |  |  |  | REMOVE ALADDIN ARM ASSEMBLY | [24 empty] | Quan: |  |  | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 200.000 400 400
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [17 empty] | Pcs | [7 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 22 CLIENT# = 22 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE CATCH BASIN OR SAND BOX | [22 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
22.01 | [5 empty] | REMOVE CATCH BASIN OR SAND BOX | [22 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [22 empty] | 3 |  | CH | Prod: | [9 empty] | 3.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 3.00 HR | [5 empty] | 51.051 | [19 empty] | 153 | [5 empty] | 153
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 3.00 HR | [5 empty] | 52.3 | [19 empty] | 157 | [5 empty] | 157
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 3.00 MH | [5 empty] | 77.06 | [12 empty] | 302 | [12 empty] | 302
LAP | [5 empty] | Labor Underground Water | [12 empty] | 1 |  |  |  | 3.00 MH | [5 empty] | 53.88 | [12 empty] | 213 | [12 empty] | 213
OPB | [5 empty] | Operator - Backhoe | [12 empty] | 1 |  |  |  | 3.00 MH | [5 empty] | 74.56 | [12 empty] | 292 | [12 empty] | 292
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 3.00 MH | [5 empty] | 74.56 | [12 empty] | 292 | [12 empty] | 292
$1,409.67 4.0000 MH/EA 12.00 MH | [28 empty] | [ 308.067 ] | [12 empty] | 1100 | [6 empty] | 310 | [5 empty] | 1410
=====> Item $1,409.67 | [5 empty] | Totals: 22 - 4.0000 MH/EA | [12 empty] | REMOVE CATCH BASIN OR SAND BOX 12.00 MH [ 308.067 ] | [18 empty] | 1100 | [10 empty] | 310 | [5 empty] | 1410
469.89 | [5 empty] | 3 EA | [31 empty] | 366.55 | [10 empty] | 103.34 | [5 empty] | 469.89
BID ITEM = 23 CLIENT# = 23 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE CONDUIT RISER | [16 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
23.01 | [5 empty] | REMOVE CONDUIT RISER | [16 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [12 empty] | 1 |  |  |  | 1.00 EA | [7 empty] | 400 | [21 empty] | 400 |  |  |  | 400
BID ITEM = 24 CLIENT# = 24 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE DOWN GUY ASSEMBLY | [18 empty] | Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
24.01 | [5 empty] | REMOVE DOWN GUY ASSEMBLY | [18 empty] | Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [12 empty] | 1 | [5 empty] | 8.00 EA | [5 empty] | 250 | [21 empty] | 2000 |  |  |  | 2000
BID ITEM = 25 CLIENT# = 25 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE ELECTRICAL VAULT | [16 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
25.01 | [5 empty] | REMOVE ELECTRICAL VAULT | [16 empty] | Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [16 empty] | 8 | [7 empty] | CH | Prod: | [7 empty] | 8.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 52.3 | [19 empty] | 418 | [5 empty] | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [12 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 68.251 | [19 empty] | 546 | [5 empty] | 546
8LO950 | [5 empty] | 950 Loader | [12 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 81.5 | [19 empty] | 652 | [5 empty] | 652
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 77.06 | [10 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 16.00 MH | [5 empty] | 52.91 | [10 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 74.56 | [10 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader | [12 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 74.56 | [10 empty] | 780 | [14 empty] | 780
$5,096.95 20.0000 MH/EA 40.00 MH | [28 empty] | [ 1460.805 ] | [10 empty] | 3481 | [8 empty] | 1616 | [5 empty] | 5097
=====> Item Totals: 25 - REMOVE ELECTRICAL VAULT
5096.95 | [5 empty] | 20.0000 MH/EA | [12 empty] | 40.00 MH | [9 empty] | [ 1460.805 ] | [10 empty] | 3481 | [8 empty] | 1616 | [5 empty] | 5097
2548.475 | [5 empty] | 2 EA | [33 empty] | 1740.28 | [8 empty] | 808.2 | [5 empty] | 2548.48
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 26 CLIENT# = 26 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE FOUNDATION, PEDESTAL | [23 empty] | Unit = EA Takeoff Quan: 20.000 Engr Quan: 20.000
26.01 | [5 empty] | REMOVE FOUNDATION, PEDESTAL | [23 empty] | Quan: 20.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
EAS 2AGS17 | [5 empty] | Earthwork 4 Man Crew SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 20.0 52.63 TON | [6 empty] | 0 CH Prod: 20.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 25.750 1,494 1,494
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 52.63 TCY | [6 empty] | 29 | [14 empty] | 1526 | [11 empty] | 1526
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 20.00 HR | [6 empty] | 51.051 | [22 empty] | 1021 |  |  |  | 1021
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 20.00 HR | [6 empty] | 52.3 | [22 empty] | 1046 |  |  |  | 1046
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 20.00 MH | [6 empty] | 77.06 | [9 empty] | 2730 | [16 empty] | 2730
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 40.00 MH | [6 empty] | 52.91 | [9 empty] | 3775 | [16 empty] | 3775
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 20.00 MH | [6 empty] | 74.56 | [9 empty] | 2643 | [16 empty] | 2643
$14,234.39 4.0000 MH/EA 80.00 MH | [29 empty] | [ 386.16 ] | [9 empty] | 9147 |  |  |  |  | 1494 |  |  |  | 1526 |  |  |  | 2067 |  |  |  | 14234
=====> Item Totals: 26 - REMOVE FOUNDATION, PEDESTAL
$14,234.39 4.0000 MH/EA 80.00 MH | [29 empty] | [ 386.16 ] | [9 empty] | 9147 |  |  |  |  | 1494 |  |  |  | 1526 |  |  |  | 2067 |  |  |  | 14234
711.720 20 EA | [39 empty] | 457.35 |  |  |  |  | 74.71 |  |  |  | 76.31 |  |  |  | 103.35 |  |  |  | 711.72
BID ITEM = 27 CLIENT# = 27 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, PED PUSH BUTTON POST Unit = EA Takeoff Quan: 13.000 Engr Quan: 13.000
027.01 REMOVE FOUNDATION, PED PUSH BUTTON PO Quan: 13.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 3.25 | [10 empty] | CH |  |  | Prod: | [7 empty] | 3.2500 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 4.33 TCY | [5 empty] | 29 | [19 empty] | 126 | [5 empty] | 126
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 3.25 HR | [5 empty] | 51.051 | [23 empty] | 166 |  | 166
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 3.25 HR | [5 empty] | 52.3 | [23 empty] | 170 |  | 170
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 3.25 MH | [5 empty] | 77.06 | [12 empty] | 327 | [12 empty] | 327
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 6.50 MH | [5 empty] | 52.91 | [12 empty] | 453 | [12 empty] | 453
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 3.25 MH | [5 empty] | 74.56 | [12 empty] | 317 | [12 empty] | 317
$1,558.69 1.0000 MH/EA 13.00 MH | [28 empty] | [ 70.796 ] | [12 empty] | 1097 | [6 empty] | 126 |  |  |  | 336 |  | 1559
=====> Item Totals: 27 - REMOVE FOUNDAT $1,558.69 1.0000 MH/EA 13.00 MH | [28 empty] | ION, PED PUSH BUT [ 70.796 ] | [8 empty] | TON POST 1,097 | [10 empty] | 126 |  |  |  | 336 |  | 1559
119.899 13 EA | [37 empty] | 84.4 | [10 empty] | 9.66 |  |  |  | 25.84 |  | 119.9
BID ITEM = 28 CLIENT# = 28 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, METAL STRAIN POLE Unit = EA Takeoff Quan: 27.000 Engr Quan: 27.000
028.01 REMOVE FOUNDATION, METAL STRAIN POLE Quan: 27.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
EAS Earthwork 4 Man Crew 54.00 CH Prod: 54.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 86.40 TON | [7 empty] | 25.750 2,453 2,453
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 86.40 TCY | [7 empty] | 29 | [13 empty] | 2506 | [11 empty] | 2506
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 54.00 HR | [7 empty] | 51.051 | [21 empty] | 2757 |  |  |  | 2757
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 54.00 HR | [7 empty] | 52.3 | [21 empty] | 2824 |  |  |  | 2824
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 54.00 MH | [7 empty] | 77.06 | [8 empty] | 5758 | [16 empty] | 5758
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 108.00 MH | [7 empty] | 52.91 | [8 empty] | 7977 | [16 empty] | 7977
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 54.00 MH | [7 empty] | 74.56 | [8 empty] | 5575 | [16 empty] | 5575
29848.88 | [5 empty] | 8.0000 MH/EA | [13 empty] | 216.00 MH | [10 empty] | [ 600.71 ] | [8 empty] | 19309 |  |  |  |  | 2453 |  |  |  | 2506 |  |  |  | 5581 |  |  |  | 29849
=====> Item Totals: 28 - REMOVE FOUNDATION, METAL STRAIN POLE
$29,848.88 8.0000 MH/EA 216.00 MH | [30 empty] | [ 600.71 ] | [8 empty] | 19309 |  |  |  |  | 2453 |  |  |  | 2506 |  |  |  | 5581 |  |  |  | 29849
1,105.514 27 EA | [39 empty] | 715.17 |  |  |  |  | 90.85 |  |  |  | 92.8 |  |  |  | 206.7 |  |  |  | 1105.51
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 29 CLIENT# = 29 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE FOUNDATION, FULL-DEPTH, METAL POL | [24 empty] | Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
29.01 | [5 empty] | REMOVE FOUNDATION, FULL-DEPTH, METAL | [24 empty] | Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 32 | [10 empty] | CH | Prod: 32.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 176.00 TON | [7 empty] | 25.750 4,997 4,997
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 176.00 TCY | [7 empty] | 29 | [13 empty] | 5104 | [11 empty] | 5104
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 32.00 HR | [7 empty] | 68.251 | [21 empty] | 2184 |  |  |  | 2184
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 32.00 HR | [7 empty] | 78 | [21 empty] | 2496 |  |  |  | 2496
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 32.00 HR | [7 empty] | 81.5 | [21 empty] | 2608 |  |  |  | 2608
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 32.00 MH | [7 empty] | 77.06 | [8 empty] | 3412 | [16 empty] | 3412
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 64.00 MH | [7 empty] | 52.91 | [8 empty] | 4727 | [16 empty] | 4727
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 64.00 MH | [7 empty] | 74.56 | [8 empty] | 6607 | [16 empty] | 6607
$32,134.65 40.0000 MH/EA 160.00 MH | [30 empty] | [ 3098.758 ] | [8 empty] | 14746 |  |  |  |  | 4997 |  |  |  | 5104 |  |  |  | 7288 |  |  |  | 32135
=====> Item Totals: 29 - REMOVE FOUNDATION, FULL-DEPTH, METAL POL $32,134.65 40.0000 MH/EA 160.00 MH [ 3098.758 ] 14,746 4,997 5,104 7,288 32,135 8,033.663 4 EA 3,686.53 1,249.13 1,276.00 1,822.01 8,033.66
BID ITEM = 30 CLIENT# = 30 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, STREET LIGHT POLE Unit = EA Takeoff Quan: 36.000 Engr Quan: 36.000
030.01 REMOVE FOUNDATION, STREET LIGHT POLE Quan: 36.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
EAS Earthwork 4 Man Crew 36.00 CH Prod: 36.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 115.20 TON | [7 empty] | 25.750 3,270 3,270
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 115.20 TCY | [7 empty] | 29 | [13 empty] | 3341 | [11 empty] | 3341
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 36.00 HR | [7 empty] | 51.051 | [21 empty] | 1838 |  |  |  | 1838
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 36.00 HR | [7 empty] | 52.3 | [21 empty] | 1883 |  |  |  | 1883
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 36.00 MH | [7 empty] | 77.06 | [8 empty] | 3838 | [16 empty] | 3838
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 72.00 MH | [7 empty] | 52.91 | [8 empty] | 5318 | [16 empty] | 5318
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 36.00 MH | [7 empty] | 74.56 | [8 empty] | 3716 | [16 empty] | 3716
$23,204.87 4.0000 MH/EA 144.00 MH | [30 empty] | [ 300.355 ] | [8 empty] | 12873 |  |  |  |  | 3270 |  |  |  | 3341 |  |  |  | 3721 |  |  |  | 23205
=====> Item Totals: 30 - REMOVE FOUNDATION, STREET LIGHT POLE
$23,204.87 4.0000 MH/EA 144.00 MH | [30 empty] | [ 300.355 ] | [8 empty] | 12873 |  |  |  |  | 3270 |  |  |  | 3341 |  |  |  | 3721 |  |  |  | 23205
644.580 36 EA | [39 empty] | 357.58 |  |  |  |  | 90.85 |  |  |  | 92.8 |  |  |  | 103.35 |  |  |  | 644.58
BID ITEM = 31 CLIENT# = 31 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, STEEL MAST ARM POLE Unit = EA Takeoff Quan: 19.000 Engr Quan: 19.000
031.01 REMOVE FOUNDATION, STEEL MAST ARM POL Quan: 19.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
EAS Earthwork 4 Man Crew 38.00 CH Prod: 38.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 112.00 TON | [7 empty] | 25.750 3,180 3,180
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 112.00 TCY | [7 empty] | 29 | [13 empty] | 3248 | [11 empty] | 3248
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 38.00 HR | [7 empty] | 51.051 | [21 empty] | 1940 |  |  |  | 1940
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 38.00 HR | [7 empty] | 52.3 | [21 empty] | 1987 |  |  |  | 1987
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 38.00 MH | [7 empty] | 77.06 | [8 empty] | 5186 | [16 empty] | 5186
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 76.00 MH | [7 empty] | 52.91 | [8 empty] | 7172 | [16 empty] | 7172
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 38.00 MH | [7 empty] | 74.56 | [8 empty] | 5021 | [16 empty] | 5021
$27,734.17 8.0000 MH/EA 152.00 MH | [30 empty] | [ 772.32 ] | [8 empty] | 17379 |  |  |  |  | 3180 |  |  |  | 3248 |  |  |  | 3927 |  |  |  | 27734
=====> Item Totals: 31 - REMOVE FOUNDATION, STEEL MAST ARM POLE
| Activity Desc Resource | [17 empty] | Pcs |  |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 31 CLIENT# = 31 Land Item SCHEDULE: 1 100
| Description = REMOVE FOUNDATION, STEEL MAST ARM POLE Unit = | [32 empty] | EA | [5 empty] | Takeoff Quan: | [8 empty] | 19 |  |  |  | Engr Quan: |  |  |  | 19
| $27,734.17 8.0000 MH/EA 152.00 MH | [32 empty] | [ 772.32 ] | [5 empty] | 17,379 3,180 | [8 empty] | 3248 |  |  |  | 3927 |  |  |  | 27734
1,459.693 19 EA 914.70 167.35 170.95 206.70 1,459.69
BID ITEM = 32 CLIENT# = 32 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE FOUNDATION, PEDESTRIAN LIGHT POLE | [24 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
32.01 | [5 empty] | REMOVE FOUNDATION, PEDESTRIAN LIGHT P | [24 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [12 empty] | 1 | [11 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 1.00 HR | [5 empty] | 51.051 | [19 empty] | 51 | [5 empty] | 51
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 1.00 HR | [5 empty] | 52.3 | [19 empty] | 52 | [5 empty] | 52
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 1.00 MH | [5 empty] | 77.06 | [12 empty] | 136 | [12 empty] | 136
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 2.00 MH | [5 empty] | 52.91 | [12 empty] | 189 | [12 empty] | 189
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 1.00 MH | [5 empty] | 74.56 | [12 empty] | 132 | [12 empty] | 132
$560.69 4.0000 MH/EA 4.00 MH | [28 empty] | [ 386.16 ] | [12 empty] | 457 | [6 empty] | 103 | [5 empty] | 561
=====> Item $560.69 | [5 empty] | Totals: 32 - 4.0000 MH/EA | [12 empty] | REMOVE FOUNDAT 4.00 MH | [9 empty] | ION, PEDESTRIAN L [ 386.16 ] | [8 empty] | IGHT POLE 457 | [10 empty] | 103 | [5 empty] | 561
560.69 | [5 empty] | 1 EA | [31 empty] | 457.36 | [10 empty] | 103.33 | [5 empty] | 560.69
BID ITEM = 33 CLIENT# = 33 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, SERVICE CABINET Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
33.01 | [5 empty] | REMOVE FOUNDATION, SERVICE CABINET | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [17 empty] | 1 | [6 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3DEDU02C | [5 empty] | Concrete Trucking and Du | [12 empty] | 1 |  |  |  |  | 5.00 TCY 29.000 | [24 empty] | 145 | [7 empty] | 145
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  |  | 1.00 HR 51.051 | [28 empty] | 51 |  |  |  | 51
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  |  | 1.00 HR 52.300 | [28 empty] | 52 |  |  |  | 52
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  |  | 1.00 MH 77.060 | [17 empty] | 136 | [14 empty] | 136
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  |  | 2.00 MH 52.910 | [17 empty] | 189 | [14 empty] | 189
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  |  | 1.00 MH 74.560 | [17 empty] | 132 | [14 empty] | 132
$705.69 4.0000 MH/EA 4.00 MH | [23 empty] | [ 386.16 ] | [17 empty] | 457 | [6 empty] | 145 |  |  |  | 103 |  |  |  | 706
=====> Item Totals: 33 - REMOVE FOUNDATION, SERVICE CABINET
705.69 | [5 empty] | 4.0000 MH/EA | [12 empty] | 4.00 MH |  |  |  |  | [ 386.16 ] | [15 empty] | 457 | [8 empty] | 145 |  |  |  | 103 |  |  |  | 706
705.69 | [5 empty] | 1 EA | [33 empty] | 457.36 | [8 empty] | 145 |  |  |  | 103.33 |  |  |  | 705.69
BID ITEM = 34 CLIENT# = 34 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, TRAFFIC SIGNAL CONTRO Unit = EA Takeoff Quan: 24.000 Engr Quan: 24.000
034.01 REMOVE FOUNDATION, TRAFFIC SIGNAL CON Quan: 24.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [12 empty] | 24 | [11 empty] | CH |  |  | Prod: | [5 empty] | 24.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02C | [5 empty] | Concrete Trucking and Du | [12 empty] | 1 |  |  |  | 27.13 TCY | [7 empty] | 29 | [17 empty] | 787 | [5 empty] | 787
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 24.00 HR | [7 empty] | 51.051 | [21 empty] | 1225 |  | 1225
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 24.00 HR | [7 empty] | 52.3 | [21 empty] | 1255 |  | 1255
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 24.00 MH | [7 empty] | 77.06 | [8 empty] | 3276 | [14 empty] | 3276
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 48.00 MH | [7 empty] | 52.91 | [8 empty] | 4530 | [14 empty] | 4530
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 24.00 MH | [7 empty] | 74.56 | [8 empty] | 3171 | [14 empty] | 3171
14243.55 | [5 empty] | 4.0000 MH/EA | [12 empty] | 96.00 MH | [11 empty] | [ 386.16 ] | [8 empty] | 10976 | [8 empty] | 787 |  |  |  | 2480 |  | 14244
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 34 CLIENT# = 34 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, TRAFFIC SIGNAL CONTRO Unit = EA Takeoff Quan: 24.000 Engr Quan: 24.000 =====> Item Totals: 34 - REMOVE FOUNDATION, TRAFFIC SIGNAL CONTRO $14,243.55 4.0000 MH/EA 593.481 24 EA
96.00 MH | [30 empty] | [ 386.16 ] | [8 empty] | 10976 | [8 empty] | 787 |  |  |  | 2480 |  |  |  | 14244
[40 empty] | 457.35 | [8 empty] | 32.78 |  |  |  | 103.35 |  |  |  | 593.48
BID ITEM = 35 CLIENT# = 35 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE GATE VALVE | [13 empty] | Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
35.01 | [5 empty] | REMOVE GATE VALVE | [13 empty] | Quan: 21.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 12.00 CH Prod: 12.0000 CH Lab Pcs: 5.00 Eqp Pcs: | [56 empty] | 3
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 68.251 | [21 empty] | 819 |  |  |  | 819
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 78 | [21 empty] | 936 |  |  |  | 936
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 81.5 | [21 empty] | 978 |  |  |  | 978
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 77.06 | [6 empty] | 1208 | [18 empty] | 1208
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 24.00 MH | [7 empty] | 53.88 | [6 empty] | 1704 | [18 empty] | 1704
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 74.56 | [6 empty] | 1169 | [18 empty] | 1169
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 74.56 | [6 empty] | 1169 | [18 empty] | 1169
$7,983.59 2.8571 MH/EA 60.00 MH | [30 empty] | [ 209.905 ] | [6 empty] | 5251 | [14 empty] | 2733 |  |  |  | 7984
=====> Item Totals: 35 - REMOVE GATE VALVE $7,983.59 2.8571 MH/EA 60.00 MH [ 209.905 ] | [37 empty] | 5251 | [14 empty] | 2733 |  |  |  | 7984
380.171 21 EA | [37 empty] | 250.03 | [14 empty] | 130.14 |  |  |  | 380.17
BID ITEM = 36 CLIENT# = 36 Land Item SCHEDULE: 1 100 Description = REMOVE HANDHOLE Unit = EA Takeoff Quan: 111.000 Engr Quan: 111.000
36.01 | [5 empty] | REMOVE HANDHOLE | [24 empty] | Quan: |  |  | 111.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 20.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 20.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3DEDU02C | [5 empty] | Concrete Trucking and Du 1.00 | [16 empty] | 25.23 TCY | [7 empty] | 29 | [17 empty] | 732 | [7 empty] | 732
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 20.00 HR | [7 empty] | 51.051 | [21 empty] | 1021 |  |  |  | 1021
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 20.00 HR | [7 empty] | 52.3 | [21 empty] | 1046 |  |  |  | 1046
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 20.00 MH | [7 empty] | 77.06 | [10 empty] | 2132 | [14 empty] | 2132
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 40.00 MH | [7 empty] | 52.91 | [10 empty] | 2955 | [14 empty] | 2955
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 20.00 MH | [7 empty] | 74.56 | [10 empty] | 2065 | [14 empty] | 2065
$9,950.34 0.7207 MH/EA 80.00 MH | [30 empty] | [ 54.118 ] | [10 empty] | 7152 | [6 empty] | 732 |  |  |  | 2067 |  |  |  | 9950
=====> Item Totals: 36 - REMOVE HANDHOLE
$9,950.34 0.7207 MH/EA 80.00 MH | [30 empty] | [ 54.118 ] | [10 empty] | 7152 | [6 empty] | 732 |  |  |  | 2067 |  |  |  | 9950
89.643 111 EA | [41 empty] | 64.43 | [6 empty] | 6.59 |  |  |  | 18.62 |  |  |  | 89.64
BID ITEM = 37 CLIENT# = 37 Land Item SCHEDULE: 1 100 Description = REMOVE HYDRANT Unit = EA Takeoff Quan: 13.000 Engr Quan: 13.000
37.01 | [5 empty] | REMOVE HYDRANT | [24 empty] | Quan: |  |  | 13.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man 26.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 26.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 26.00 HR | [5 empty] | 68.251 | [23 empty] | 1775 |  |  |  | 1775
8EX200 | [5 empty] | 200 Excavator 1.00 | [16 empty] | 26.00 HR | [5 empty] | 78 | [23 empty] | 2028 |  |  |  | 2028
8LO950 | [5 empty] | 950 Loader 1.00 | [16 empty] | 26.00 HR | [5 empty] | 81.5 | [23 empty] | 2119 |  |  |  | 2119
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 26.00 MH | [5 empty] | 77.06 | [12 empty] | 2617 | [14 empty] | 2617
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 37 CLIENT# = 37 Land Item SCHEDULE: 1 100 Description = REMOVE HYDRANT Unit = EA Takeoff Quan: 13.000 Engr Quan: 13.000
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 52.00 MH | [7 empty] | 53.88 | [6 empty] | 3692 | [14 empty] | 3692
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 26.00 MH | [7 empty] | 74.56 | [6 empty] | 2534 | [14 empty] | 2534
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 26.00 MH | [7 empty] | 74.56 | [6 empty] | 2534 | [14 empty] | 2534
$17,297.80 10.0000 MH/EA 130.00 MH [ 734.669 ] | [37 empty] | 11376 | [14 empty] | 5922 |  |  |  | 17298
=====> Item Totals: 37 - REMOVE HYDRANT $17,297.80 10.0000 MH/EA 130.00 MH [ 734.669 ] | [37 empty] | 11376 | [14 empty] | 5922 |  |  |  | 17298
1,330.600 13 EA | [37 empty] | 875.1 | [14 empty] | 455.5 |  |  |  | 1330.6
BID ITEM = 38 CLIENT# = 38 Land Item SCHEDULE: 1 100 Description = REMOVE INLET Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
38.01 | [5 empty] | REMOVE INLET | [24 empty] | Quan: |  |  | 4.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man 3.90 | [24 empty] | CH |  |  | Prod: | [7 empty] | 3.9024 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 3.90 HR | [5 empty] | 51.051 | [23 empty] | 199 |  |  |  | 199
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 3.90 HR | [5 empty] | 52.3 | [23 empty] | 204 |  |  |  | 204
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 3.90 MH | [5 empty] | 77.06 | [12 empty] | 532 | [14 empty] | 532
LAP | [5 empty] | Labor Underground Water 1.00 | [16 empty] | 3.90 MH | [5 empty] | 53.88 | [12 empty] | 375 | [14 empty] | 375
OPB | [5 empty] | Operator - Backhoe 1.00 | [16 empty] | 3.90 MH | [5 empty] | 74.56 | [12 empty] | 515 | [14 empty] | 515
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 3.90 MH | [5 empty] | 74.56 | [12 empty] | 515 | [14 empty] | 515
$2,340.58 3.9000 MH/EA 15.60 MH | [28 empty] | [ 409.59 ] | [12 empty] | 1938 | [10 empty] | 403 |  |  |  | 2341
=====> Item Totals: 38 - REMOVE INLET
2340.58 | [5 empty] | 3.9000 MH/EA 15.60 MH | [22 empty] | [ 409.59 ] | [10 empty] | 1938 | [12 empty] | 403 |  |  |  | 2341
585.145 | [5 empty] | 4 EA | [33 empty] | 484.38 | [12 empty] | 100.76 |  |  |  | 585.15
BID ITEM = 39 CLIENT# = 39 Land Item SCHEDULE: 1 100 Description = REMOVE LUMINAIRE, ROADWAY Unit = EA Takeoff Quan: 77.000 Engr Quan: 77.000
4ELEC Electrical sub 1.00 77.00 EA 210.000 16,170 16,170
BID ITEM = 40 CLIENT# = 40 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE PAVEMENT INCLUDING RAIL AND CABLE Unit = | [27 empty] | SY Takeoff Quan: 3,648.000 Engr Quan: 3,648.000
40.01 | [5 empty] | REMOVE PAVEMENT INCLUDING RAIL AND CA Quan: | [27 empty] | 3,648.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 344 | [10 empty] | CH |  |  | Prod: | [5 empty] | 344.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 2,963.00 TCY | [7 empty] | 29 | [17 empty] | 85927 | [5 empty] | 85927
3DEDUO2B | [5 empty] | TRUCKING BRICK MIX | [13 empty] | 1 |  |  | 685.00 TCY | [7 empty] | 29 | [17 empty] | 19865 | [5 empty] | 19865
3RAILDIS | [5 empty] | DISPOSAL OF RAIL | [13 empty] | 1 |  |  | 7,000.00 LF | [7 empty] | 2 | [17 empty] | 14000 | [5 empty] | 14000
3TIEDIS | [5 empty] | DISPOSAL RAIL TIE | [13 empty] | 1 |  |  | 1,635.00 LF | [7 empty] | 2 | [17 empty] | 3270 | [5 empty] | 3270
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 344.00 HR | [7 empty] | 68.251 | [21 empty] | 23478 |  | 23478
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 344.00 HR | [7 empty] | 78 | [21 empty] | 26832 |  | 26832
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 344.00 HR | [7 empty] | 81.5 | [21 empty] | 28036 |  | 28036
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 344.00 MH | [7 empty] | 77.06 | [8 empty] | 34623 | [14 empty] | 34623
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 688.00 MH | [7 empty] | 52.91 | [8 empty] | 47995 | [14 empty] | 47995
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 688.00 MH | [7 empty] | 74.56 | [8 empty] | 67046 | [14 empty] | 67046
$351,071.74 0.4714 MH/SY 1,720.00 MH [ 34.438 ] | [39 empty] | 149663 | [8 empty] | 123062 |  |  |  | 78346 |  | 351072
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 40 CLIENT# = 40 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT INCLUDING RAIL AND CABLE Unit = SY Takeoff Quan: 3,648.000 Engr Quan: 3,648.000 =====> Item Totals: 40 - REMOVE PAVEMENT INCLUDING RAIL AND CABLE $351,071.74 0.4714 MH/SY 96.237 3648 SY
1,720.00 MH | [30 empty] | [ 34.438 ] 149,663 | [17 empty] | 123062 |  |  |  | 78346 |  |  |  | 351072
[31 empty] | 41.03 | [17 empty] | 33.73 |  |  |  | 21.48 |  |  |  | 96.24
BID ITEM = 41 CLIENT# = 41 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE MAINTENANCE HOLE | [18 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
41.01 | [5 empty] | REMOVE MAINTENANCE HOLE | [18 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [18 empty] | 12 | [5 empty] | CH | Prod: | [7 empty] | 12.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  |  |  | 21.00 TCY | [5 empty] | 29 | [17 empty] | 609 | [5 empty] | 609
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 12.00 HR | [5 empty] | 68.251 | [21 empty] | 819 |  | 819
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 12.00 HR | [5 empty] | 78 | [21 empty] | 936 |  | 936
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 12.00 HR | [5 empty] | 81.5 | [21 empty] | 978 |  | 978
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 12.00 MH | [5 empty] | 77.06 | [8 empty] | 1208 | [14 empty] | 1208
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 24.00 MH | [5 empty] | 53.88 | [8 empty] | 1704 | [14 empty] | 1704
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 12.00 MH | [5 empty] | 74.56 | [8 empty] | 1169 | [14 empty] | 1169
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 12.00 MH | [5 empty] | 74.56 | [8 empty] | 1169 | [14 empty] | 1169
$8,592.59 20.0000 MH/EA 60.00 MH | [30 empty] | [ 1469.333 ] | [8 empty] | 5251 | [8 empty] | 609 |  |  |  | 2733 |  | 8593
=====> Item Totals: 41 - REMOVE MAINTENANCE HOLE
8592.59 | [5 empty] | 20.0000 MH/EA | [13 empty] | 60.00 MH | [10 empty] | [ 1469.333 ] | [8 empty] | 5251 | [8 empty] | 609 |  |  |  | 2733 |  | 8593
2864.197 | [5 empty] | 3 EA | [33 empty] | 1750.2 | [8 empty] | 203 |  |  |  | 911 |  | 2864.2
BID ITEM = 42 CLIENT# = 42 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE PEDESTAL | [23 empty] | Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000
42.01 |  |  | REMOVE PEDESTAL | [23 empty] | Quan: 22.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC |  |  | Electrical sub | [10 empty] | 1 |  |  | 22.00 EA | [9 empty] | 400.000 8,800 8,800
BID ITEM = 43 CLIENT# = 43 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE POLE, METAL STRAIN | [18 empty] | Unit = EA Takeoff Quan: 24.000 Engr Quan: 24.000
43.01 | [5 empty] | REMOVE POLE, METAL STRAIN | [18 empty] | Quan: 24.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  |  |  | 24.00 EA | [5 empty] | 1600 | [21 empty] | 38400 |  |  |  | 38400
BID ITEM = 44 CLIENT# = 44 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE MAST ARM | [13 empty] | Unit = | [13 empty] | EA Takeoff Quan: 2.000 Engr Quan: 2.000
44.01 | [5 empty] | REMOVE MAST ARM | [13 empty] | Quan: | [13 empty] | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 2.00 EA | [7 empty] | 1,600.000 3,200 3,200
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 45 CLIENT# = 45 Land Item SCHEDULE: 1 100 Description = REMOVE POLE, STREET LIGHT Unit = EA Takeoff Quan: 31.000 Engr Quan: 31.000
4ELEC Electrical sub 1.00 31.00 EA 400.000 12,400 12,400
BID ITEM = 46 CLIENT# = 46 Land Item SCHEDULE: 1 100 Description = REMOVE POLE, STEEL MAST ARM Unit = EA Takeoff Quan: 19.000 Engr Quan: 19.000
4ELEC Electrical sub 1.00 19.00 EA 1,600.000 30,400 30,400
BID ITEM = 47 CLIENT# = 47 Land Item SCHEDULE: 1 100 Description = REMOVE POLE, PEDESTRIAN LIGHT Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
4ELEC Electrical sub 1.00 2.00 EA 400.000 800 800
BID ITEM = 48 CLIENT# = 48 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE POLE, WOOD | [23 empty] | Unit = EA Takeoff Quan: 19.000 Engr Quan: 19.000
48.01 |  |  | REMOVE POLE, WOOD | [23 empty] | Quan: 19.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC |  |  | Electrical sub | [10 empty] | 1 |  |  | 19.00 EA | [9 empty] | 390.000 7,410 7,410
BID ITEM = 49 CLIENT# = 49 Land Item SCHEDULE: 1 100 Description = REMOVE POST, BUS ZONE Unit = EA Takeoff Quan: 24.000 Engr Quan: 24.000
049.01 REMOVE POST, BUS ZONE | [26 empty] | Quan: |  |  | 24.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [16 empty] | 12 | [9 empty] | CH |  |  | Prod: | [5 empty] | 12.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 12.00 MH | [16 empty] | 52.91 | [18 empty] | 837 | [13 empty] | 837
$837.12 0.5000 MH/EA 12.00 MH | [16 empty] | [ 29.1 ] | [18 empty] | 837 | [13 empty] | 837
=====> Item Totals: 49 - REMOVE POST, BUS ZONE $837.12 0.5000 MH/EA 12.00 MH [ 29.1 ] 837 837 34.880 24 EA 34.88 34.88
BID ITEM = 50 CLIENT# = 50 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE POST, PEDESTRIAN PUSHBUTTON | [23 empty] | Unit = |  |  | EA Takeoff Quan: 13.000 Engr Quan: 13.000
50.01 |  |  | REMOVE POST, PEDESTRIAN PUSHBUTTON | [23 empty] | Quan: |  |  | 13.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 13.00 EA 310.000 4,030 4,030
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract Total
BID ITEM = 51 CLIENT# = 51 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE POST, TRAFFIC SIGN | [24 empty] | Unit = |  |  | EA Takeoff Quan: 233.000 Engr Quan: 233.000
51.01 | [5 empty] | REMOVE POST, TRAFFIC SIGN | [24 empty] | Quan: |  |  | 233.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ | [5 empty] | SIGN CREW | [13 empty] | 116.50 CH Prod: 116.5000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG | [5 empty] | General Laborer | [13 empty] | 1.00 116.50 MH 52.910 8,127 8,127
8127.08 | [5 empty] | 0.5000 MH/EA 116.50 MH [ 29.101 ] 8,127 8,127
=====> Item Totals: $8,127.08 | [9 empty] | 51 0.5000 MH/EA | [6 empty] | - REMOVE POST, TRAFFIC SIGN 116.50 MH | [16 empty] | [ 29.101 ] |  |  |  | 8127 | [14 empty] | 8127
34.88 | [9 empty] | 233 EA | [27 empty] | 34.88 | [14 empty] | 34.88
BID ITEM = 52 CLIENT# = 52 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, STREET DESIGNATION Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000
052.01 REMOVE SIGN, STREET DESIGNATION | [26 empty] | Quan: |  |  | 22.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW 11.00 | [26 empty] | CH |  |  | Prod: | [5 empty] | 11.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 11.00 MH 52.910 | [35 empty] | 767 | [13 empty] | 767
$767.36 0.5000 MH/EA 11.00 MH [ 29.1 ] | [35 empty] | 767 | [13 empty] | 767
=====> Item Totals: 52 - REMOVE SIGN, STREET DESIGNATION
$767.36 0.5000 MH/EA 11.00 MH [ 29.1 ] | [35 empty] | 767 | [13 empty] | 767
34.880 22 EA | [35 empty] | 34.88 | [13 empty] | 34.88
BID ITEM = 53 CLIENT# = 53 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, ILLUMINATED SIGN Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
4ELEC Electrical sub 1.00 5.00 EA 570.000 2,850 2,850
BID ITEM = 54 CLIENT# = 54 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, BUS ZONE Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
054.01 REMOVE SIGN, BUS ZONE | [30 empty] | Quan: |  |  | 3.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [22 empty] | 1.5 | [7 empty] | CH |  |  | Prod: | [7 empty] | 1.5000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 1.50 MH | [22 empty] | 52.91 | [18 empty] | 105 | [10 empty] | 105
$104.64 0.5000 MH/EA 1.50 MH | [22 empty] | [ 29.1 ] | [18 empty] | 105 | [10 empty] | 105
=====> Item $104.64 | [6 empty] | Totals: 54 - REMOVE SIGN, BUS 0.5000 MH/EA 1.50 MH | [15 empty] | ZONE [ 29.1 ] | [14 empty] | 105 | [14 empty] | 105
34.88 | [6 empty] | 3 EA | [30 empty] | 34.88 | [14 empty] | 34.88
BID ITEM = 55 CLIENT# = 55 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE SIGN, STREET NAME, POLE MOUNTED | [23 empty] | Unit = |  |  | EA Takeoff Quan: 33.000 Engr Quan: 33.000
55.01 |  |  | REMOVE SIGN, STREET NAME | [23 empty] | Quan: |  |  | 33.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 55 CLIENT# = 55 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, STREET NAME, POLE MOUNTED Unit = EA Takeoff Quan: 33.000 Engr Quan: 33.000 ZZZ SIGN CREW 16.00 CH Prod: 16.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00 LAG General Laborer 1.00 $1,116.17 0.4848 MH/EA
16.00 MH | [30 empty] | 52.91 | [8 empty] | 1116 | [12 empty] | 1116
16.00 MH | [30 empty] | [ 28.219 ] | [8 empty] | 1116 | [12 empty] | 1116
=====> Item Totals: 55 - REMOVE SIGN, STREET NAME, POLE MOUNTED $1,116.17 0.4848 MH/EA 16.00 MH [ 28.219 ] 1,116 1,116 33.823 33 EA 33.82 33.82
BID ITEM = 56 CLIENT# = 56 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, OVERHEAD Unit = EA Takeoff Quan: 12.000 Engr Quan: 12.000
4ELEC Electrical sub 1.00 12.00 EA 50.000 600 600
BID ITEM = 57 CLIENT# = 57 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE SIGN, TRAFFIC | [13 empty] | Unit = | [13 empty] | EA Takeoff Quan: 341.000 Engr Quan: 341.000
57.01 | [5 empty] | REMOVE SIGN, TRAFFIC | [13 empty] | Quan: | [13 empty] | 341.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ | [5 empty] | SIGN CREW | [13 empty] | 170.50 CH Prod: 170.5000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG | [5 empty] | General Laborer | [13 empty] | 1.00 170.50 MH 52.910 11,894 11,894
11894.14 | [5 empty] | 0.5000 MH/EA 170.50 MH [ 29.1 ] 11,894 11,894
=====> Item Totals: 57 - REMOVE SIGN, TRAFFIC $11,894.14 0.5000 MH/EA 170.50 MH [ 29.1 ] 11,894 11,894 34.880 341 EA 34.88 34.88
BID ITEM = 58 CLIENT# = 58 Land Item SCHEDULE: 1 100 Description = REMOVE SIGN, STREET NAME Unit = EA Takeoff Quan: 13.000 Engr Quan: 13.000
058.01 REMOVE SIGN, STREET NAME | [30 empty] | Quan: |  |  | 13.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [24 empty] | 6.5 | [5 empty] | CH |  |  | Prod: | [7 empty] | 6.5000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 6.50 MH | [24 empty] | 52.91 | [16 empty] | 453 | [10 empty] | 453
$453.45 0.5000 MH/EA 6.50 MH | [24 empty] | [ 29.101 ] | [16 empty] | 453 | [10 empty] | 453
=====> $453.45 |  |  |  | Item Totals: | [5 empty] | 58 0.5000 MH/EA | [6 empty] | - REMOVE SIGN, STREET NAME 6.50 MH | [16 empty] | [ 29.101 ] |  |  |  | 453 | [14 empty] | 453
34.881 | [9 empty] | 13 EA | [27 empty] | 34.88 | [14 empty] | 34.88
BID ITEM = 59 CLIENT# = 59 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE SERVICE CABINET | [23 empty] | Unit = |  |  | EA Takeoff Quan: 1.000 Engr Quan: 1.000
59.01 |  |  | REMOVE SERVICE CABINET | [23 empty] | Quan: |  |  | 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 990.000 990 990
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 60 CLIENT# = 60 Land Item SCHEDULE: 1 100 Description = REMOVE TRAFFIC SIGNAL CONTROLLER CABINET Unit = EA Takeoff Quan: 26.000 Engr Quan: 26.000
060.01 REMOVE TRAFFIC SIGNAL CONTROLLER CABI Quan: 26.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 26.00 EA 990.000 25,740 25,740
BID ITEM = 61 CLIENT# = 61 Land Item SCHEDULE: 1 100 EA Takeoff Quan: 53.000 Engr Quan: 53.000
Description = |  |  | REMOVE TREE | [23 empty] | Unit =
61.01 |  |  | REMOVE TREE | [23 empty] | Quan:
3TREEREM |  |  | TREE REMOVAL | [10 empty] | 1 |  |  | 53.00 EA | [9 empty] | 2
350 | [37 empty] | 124550 | [14 empty] | 124550
[ ] | [37 empty] | 124550 | [14 empty] | 124550
[38 empty] | 2350 | [14 empty] | 2350
=====> Item Totals: 61 - REMOVE TREE $124,550.00 2,350.000 53 EA
BID ITEM = 62 CLIENT# = 62 Land Item SCHEDULE: 1 100
Description = | [6 empty] | REMOVE VALVE CHAMBER | [15 empty] | Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
62.01 | [6 empty] | REMOVE VALVE CHAMBER | [15 empty] | Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNM | [6 empty] | Unerground Utilities 6 Man | [15 empty] | 8 | [7 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
8EX135A | [6 empty] | 135 Excavator W/Attach | [11 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 68.251 | [19 empty] | 546 | [5 empty] | 546
8EX200 | [6 empty] | 200 Excavator | [11 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 78 | [19 empty] | 624 | [5 empty] | 624
8LO950 | [6 empty] | 950 Loader | [11 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 81.5 | [19 empty] | 652 | [5 empty] | 652
FOCI | [6 empty] | Civil Forman | [11 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 853 | [13 empty] | 853
LAP | [6 empty] | Labor Underground Water | [11 empty] | 2 |  |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1203 | [13 empty] | 1203
OPE | [6 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 826 | [13 empty] | 826
OPL | [6 empty] | Operator - Loader | [11 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 826 | [13 empty] | 826
$5,529.58 10.0000 MH/EA 40.00 MH | [28 empty] | [ 779.215 ] | [11 empty] | 3708 | [7 empty] | 1822 | [5 empty] | 5530
=====> Item $5,529.58 | [6 empty] | Totals: 62 - 10.0000 MH/EA | [11 empty] | REMOVE VALVE CHAMBER 40.00 MH [ 779.215 ] | [18 empty] | 3708 | [10 empty] | 1822 | [5 empty] | 5530
1382.395 | [6 empty] | 4 EA | [30 empty] | 926.9 | [10 empty] | 455.5 | [5 empty] | 1382.4
BID ITEM = 63 CLIENT# = 63 Land Item SCHEDULE: 1 100 Description = REMOVE VEHICLE SIGNAL HEAD Unit = EA Takeoff Quan: 200.000 Engr Quan: 200.000
4ELEC Electrical sub 1.00 200.00 EA 290.000 58,000 58,000
BID ITEM = 64 CLIENT# = 64 Land Item SCHEDULE: 1 100
Description = |  |  | REMOVE PEDESTRIAN SIGNAL HEAD | [23 empty] | Unit = |  |  | EA Takeoff Quan: 146.000 Engr Quan: 146.000
64.01 |  |  | REMOVE PEDESTRIAN SIGNAL HEAD | [23 empty] | Quan: |  |  | 146.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 146.00 EA 150.000 21,900 21,900
Activity |  |  | Desc | [13 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 65 CLIENT# = 65 Land Item SCHEDULE: 1 100 Description = REMOVE PEDESTRIAN PUSH BUTTON ASSEMBLY Unit = EA Takeoff Quan: 72.000 Engr Quan: 72.000
065.01 REMOVE PEDESTRIAN PUSH BUTTON ASSEMB Quan: 72.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 72.00 EA 90.000 6,480 6,480
BID ITEM = 66 CLIENT# = 66 Land Item SCHEDULE: 1 100 Description = REMOVE VIDEO DETECTION CAMERA Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
066.01 REMOVE VIDEO DETECTION CAMERA Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 5.00 EA 290.000 1,450 1,450
BID ITEM = 67 CLIENT# = 67 Land Item SCHEDULE: 1 100 Description = REMOVE BICYCLE PUSHBUTTON ASSEMBLY Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
067.01 REMOVE BICYCLE PUSHBUTTON ASSEMBLY Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 90.000 90 90
BID ITEM = 68 CLIENT# = 68 Land Item SCHEDULE: 1 100 Description = REMOVE EMERGENCY PRE-EMPT DETECTOR Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
068.01 REMOVE EMERGENCY PRE-EMPT DETECTOR Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 3.00 EA 110.000 330 330
BID ITEM = 69 CLIENT# = 69 Land Item SCHEDULE: 1 100 Description = REMOVE RRFB SYSTEM, (19TH & UNION) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
069.01 REMOVE RRFB SYSTEM, (19TH & UNION) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,090.000 3,090 3,090
BID ITEM = 70 CLIENT# = 70 Land Item SCHEDULE: 1 100 Description = SAWCUT CEMENT CONCRETE SIDEWALK, FULL DE Unit = LF Takeoff Quan: 6,831.000 Engr Quan: 6,831.000
070.01 SAWCUT CEMENT CONCRETE SIDEWALK, FUL Quan: 27,324.00 INFT Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4SAWC Sawcutting 1.00 27,324.00 INFT 0.580 15,848 15,848
BID ITEM = 71 CLIENT# = 71 Land Item SCHEDULE: 1 100 Description = SAWCUT RIGID PAVEMENT, FULL DEPTH Unit = LF Takeoff Quan: 19,472.000 Engr Quan: 19,472.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 71 CLIENT# = 71 Land Item SCHEDULE: 1 100 Description = SAWCUT RIGID PAVEMENT, FULL DEPTH Unit = LF Takeoff Quan: 19,472.000 Engr Quan: 19,472.000
071,01 SAWCUT RIGID PAVEMENT, FULL DEPTH Quan: 282,459.25 INFT Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4SAWC Sawcutting 1.00 282,459.24 INFT 0.680 192,072 192,072
BID ITEM = 72 CLIENT# = 72 Land Item SCHEDULE: 1 100 Description = ABANDON CATCH BASIN Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
UNS Underground Utilities 4 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS17 SEATTLE TYPE 1@110.2 1.00 20.00 TON 25.750 568 | [56 empty] | 568
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 51.051 | [17 empty] | 204 | [5 empty] | 204
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 52.3 | [17 empty] | 209 | [5 empty] | 209
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [8 empty] | 426 | [14 empty] | 426
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 53.88 | [8 empty] | 301 | [14 empty] | 301
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 413 | [14 empty] | 413
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 413 | [14 empty] | 413
$2,534.26 8.0000 MH/EA 16.00 MH | [30 empty] | [ 653.495 ] | [8 empty] | 1553 |  |  |  |  | 568 |  |  |  | 413 | [5 empty] | 2534
=====> Item Totals: 72 - ABANDON CATCH BASIN
2534.26 | [5 empty] | 8.0000 MH/EA | [13 empty] | 16.00 MH | [10 empty] | [ 653.495 ] | [8 empty] | 1553 |  |  |  |  | 568 |  |  |  | 413 | [5 empty] | 2534
1267.13 | [5 empty] | 2 EA | [33 empty] | 776.54 |  |  |  |  | 283.9 |  |  |  | 206.7 | [5 empty] | 1267.13
BID ITEM = 73 CLIENT# = 73 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ABANDON VALVE CHAMBER | [16 empty] | Unit = EA Takeoff Quan: 19.000 Engr Quan: 19.000
73.01 | [5 empty] | ABANDON VALVE CHAMBER | [16 empty] | Quan: 19.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2AGS17 | [5 empty] | Unerground Utilities 6 Man SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 19.0 50.00 TON | [6 empty] | 0 CH Prod: 19.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 25.750 1,419 1,419
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 19.00 HR | [6 empty] | 68.251 | [14 empty] | 1297 | [11 empty] | 1297
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 19.00 HR | [6 empty] | 78 | [14 empty] | 1482 | [11 empty] | 1482
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 19.00 HR | [6 empty] | 81.5 | [14 empty] | 1548 | [11 empty] | 1548
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 19.00 MH | [6 empty] | 77.06 | [7 empty] | 1912 | [18 empty] | 1912
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 38.00 MH | [6 empty] | 53.88 | [7 empty] | 2698 | [18 empty] | 2698
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 19.00 MH | [6 empty] | 74.56 | [7 empty] | 1852 | [18 empty] | 1852
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 19.00 MH | [6 empty] | 74.56 | [7 empty] | 1852 | [18 empty] | 1852
$14,060.15 5.0000 MH/EA 95.00 MH | [29 empty] | [ 367.333 ] | [7 empty] | 8313 | [6 empty] | 1419 | [7 empty] | 4327 |  |  |  | 14060
=====> Item Totals: | [9 empty] | 73 | [6 empty] | - ABANDON VALVE CHAMBER
14060.15 | [9 empty] | 5.0000 MH/EA | [6 empty] | 95.00 MH | [14 empty] | [ 367.333 ] | [5 empty] | 8313 | [6 empty] | 1419 | [7 empty] | 4327 |  |  |  | 14060
740.008 19 EA | [37 empty] | 437.55 | [6 empty] | 74.71 | [7 empty] | 227.75 |  |  |  | 740.01
BID ITEM | [5 empty] | = |  | 74 | [5 empty] | CLIENT# = | [8 empty] | 74 |  | Land Item SCHEDULE: 1 100
Description = | [5 empty] | ABANDON AND FILL PIPE | [22 empty] | Unit = LF Takeoff Quan: 1,282.000 Engr Quan: 1,282.000
74.01 | [5 empty] | ABANDON AND FILL PIPE | [22 empty] | Quan: 1,282.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS 2CRCDF | [5 empty] | Underground Utilities 4 Man CDF@110.25% 1.00 | [16 empty] | 37.29 CY | [5 empty] | 66.29 CH Prod: 66.2961 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 106.150 4,364 4,364
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  | Total
BID ITEM = 74 CLIENT# = 74 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ABANDON AND FILL PIPE | [24 empty] | Unit = |  |  | LF |  |  |  | Takeoff Quan: | [10 empty] | 1282 |  |  |  | Engr Quan: |  |  | 1282
3PUMPLINE | [5 empty] | LINE PUMP | [13 empty] | 1 |  |  | 41.44 HR | [10 empty] | 175 | [14 empty] | 7252 | [6 empty] | 7252
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 66.30 HR | [10 empty] | 51.051 | [18 empty] | 3385 |  |  | 3385
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 66.30 HR | [10 empty] | 52.3 | [18 empty] | 3467 |  |  | 3467
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 66.30 MH | [10 empty] | 77.06 |  |  |  | 6673 | [17 empty] | 6673
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 66.30 MH | [10 empty] | 53.88 |  |  |  | 4707 | [17 empty] | 4707
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 66.30 MH | [10 empty] | 74.56 |  |  |  | 6461 | [17 empty] | 6461
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 66.30 MH | [10 empty] | 74.56 |  |  |  | 6461 | [17 empty] | 6461
$42,770.40 0.2068 MH/LF 265.20 MH [ 15.932 ] | [37 empty] | 24302 | [6 empty] | 4364 |  |  |  | 7252 |  |  |  | 6852 |  |  | 42770
=====> Item Totals: 74 - ABANDON AND FILL PIPE $42,770.40 0.2068 MH/LF 265.20 MH [ 15.932 ] | [37 empty] | 24302 | [6 empty] | 4364 |  |  |  | 7252 |  |  |  | 6852 |  |  | 42770
33.362 1282 LF | [37 empty] | 18.96 | [6 empty] | 3.4 |  |  |  | 5.66 |  |  |  | 5.34 |  |  | 33.36
BID ITEM = 75 CLIENT# = 75 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL KCM SIGN Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
075.01 REMOVE, STORE AND REINSTALL KCM SIGN Quan: | [33 empty] | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW 1.00 CH | [33 empty] | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 1.00 MH | [33 empty] | 52.91 | [7 empty] | 70 | [10 empty] | 70
$69.76 1.0000 MH/EA 1.00 MH | [33 empty] | [ 58.2 ] | [7 empty] | 70 | [10 empty] | 70
=====> Item $69.76 | [5 empty] | Totals: 75 - REMOVE, STORE AND REINSTALL KCM 1.0000 MH/EA 1.00 MH [ 58.2 ] | [31 empty] | SIGN 70 | [14 empty] | 70
69.76 | [5 empty] | 1 EA | [31 empty] | 69.76 | [14 empty] | 69.76
BID ITEM = 76 CLIENT# = 76 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE, STORE AND REINSTALL MOSAIC TILE | [24 empty] | Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
76.01 | [5 empty] | REMOVE STOR MOSAIC TILE | [24 empty] | Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 3 | [10 empty] | CH |  |  | Prod: | [7 empty] | 3.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
4SAWC | [5 empty] | Sawcutting | [13 empty] | 1 |  |  | 216.00 INFT | [5 empty] | 0.58 | [25 empty] | 125 |  | 125
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 3.00 HR | [5 empty] | 51.051 | [19 empty] | 153 | [7 empty] | 153
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 3.00 HR | [5 empty] | 52.3 | [19 empty] | 157 | [7 empty] | 157
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 3.00 MH | [5 empty] | 77.06 | [12 empty] | 302 | [14 empty] | 302
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 6.00 MH | [5 empty] | 52.91 | [12 empty] | 419 | [14 empty] | 419
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 3.00 MH | [5 empty] | 74.56 | [12 empty] | 292 | [14 empty] | 292
1448.17 | [5 empty] | 2.0000 MH/EA | [13 empty] | 12.00 MH [ 141.593 ] 1,013 310 125 1,448
76.02 | [5 empty] | INSTALL MOSIAC TILE | [13 empty] | Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [13 empty] | 5 | [10 empty] | CH | Prod: | [8 empty] | 5.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 25.00 MH | [7 empty] | 64.98 | [9 empty] | 2130 | [7 empty] | 2130
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 5.00 MH | [7 empty] | 68.98 | [9 empty] | 452 | [7 empty] | 452
$2,581.51 5.0000 MH/EA 30.00 MH | [30 empty] | [ 361.057 ] | [9 empty] | 2582 | [7 empty] | 2582
=====> Item Totals: 76 - REMOVE, STORE AND REINSTALL MOSAIC TILE
4029.68 | [5 empty] | 7.0000 MH/EA | [13 empty] | 42.00 MH | [10 empty] | [ 502.65 ] | [9 empty] | 3594 | [7 empty] | 310 | [5 empty] | 125 |  | 4030
671.613 | [5 empty] | 6 EA | [34 empty] | 599.06 | [7 empty] | 51.67 | [5 empty] | 20.88 |  | 671.61
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM | [5 empty] | = |  | 77 | [5 empty] | CLIENT# = | [8 empty] | 77 | Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE SPAN WIRE | [22 empty] | Unit = LF Takeoff Quan: 2,230.000 Engr Quan: 2,230.000
77.01 | [5 empty] | REMOVE SPAN WIRE | [22 empty] | Quan: 2,230.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 2,230.00 LF | [5 empty] | 3.300 7,359 7,359
BID ITEM = 78 CLIENT# = 78 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL BIKE RACK Unit = EA Takeoff Quan: 36.000 Engr Quan: 36.000
078.01 REMOVE, STORE AND REINSTALL BIKE RACK Quan: 36.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 72.00 CH Prod: 72.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 LAG General Laborer 2.00 $10,045.48 4.0000 MH/ EA
144.00 MH | [30 empty] | 52.91 | [8 empty] | 10045 | [12 empty] | 10045
144.00 MH | [30 empty] | [ 232.804 ] | [8 empty] | 10045 | [12 empty] | 10045
=====> Item Totals: 78 - REMOVE, STORE AND REINSTALL BIKE RACK $10,045.48 4.0000 MH/ EA 144.00 MH [ 232.804 ] 10,045 10,045 279.041 36 EA 279.04 279.04
BID ITEM = 79 CLIENT# = 79 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL BOLLARD Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
079.01 REMOVE, STORE AND REINSTALL BOLLARD Quan: | [33 empty] | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 4.00 CH | [33 empty] | Prod: | [7 empty] | 4.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 8.00 MH | [33 empty] | 52.91 | [7 empty] | 558 | [10 empty] | 558
$558.08 8.0000 MH/EA 8.00 MH | [33 empty] | [ 465.61 ] | [7 empty] | 558 | [10 empty] | 558
=====> Item Totals: 79 - REMOVE, STORE AND REINSTALL BOLLARD
558.08 | [5 empty] | 8.0000 MH/EA | [16 empty] | 8.00 MH | [10 empty] | [ 465.61 ] | [5 empty] | 558 | [12 empty] | 558
558.08 | [5 empty] | 1 EA | [33 empty] | 558.08 | [12 empty] | 558.08
BID ITEM = 80 CLIENT# = 80 Land Item SCHEDULE: 1 100
Description = | [6 empty] | REMOVE, STORE AND REINSTALL BENCH | [22 empty] | Unit = |  |  |  | EA Takeoff Quan: 6.000 Engr Quan: 6.000
80.01 | [6 empty] | REMOVE, STORE AND REINSTALL BENCH | [22 empty] | Quan: |  |  |  | 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 12.00 CH Prod: 12.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 24.00 MH | [29 empty] | 52.91 | [7 empty] | 1674 | [14 empty] | 1674
$1,674.24 4.0000 MH/EA 24.00 MH | [29 empty] | [ 232.803 ] | [7 empty] | 1674 | [14 empty] | 1674
=====> Item $1,674.24 | [6 empty] | Totals: 80 - RE 4.0000 MH/EA | [14 empty] | MOVE, STORE AND 24.00 MH | [7 empty] | REINSTALL BENCH [ 232.803 ] 1,674 | [22 empty] | 1674
279.04 | [6 empty] | 6 EA | [30 empty] | 279.04 | [14 empty] | 279.04
BID ITEM = 81 CLIENT# = 81 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL LITTER RECEP Unit = EA Takeoff Quan: 14.000 Engr Quan: 14.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 81 CLIENT# = 81 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL LITTER RECEP Unit = EA Takeoff Quan: 14.000 Engr Quan: 14.000 ZZZZ SITE FURNISHINGS CREW 14.00 CH Prod: 14.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 LAG General Laborer 2.00 $1,953.29 2.0000 MH/EA
28.00 MH | [30 empty] | 52.91 | [8 empty] | 1953 | [12 empty] | 1953
28.00 MH | [30 empty] | [ 116.402 ] | [8 empty] | 1953 | [12 empty] | 1953
=====> Item Totals: 81 - REMOVE, STORE AND REINSTALL LITTER RECEP $1,953.29 2.0000 MH/EA 28.00 MH [ 116.402 ] 1,953 1,953 139.521 14 EA 139.52 139.52
BID ITEM = 82 CLIENT# = 82 Land Item SCHEDULE: 1 100 Description = SALVAGE, STORE AND REINSTALL BRICK PAVER Unit = SY Takeoff Quan: 43.000 Engr Quan: 43.000
82.01 | [5 empty] | REMOVE BRICK PAVERS | [24 empty] | Quan: |  |  | 43.00 SY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 4 | [7 empty] | CH |  |  | Prod: | [7 empty] | 4.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 4.00 HR 51.051 | [29 empty] | 204 |  |  |  | 204
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 4.00 HR 52.300 | [29 empty] | 209 |  |  |  | 209
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH 77.060 | [18 empty] | 403 | [14 empty] | 403
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 8.00 MH 52.910 | [18 empty] | 558 | [14 empty] | 558
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH 74.560 | [18 empty] | 390 | [14 empty] | 390
$1,763.87 0.3720 MH/SY | [22 empty] | 16.00 MH [ 26.343 ] | [18 empty] | 1350 | [10 empty] | 413 |  |  |  | 1764
82.02 | [5 empty] | INSTALL BRICK PAVERS | [24 empty] | Quan: 43.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [13 empty] | 8 | [10 empty] | CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH 64.980 | [18 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH 68.980 | [18 empty] | 723 | [10 empty] | 723
$4,130.40 1.1162 MH/SY | [22 empty] | 48.00 MH [ 80.608 ] | [18 empty] | 4130 | [10 empty] | 4130
=====> Item Totals: 82 - SALVAGE, STORE AND REINSTALL BRICK PAVER $5,894.27 1.4883 MH/SY 137.076 43 SY
64.00 MH | [30 empty] | [ 106.95 ] | [8 empty] | 5481 | [12 empty] | 413 |  |  |  | 5894
[40 empty] | 127.46 | [12 empty] | 9.61 |  |  |  | 137.08
BID ITEM = 83 CLIENT# = 83 Land Item SCHEDULE: 1 100 Description = REMOVE CURB, GRANITE W/ SALVAGE Unit = LF Takeoff Quan: 690.000 Engr Quan: 690.000
83.01 | [5 empty] | REMOVE CURB, GRANITE W/ SALVAGE | [24 empty] | Quan: |  |  | 690.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 34.5 | [5 empty] | CH |  |  | Prod: | [7 empty] | 34.5000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 34.50 HR 51.051 | [27 empty] | 1761 |  |  |  | 1761
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 34.50 HR 52.300 | [27 empty] | 1804 |  |  |  | 1804
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 34.50 MH 77.060 | [16 empty] | 3472 | [14 empty] | 3472
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 69.00 MH 52.910 | [16 empty] | 4813 | [14 empty] | 4813
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 34.50 MH 74.560 | [16 empty] | 3362 | [14 empty] | 3362
$15,213.42 0.2000 MH/LF 138.00 MH [ 14.159 ] 11,648 | [52 empty] | 3566 |  |  |  | 15213
=====> Item Totals: 83 - REMOVE CURB, GRANITE W/ SALVAGE $15,213.42 0.2000 MH/LF 22.048 690 LF
138.00 MH | [30 empty] | [ 14.159 ] | [8 empty] | 11648 | [12 empty] | 3566 |  |  |  | 15213
[40 empty] | 16.88 | [12 empty] | 5.17 |  |  |  | 22.05
BID ITEM = 84 CLIENT# = 84 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, BUS SHELTER Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 84 CLIENT# = 84 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE FOUNDATION, BUS SHELTER | [22 empty] | Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
84.01 | [5 empty] | REMOVE FOUNDATION, BUS SHELTER | [22 empty] | Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 5 |  | CH | Prod: | [7 empty] | 5.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 26.00 TCY | [5 empty] | 29 | [19 empty] | 754 | [5 empty] | 754
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 5.00 HR | [5 empty] | 51.051 | [23 empty] | 255 |  | 255
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 5.00 HR | [5 empty] | 52.3 | [23 empty] | 261 |  | 261
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 5.00 MH | [5 empty] | 77.06 | [10 empty] | 503 | [14 empty] | 503
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 10.00 MH | [5 empty] | 52.91 | [10 empty] | 698 | [14 empty] | 698
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 5.00 MH | [5 empty] | 74.56 | [10 empty] | 487 | [14 empty] | 487
$2,958.83 4.0000 MH/EA 20.00 MH | [28 empty] | [ 283.184 ] | [10 empty] | 1688 | [8 empty] | 754 |  |  |  | 517 |  | 2959
=====> Item Totals: 84 - REMOVE FOUNDATION, BUS SHELTER
2958.83 | [5 empty] | 4.0000 MH/EA | [13 empty] | 20.00 MH | [8 empty] | [ 283.184 ] | [10 empty] | 1688 | [8 empty] | 754 |  |  |  | 517 |  | 2959
591.766 | [5 empty] | 5 EA | [33 empty] | 337.62 | [8 empty] | 150.8 |  |  |  | 103.35 |  | 591.77
BID ITEM = 85 CLIENT# = 85 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION, LITTER RECEPTACLE Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
085.01 REMOVE FOUNDATION, LITTER RECEPTACLE Quan: | [33 empty] | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 0.50 CH | [33 empty] | Prod: | [7 empty] | 0.5000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 0.50 HR | [10 empty] | 51.051 | [18 empty] | 26 |  |  |  | 26
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 0.50 HR | [10 empty] | 52.3 | [18 empty] | 26 |  |  |  | 26
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 0.50 MH | [10 empty] | 77.06 | [7 empty] | 50 | [14 empty] | 50
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 1.00 MH | [10 empty] | 52.91 | [7 empty] | 70 | [14 empty] | 70
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 0.50 MH | [10 empty] | 74.56 | [7 empty] | 49 | [14 empty] | 49
$220.47 2.0000 MH/EA 2.00 MH | [33 empty] | [ 141.59 ] | [7 empty] | 169 | [10 empty] | 52 |  |  |  | 220
=====> Item Totals: 85 - REMOVE FOUNDATION, LITTER RECEPTACLE
220.47 | [5 empty] | 2.0000 MH/EA | [13 empty] | 2.00 MH | [13 empty] | [ 141.59 ] | [5 empty] | 169 | [12 empty] | 52 |  |  |  | 220
220.47 | [5 empty] | 1 EA | [33 empty] | 168.82 | [12 empty] | 51.65 |  |  |  | 220.47
BID ITEM = 86 CLIENT# = 86 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE INTERCONNECT CABLE | [19 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
86.01 | [5 empty] | REMOVE INTERCONNECT CABLE | [19 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 | [5 empty] | 1.00 LS |  |  |  |  | 7580 | [21 empty] | 7580 |  |  |  | 7580
BID ITEM = 87 CLIENT# = 87 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE STEEL RAILING | [16 empty] | Unit = LF Takeoff Quan: 28.000 Engr Quan: 28.000
87.01 | [5 empty] | REMOVE STEEL RAILING | [24 empty] | Quan: |  |  | 28.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 2 | [7 empty] | CH |  |  | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 2.00 HR | [5 empty] | 51.051 | [23 empty] | 102 |  |  |  | 102
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 2.00 HR | [5 empty] | 52.3 | [23 empty] | 105 |  |  |  | 105
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 2.00 MH | [5 empty] | 77.06 | [12 empty] | 201 | [14 empty] | 201
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 4.00 MH | [5 empty] | 52.91 | [12 empty] | 279 | [14 empty] | 279
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 2.00 MH | [5 empty] | 74.56 | [12 empty] | 195 | [14 empty] | 195
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  | Unit Cost | [9 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 87 CLIENT# = 87 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE STEEL RAILING | [23 empty] | Unit = |  |  |  | LF | [5 empty] | Takeoff Quan: | [8 empty] | 28 |  |  |  | Engr Quan: |  |  |  | 28
881.92 | [5 empty] | 0.2857 MH/LF | [13 empty] | 8.00 MH | [13 empty] | [ 20.227 ] | [5 empty] | 675 | [12 empty] | 207 |  |  |  | 882
=====> Item Totals: 87 - REMOVE STEEL RAILI $881.92 0.2857 MH/LF 8.00 MH | [29 empty] | NG [ 20.227 ] | [9 empty] | 675 | [8 empty] | 207 | [7 empty] | 882
31.497 28 LF | [39 empty] | 24.12 | [8 empty] | 7.38 | [7 empty] | 31.5
BID ITEM = 88 CLIENT# = 88 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL STEEL RAILIN Unit = LF Takeoff Quan: 73.000 Engr Quan: 73.000
88.01 | [5 empty] | REMOVE AND STOR STEEL RAILING | [24 empty] | Quan: |  |  | 73.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [17 empty] | 2 | [6 empty] | CH |  |  | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 2.00 HR 51.051 | [28 empty] | 102 |  |  |  | 102
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  | 2.00 HR 52.300 | [28 empty] | 105 |  |  |  | 105
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 2.00 MH 77.060 | [17 empty] | 201 | [14 empty] | 201
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  | 4.00 MH 52.910 | [17 empty] | 279 | [14 empty] | 279
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 2.00 MH 74.560 | [17 empty] | 195 | [14 empty] | 195
$881.92 0.1095 MH/LF | [23 empty] | 8.00 MH [ 7.758 ] | [17 empty] | 675 | [10 empty] | 207 |  |  |  | 882
88.02 | [5 empty] | INSTALL STEEL RAILING | [24 empty] | Quan: |  |  | 73.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [17 empty] | 6 | [6 empty] | CH |  |  | Prod: | [7 empty] | 6.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 | [23 empty] | 12.00 MH 52.910 | [17 empty] | 837 | [10 empty] | 837
$837.12 0.1643 MH/LF | [23 empty] | 12.00 MH [ 9.567 ] | [17 empty] | 837 | [10 empty] | 837
=====> Item Totals: 88 - REMOVE, STORE AND REINSTALL STEEL RAILIN $1,719.04 0.2739 MH/LF 23.548 73 LF
20.00 MH | [30 empty] | [ 17.326 ] | [8 empty] | 1512 | [12 empty] | 207 |  |  |  | 1719
[40 empty] | 20.72 | [12 empty] | 2.83 |  |  |  | 23.55
BID ITEM = 89 CLIENT# = 89 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL 18"-HIGH DEC Unit = LF Takeoff Quan: 65.000 Engr Quan: 65.000
89.01 | [5 empty] | REMOVE AND STOR DECRATIVE FENCE | [24 empty] | Quan: |  |  | 65.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [17 empty] | 2 | [6 empty] | CH |  |  | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 2.00 HR 51.051 | [28 empty] | 102 |  |  |  | 102
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  | 2.00 HR 52.300 | [28 empty] | 105 |  |  |  | 105
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 2.00 MH 77.060 | [17 empty] | 201 | [14 empty] | 201
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  | 4.00 MH 52.910 | [17 empty] | 279 | [14 empty] | 279
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 2.00 MH 74.560 | [17 empty] | 195 | [14 empty] | 195
$881.92 0.1230 MH/LF | [23 empty] | 8.00 MH [ 8.713 ] | [17 empty] | 675 | [10 empty] | 207 |  |  |  | 882
89.02 | [5 empty] | INSTALL DECROTIVE FENCE | [24 empty] | Quan: |  |  | 65.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [17 empty] | 6 | [6 empty] | CH |  |  | Prod: | [7 empty] | 6.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 | [23 empty] | 12.00 MH 52.910 | [17 empty] | 837 | [10 empty] | 837
$837.12 0.1846 MH/LF | [23 empty] | 12.00 MH [ 10.745 ] | [17 empty] | 837 | [10 empty] | 837
=====> Item Totals: 89 - REMOVE, STORE AND REINSTALL 18"-HIGH DEC $1,719.04 0.3076 MH/LF 20.00 MH [ 19.458 ] 1,512 | [52 empty] | 207 |  |  |  | 1719
26.447 65 LF | [37 empty] | 23.27 | [14 empty] | 3.18 |  |  |  | 26.45
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [17 empty] | Pcs | [7 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 90 CLIENT# = 90 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE PONY BAR FENCE | [16 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
90.01 | [5 empty] | REMOVE PONY BAR FENCE | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 8 | [7 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3PFENCEDIS | [5 empty] | DISOSE PONY BAR FEN | [12 empty] | 1 |  |  |  | 1.00 LS | [5 empty] | 1000 | [19 empty] | 1000 | [5 empty] | 1000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 51.051 | [23 empty] | 408 |  | 408
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 8.00 HR | [5 empty] | 52.3 | [23 empty] | 418 |  | 418
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 16.00 MH | [5 empty] | 52.91 | [11 empty] | 1116 | [13 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
$4,527.75 32.0000 MH/LS | [22 empty] | 32.00 MH | [5 empty] | [ 2265.48 ] | [11 empty] | 2701 | [7 empty] | 1000 |  |  |  | 827 |  | 4528
=====> Item $4,527.75 | [5 empty] | Totals: 90 - 32.0000 MH/LS | [12 empty] | REMOVE PONY BAR FENCE 32.00 MH [ 2265.48 ] | [18 empty] | 2701 | [10 empty] | 1000 |  |  |  | 827 |  | 4528
4527.75 | [5 empty] | 1 LS | [31 empty] | 2700.95 | [10 empty] | 1000 |  |  |  | 826.8 |  | 4527.75
BID ITEM = 91 CLIENT# = 91 Land Item SCHEDULE: 1 100 Description = REMOVE SCL VAULT LID AND RISERS Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
91.01 | [5 empty] | REMOVE SCL VAULT LID AND RISERS | [24 empty] | Quan: |  |  | 3.00 EA | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 8 | [7 empty] | CH |  |  | Prod: | [6 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 8.00 HR 51.051 | [29 empty] | 408 |  |  |  | 408
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 8.00 HR 52.300 | [29 empty] | 418 |  |  |  | 418
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 8.00 MH 77.060 | [17 empty] | 805 | [15 empty] | 805
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 16.00 MH 52.910 | [17 empty] | 1116 | [15 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 8.00 MH 74.560 | [17 empty] | 780 | [15 empty] | 780
$3,527.75 10.6666 MH/EA 32.00 MH | [22 empty] | [ 755.16 ] | [17 empty] | 2701 | [11 empty] | 827 |  |  |  | 3528
=====> Item Totals: 91 - REMOVE SCL VAULT LID AND RISERS
3527.75 | [5 empty] | 10.6666 MH/EA | [12 empty] | 32.00 MH |  |  |  | [ 755.16 ] | [16 empty] | 2701 | [12 empty] | 827 |  |  |  | 3528
1175.917 | [5 empty] | 3 EA | [33 empty] | 900.32 | [12 empty] | 275.6 |  |  |  | 1175.92
BID ITEM = 92 CLIENT# = 92 Land Item SCHEDULE: 1 100 Description = ABANDON MONITORING WELL Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
EAS Earthwork 4 Man Crew 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS07 SEATTLE TYPE 7@110.2 1.00 5.00 TON 29.750 164 | [56 empty] | 164
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 4.00 HR | [7 empty] | 51.051 | [17 empty] | 204 | [5 empty] | 204
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 4.00 HR | [7 empty] | 52.3 | [17 empty] | 209 | [5 empty] | 209
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 77.06 | [6 empty] | 403 | [16 empty] | 403
LAG | [5 empty] | General Laborer | [12 empty] | 2 |  |  |  | 8.00 MH | [7 empty] | 52.91 | [6 empty] | 558 | [16 empty] | 558
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
$1,927.87 16.0000 MH/EA 16.00 MH | [30 empty] | [ 1132.73 ] | [6 empty] | 1350 | [6 empty] | 164 |  |  |  | 413 | [5 empty] | 1928
=====> Item Totals: 92 - ABANDON MONITORING WELL
1927.87 | [5 empty] | 16.0000 MH/EA | [12 empty] | 16.00 MH | [11 empty] | [ 1132.73 ] | [6 empty] | 1350 | [6 empty] | 164 |  |  |  | 413 | [5 empty] | 1928
1927.87 | [5 empty] | 1 EA | [31 empty] | 1350.47 | [6 empty] | 164 |  |  |  | 413.4 | [5 empty] | 1927.87
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 93 CLIENT# = 93 Land Item SCHEDULE: 1 100 Description = REMOVE TREE GRATE Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
93.01 | [5 empty] | REMOVE TREE GRATE | [24 empty] | Quan: |  |  | 21.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 5.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 5.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 5.00 HR | [5 empty] | 51.051 | [23 empty] | 255 |  |  |  | 255
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 5.00 HR | [5 empty] | 52.3 | [23 empty] | 261 |  |  |  | 261
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 5.00 MH | [5 empty] | 77.06 | [12 empty] | 503 | [14 empty] | 503
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 10.00 MH | [5 empty] | 52.91 | [12 empty] | 698 | [14 empty] | 698
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 5.00 MH | [5 empty] | 74.56 | [12 empty] | 487 | [14 empty] | 487
$2,204.83 0.9523 MH/EA 20.00 MH | [28 empty] | [ 67.425 ] | [12 empty] | 1688 | [10 empty] | 517 |  |  |  | 2205
=====> Item Totals: 93 - REMOVE TREE GRATE $2,204.83 0.9523 MH/EA 104.992 21 EA
20.00 MH | [30 empty] | [ 67.425 ] | [8 empty] | 1688 | [12 empty] | 517 |  |  |  | 2205
[40 empty] | 80.39 | [12 empty] | 24.61 |  |  |  | 104.99
BID ITEM = 94 CLIENT# = 94 Land Item SCHEDULE: 1 100
Description = | [6 empty] | REMOVE AND SALVAGE WATER FOUNTAIN | [22 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
94.01 | [6 empty] | REMOVE AND SALVAGE WATER FOUNTAIN | [22 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 4.00 CH Prod: 4.0000 CH Lab Pcs: 4.00 Eqp Pcs: | [56 empty] | 2
8BA310A | [6 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 |  |  |  | 4.00 HR | [6 empty] | 51.051 | [22 empty] | 204 |  |  |  | 204
8EX100 | [6 empty] | 100 Excavator | [11 empty] | 1 |  |  |  | 4.00 HR | [6 empty] | 52.3 | [22 empty] | 209 |  |  |  | 209
FOCI | [6 empty] | Civil Forman | [11 empty] | 1 |  |  |  | 4.00 MH | [6 empty] | 77.06 | [9 empty] | 403 | [16 empty] | 403
LAG | [6 empty] | General Laborer | [11 empty] | 2 |  |  |  | 8.00 MH | [6 empty] | 52.91 | [9 empty] | 558 | [16 empty] | 558
OPE | [6 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  | 4.00 MH | [6 empty] | 74.56 | [9 empty] | 390 | [16 empty] | 390
$1,763.87 16.0000 MH/EA 16.00 MH | [29 empty] | [ 1132.73 ] | [9 empty] | 1350 | [12 empty] | 413 |  |  |  | 1764
=====> Item $1,763.87 | [6 empty] | Totals: 94 - 16.0000 MH/EA | [11 empty] | REMOVE AND SALVAG 16.00 MH | [10 empty] | E WATER FOUNTAIN [ 1132.73 ] 1,350 | [22 empty] | 413 |  |  |  | 1764
1763.87 | [6 empty] | 1 EA | [22 empty] | 1350.47 | [22 empty] | 413.4 |  |  |  | 1763.87
BID ITEM = 95 CLIENT# = 95 Land Item SCHEDULE: 1 100 Description = REMOVE WATER METER BOX Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
95.01 |  |  |  | REMOVE WATER METER BOX | [26 empty] | Quan: |  |  | 4.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS |  |  |  | Earthwork 4 Man Crew | [20 empty] | 1 | [5 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A |  |  |  | 418 Backhoe W/Attachme | [12 empty] | 1 | [7 empty] | 1.00 HR 51.051 | [27 empty] | 51 |  |  |  | 51
8EX100 |  |  |  | 100 Excavator | [12 empty] | 1 | [7 empty] | 1.00 HR 52.300 | [27 empty] | 52 |  |  |  | 52
FOCI |  |  |  | Civil Forman | [12 empty] | 1 | [7 empty] | 1.00 MH 77.060 | [16 empty] | 101 | [14 empty] | 101
LAG |  |  |  | General Laborer | [12 empty] | 2 | [7 empty] | 2.00 MH 52.910 | [16 empty] | 140 | [14 empty] | 140
OPE |  |  |  | Operator - Excavator | [12 empty] | 1 | [7 empty] | 1.00 MH 74.560 | [16 empty] | 97 | [14 empty] | 97
$440.95 1.0000 MH/EA 4.00 MH | [24 empty] | [ 70.798 ] | [16 empty] | 338 | [10 empty] | 103 |  |  |  | 441
=====> $440.95 |  |  |  | Item Totals: | [5 empty] | 95 1.0000 MH/EA | [6 empty] | - REMOVE WATER METER BOX 4.00 MH | [16 empty] | [ 70.798 ] |  |  |  | 338 | [14 empty] | 103 |  |  |  | 441
110.238 | [9 empty] | 4 EA | [27 empty] | 84.41 | [14 empty] | 25.83 |  |  |  | 110.24
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 96 CLIENT# = 96 Land Item SCHEDULE: 1 100 Description = REMOVE BUTTERFLY VALVE Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
96.01 | [5 empty] | REMOVE BUTTERFLY VALVE | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [17 empty] | 1 | [6 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 1.00 HR 68.251 | [28 empty] | 68 |  |  |  | 68
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  | 1.00 HR 78.000 | [28 empty] | 78 |  |  |  | 78
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  | 1.00 HR 81.500 | [28 empty] | 81 |  |  |  | 81
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 1.00 MH 77.060 | [17 empty] | 101 | [14 empty] | 101
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  | 2.00 MH 53.880 | [17 empty] | 142 | [14 empty] | 142
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 1.00 MH 74.560 | [17 empty] | 97 | [14 empty] | 97
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  | 1.00 MH 74.560 | [17 empty] | 97 | [14 empty] | 97
$665.29 5.0000 MH/EA 5.00 MH | [23 empty] | [ 367.35 ] | [17 empty] | 438 | [10 empty] | 228 |  |  |  | 665
=====> Item Totals: 96 - REMOVE BUTTERFLY VALVE
665.29 | [5 empty] | 5.0000 MH/EA | [13 empty] | 5.00 MH |  |  |  | [ 367.35 ] | [15 empty] | 438 | [12 empty] | 228 |  |  |  | 665
665.29 | [5 empty] | 1 EA | [33 empty] | 437.56 | [12 empty] | 227.73 |  |  |  | 665.29
BID ITEM = 97 CLIENT# = 97 Land Item SCHEDULE: 1 100 Description = ABANDON VALVE VAULT Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
97.01 | [5 empty] | ABANDON VALVE VAULT | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [17 empty] | 1 | [6 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  |  | 5.00 TON 25.750 142 142
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 1.00 HR 68.251 | [20 empty] | 68 | [11 empty] | 68
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  | 1.00 HR 78.000 | [20 empty] | 78 | [11 empty] | 78
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  | 1.00 HR 81.500 | [20 empty] | 81 | [11 empty] | 81
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 1.00 MH 77.060 | [17 empty] | 101 | [14 empty] | 101
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  | 2.00 MH 53.880 | [17 empty] | 142 | [14 empty] | 142
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 1.00 MH 74.560 | [17 empty] | 97 | [14 empty] | 97
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  | 1.00 MH 74.560 | [17 empty] | 97 | [14 empty] | 97
$807.24 5.0000 MH/EA 5.00 MH | [23 empty] | [ 367.35 ] | [17 empty] | 438 |  |  | 142 | [7 empty] | 228 |  |  |  | 807
=====> Item Totals: 97 - ABANDON VALVE VAULT
807.24 | [5 empty] | 5.0000 MH/EA | [13 empty] | 5.00 MH |  |  |  | [ 367.35 ] | [15 empty] | 438 |  |  |  |  | 142 | [7 empty] | 228 |  |  |  | 807
807.24 | [5 empty] | 1 EA | [33 empty] | 437.56 |  |  |  |  | 141.95 | [7 empty] | 227.73 |  |  |  | 807.24
BID ITEM = 98 CLIENT# = 98 Land Item SCHEDULE: 1 100 Description = REMOVE AND DISPOSE POLE, METAL STRAIN Unit = EA Takeoff Quan: 12.000 Engr Quan: 12.000
098.01 REMOVE AND DISPOSE POLE, METAL STRAIN Quan: 12.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 12.00 EA 2,650.000 31,800 31,800
BID ITEM = 99 CLIENT# = 99 Land Item SCHEDULE: 1 100 Description = COMMON EXCAVATION Unit = CY Takeoff Quan: 11,277.000 Engr Quan: 11,277.000
099.01 COMMON EXCAVATION Quan: 11,277.00 CY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
GRM Grading 5 Man Crew 422.22 CH Prod: 422.2262 CH Lab Pcs: 5.00 Eqp Pcs: 4.00 3DEDU02D Dirt Trucking and Dump 1.00 14,762.56 TCY 24.500 361,683 361,683
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 99 CLIENT# = 99 Land Item SCHEDULE: 1 100 Description = COMMON EXCAVATION Unit = CY Takeoff Quan: 11,277.000 Engr Quan: 11,277.000
8DO0450 | [5 empty] | JD 450 Dozer | [13 empty] | 1 |  |  | 422.23 HR | [7 empty] | 49.5 | [17 empty] | 20900 | [7 empty] | 20900
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 422.23 HR | [7 empty] | 68.251 | [17 empty] | 28818 | [7 empty] | 28818
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 422.23 HR | [7 empty] | 78 | [17 empty] | 32934 | [7 empty] | 32934
8RO84 | [5 empty] | 84 Inch Roller | [13 empty] | 1 |  |  | 422.23 HR | [7 empty] | 55.7 | [17 empty] | 23518 | [7 empty] | 23518
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 422.23 MH | [7 empty] | 77.06 | [6 empty] | 45020 | [18 empty] | 45020
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 844.45 MH | [7 empty] | 52.91 | [6 empty] | 62374 | [18 empty] | 62374
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 844.45 MH | [7 empty] | 74.56 | [6 empty] | 87175 | [18 empty] | 87175
$662,421.12 0.1872 MH/CY 2,111.13 MH [ 14.503 ] | [37 empty] | 194568 | [10 empty] | 361683 |  |  |  | 106170 |  |  |  | 662421
=====> Item Totals: 99 - COMMON EXCAVATION $662,421.12 0.1872 MH/CY 2,111.13 MH [ 14.503 ] | [37 empty] | 194568 | [10 empty] | 361683 |  |  |  | 106170 |  |  |  | 662421
58.741 11277 CY | [37 empty] | 17.25 | [10 empty] | 32.07 |  |  |  | 9.41 |  |  |  | 58.74
BID ITEM = 100 CLIENT# = 100 Land Item SCHEDULE: 1 100 Description = UTILITY VERIFICATION EXCAVATION. 10 FT D Unit = EA Takeoff Quan: 153.000 Engr Quan: 153.000
100.01 UTILITY VERIFICATION EXCAVATION. 10 FT D Quan: 153.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 153.00 EA 3,000.000 459,000 459,000
BID ITEM = 101 CLIENT# = 101 Land Item SCHEDULE: 1 100 Description = UTILITY VERIFICATION EXCAVATION. 5 FT DE Unit = EA Takeoff Quan: 11.000 Engr Quan: 11.000
101.01 UTILITY VERIFICATION EXCAVATION. 5 FT DE Quan: 11.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 11.00 EA 2,250.000 24,750 24,750
BID ITEM = 102 CLIENT# = 102 Land Item SCHEDULE: 1 100 Description = SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN Unit = SF Takeoff Quan: 37,667.000 Engr Quan: 37,667.000
102.01 SAFETY SYSTEMS IN TRENCH EXCAVATION, M Quan: 37,717.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3SHORETRENC TRENCH SHORING 1.00 1.00 LS 100,000.000 | [37 empty] | 100000 | [14 empty] | 100000
=====> Item Totals: 102 - SAFETY SYSTEMS IN TRENCH EXCAVA $100,000.00 [ ] 2.655 37667 SF | [37 empty] | TION, MIN 100,000 | [14 empty] | 100000
[38 empty] | 2.65 | [14 empty] | 2.65
BID ITEM = 103 CLIENT# = 103 Land Item SCHEDULE: 1 100 Description = SUPPORT AND SAFETY SYSTEM Unit = SF Takeoff Quan: 1,515.000 Engr Quan: 1,515.000
103.01 | [7 empty] | SLIDE RAIL RENT | [20 empty] | Quan: |  |  |  |  | 1,515.00 SF | [8 empty] | Hrs/Shft: | [5 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
3SHORESOILDI | [7 empty] | SOILDER PILE SHORING | [11 empty] | 1 |  |  | 1,515.00 SF | [10 empty] | 24 | [14 empty] | 36360 | [7 empty] | 36360
103.02 | [7 empty] | INSTALL SLIDE RAIL | [20 empty] | Quan: |  |  |  |  | 1,515.00 SF | [8 empty] | Hrs/Shft: | [5 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
UNM 8EX135A | [7 empty] | Unerground Utilities 6 Man 135 Excavator W/Attach | [11 empty] | 1 |  |  | 40.00 HR | [5 empty] | 40.00 CH Prod: 40.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 68.251 2,730 2,730
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 103 CLIENT# = 103 Land Item SCHEDULE: 1 100 Description = SUPPORT AND SAFETY SYSTEM Unit = SF Takeoff Quan: 1,515.000 Engr Quan: 1,515.000
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 78 | [19 empty] | 3120 | [7 empty] | 3120
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 81.5 | [19 empty] | 3260 | [7 empty] | 3260
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 77.06 | [11 empty] | 4026 | [15 empty] | 4026
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 80.00 MH | [5 empty] | 53.88 | [11 empty] | 5680 | [15 empty] | 5680
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [11 empty] | 3898 | [15 empty] | 3898
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [11 empty] | 3898 | [15 empty] | 3898
$26,612.01 0.1320 MH/SF | [22 empty] | 200.00 MH | [5 empty] | [ 9.699 ] | [11 empty] | 17502 | [7 empty] | 9110 | [7 empty] | 26612
103.03 | [5 empty] | REMOVE SLIDE RAIL | [24 empty] | Quan: |  |  | 1,515.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 20 | [10 empty] | CH |  |  | Prod: | [6 empty] | 20.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 68.251 | [19 empty] | 1365 | [7 empty] | 1365
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 78 | [19 empty] | 1560 | [7 empty] | 1560
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 81.5 | [19 empty] | 1630 | [7 empty] | 1630
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 77.06 | [11 empty] | 2013 | [15 empty] | 2013
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 40.00 MH | [5 empty] | 53.88 | [11 empty] | 2840 | [15 empty] | 2840
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 74.56 | [11 empty] | 1949 | [15 empty] | 1949
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 74.56 | [11 empty] | 1949 | [15 empty] | 1949
$13,306.01 0.0660 MH/SF | [22 empty] | 100.00 MH | [5 empty] | [ 4.849 ] | [11 empty] | 8751 | [7 empty] | 4555 | [7 empty] | 13306
=====> Item Totals: 103 - SUPPORT AND SAFETY SYSTEM
$76,278.02 0.1980 MH/SF 300.00 MH | [28 empty] | [ 14.548 ] | [11 empty] | 26253 | [7 empty] | 36360 |  |  |  | 13665 |  |  |  | 76278
50.349 1515 SF | [40 empty] | 17.33 | [7 empty] | 24 |  |  |  | 9.02 |  |  |  | 50.35
BID ITEM = 104 CLIENT# = 104 Land Item SCHEDULE: 1 100
Description = UTILITY CROSSING SUPPORT IN TRENCH Unit = LS Takeoff Quan: 1.000 | [53 empty] | Engr Quan: |  |  | 1
104.01 UTILITY CROSSING SUPPORT IN TRENCH Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 3SHORUTSU UTILITY SUPPORT 1.00 1.00 LS 1,500.000 1,500 | [53 empty] | WC: WAAVG |  |  | 1500
=====> Item Totals $1,500.00 | [8 empty] | : 104 - UTILITY CROSSI | [17 empty] | NG SUPPORT IN TRENCH [ ] | [12 empty] | 1500 | [13 empty] | 1500
1500 | [8 empty] | 1 LS | [30 empty] | 1500 | [13 empty] | 1500
BID ITEM = 105 CLIENT# = 105 Land Item SCHEDULE: 1 100
Description = | [5 empty] | DEWATERING | [13 empty] | Unit = FA Takeoff Quan: 100,000.000 Engr Quan: 100,000.000
105.01 9FORCE | [5 empty] | DEWATERING FORCE ACCOUNT | [13 empty] | Quan: 100,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG 1.00 100,000.00 FA 0.890 89,000 89,000
=====> Item $89,000.00 | [5 empty] | Totals: 105 - DEWATERING [ ] | [33 empty] | 89000 | [12 empty] | 89000
0.89 | [5 empty] | 100000 FA | [33 empty] | 0.89 | [12 empty] | 0.89
BID ITEM = 106 CLIENT# = 106 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | CONTROLLED DENSITY FILL | [24 empty] | Unit = |  |  | CY Takeoff Quan: 50.000 Engr Quan: 50.000
| 106.01 |  |  |  |  | CONTROLLED DENSITY FILL | [24 empty] | Quan: |  |  | 50.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 106 CLIENT# = 106 Land Item SCHEDULE: 1 100 Description = CONTROLLED DENSITY FILL Unit = CY Takeoff Quan: 50.000 Engr Quan: 50.000 UNM Unerground Utilities 6 Man 5.00 CH Prod: 5.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CRCDF | [5 empty] | CDF@110.25% | [10 empty] | 1 | [5 empty] | 50.00 CY | [10 empty] | 106.150 5,852 5,852
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [10 empty] | 1 | [5 empty] | 60.00 TCY | [10 empty] | 24.5 | [10 empty] | 1470 | [11 empty] | 1470
8EX135A | [5 empty] | 135 Excavator W/Attach | [10 empty] | 1 | [5 empty] | 5.00 HR | [10 empty] | 68.251 | [18 empty] | 341 |  |  |  | 341
8EX200 | [5 empty] | 200 Excavator | [10 empty] | 1 | [5 empty] | 5.00 HR | [10 empty] | 78 | [18 empty] | 390 |  |  |  | 390
8LO950 | [5 empty] | 950 Loader | [10 empty] | 1 | [5 empty] | 5.00 HR | [10 empty] | 81.5 | [18 empty] | 407 |  |  |  | 407
FOCI | [5 empty] | Civil Forman | [10 empty] | 1 | [5 empty] | 5.00 MH | [10 empty] | 77.06 |  |  |  | 503 | [18 empty] | 503
LAP | [5 empty] | Labor Underground Water | [10 empty] | 2 | [5 empty] | 10.00 MH | [10 empty] | 53.88 |  |  |  | 710 | [18 empty] | 710
OPE | [5 empty] | Operator - Excavator | [10 empty] | 1 | [5 empty] | 5.00 MH | [10 empty] | 74.56 |  |  |  | 487 | [18 empty] | 487
OPL | [5 empty] | Operator - Loader | [10 empty] | 1 | [5 empty] | 5.00 MH | [10 empty] | 74.56 |  |  |  | 487 | [18 empty] | 487
$10,648.01 0.5000 MH/CY 25.00 MH | [33 empty] | [ 36.733 ] |  |  |  | 2188 | [6 empty] | 5852 |  |  |  | 1470 |  |  |  | 1139 |  |  |  | 10648
=====> Item Totals: $10,648.01 | [9 empty] | 106 0.5000 MH/CY | [6 empty] | - CONTROLLED DENSITY FILL 25.00 MH | [16 empty] | [ 36.733 ] |  |  |  | 2188 | [6 empty] | 5852 |  |  |  | 1470 |  |  |  | 1139 |  |  |  | 10648
212.960 50 CY 43.76 117.03 29.40 | [52 empty] | 22.77 |  |  |  | 212.96
BID ITEM = 107 CLIENT# = 107 Land Item SCHEDULE: 1 100 Description = MINERAL AGGREGATE, TYPE 2 Unit = TN Takeoff Quan: 19,931.000 Engr Quan: 19,931.000
107.01 MINERAL AGGREGATE, TYPE 2 Quan: 19,931.00 TN Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
GRM Grading 5 Man Crew 711.34 CH Prod: 711.3462 CH Lab Pcs: 5.00 Eqp Pcs: 4.00
2AGS02 | [5 empty] | SEATTLE TYPE 2@110.2 | [13 empty] | 1 |  |  | 19,931.00 TON | [7 empty] | 29.750 653,724 653,724
8DO0450 | [5 empty] | JD 450 Dozer | [13 empty] | 1 |  |  | 711.35 HR | [7 empty] | 49.5 | [13 empty] | 35212 | [10 empty] | 35212
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 711.35 HR | [7 empty] | 68.251 | [13 empty] | 48550 | [10 empty] | 48550
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 711.35 HR | [7 empty] | 78 | [13 empty] | 55485 | [10 empty] | 55485
8RO84 | [5 empty] | 84 Inch Roller | [13 empty] | 1 |  |  | 711.35 HR | [7 empty] | 55.7 | [13 empty] | 39622 | [10 empty] | 39622
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 711.35 MH | [7 empty] | 77.06 | [6 empty] | 75847 | [17 empty] | 75847
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 1,422.69 MH | [7 empty] | 52.91 | [6 empty] | 105085 | [17 empty] | 105085
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 1,422.69 MH | [7 empty] | 74.56 | [6 empty] | 146868 | [17 empty] | 146868
$1,160,393.18 0.1784 MH/TN 3,556.73 MH [ 13.824 ] | [37 empty] | 327799 | [6 empty] | 653724 | [7 empty] | 178870 |  |  | 1160393
=====> Item Totals: 107 - MINERAL AGGREGATE, TYPE 2 $1,160,393.18 0.1784 MH/TN 3,556.73 MH [ 13.824 ] | [37 empty] | 327799 | [6 empty] | 653724 | [7 empty] | 178870 |  |  | 1160393
58.221 19931 TN | [37 empty] | 16.45 | [6 empty] | 32.8 | [7 empty] | 8.97 |  |  | 58.22
BID ITEM | [5 empty] | = |  | 108 |  |  | CLIENT# = | [11 empty] | 108 | [5 empty] | Land Item SCHEDULE: 1 100
Description = | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [22 empty] | Unit = TN Takeoff Quan: 7,568.000 Engr Quan: 7,568.000
108.01 | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [22 empty] | Quan: 7,568.00 TN Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  | 7,568.00 TON | [5 empty] | 25.75 | [8 empty] | 214851 | [14 empty] | 214851
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 6,054.19 TCY | [5 empty] | 24.5 | [19 empty] | 148328 |  |  |  | 148328
363178.45 | [28 empty] | [ ] | [8 empty] | 214851 | [10 empty] | 148328 |  |  |  | 363178
=====> Item Totals: $363,178.45 | [10 empty] | 108 |  |  | - MINERAL AGGREGATE, TYPE 17 | [21 empty] | [ ] |  | 214851 | [10 empty] | 148328 |  |  |  | 363178
47.989 | [13 empty] | 7568 TN | [23 empty] | 28.39 | [10 empty] | 19.6 |  |  |  | 47.99
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 109 CLIENT# = 109 Land Item SCHEDULE: 1 100 Description = MINERAL AGGREGATE, TYPE 9 Unit = CY Takeoff Quan: 32.000 Engr Quan: 32.000
109.01 | [5 empty] | MINERAL AGGREGATE, TYPE 9 | [24 empty] | Quan: |  |  | 32.00 CY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 5 | [5 empty] | CH |  |  | Prod: | [7 empty] | 5.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  |  |  | 55.17 TON 29.750 | [16 empty] | 1,810 1,810
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 5.00 HR 51.051 | [19 empty] | 255 | [11 empty] | 255
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 5.00 HR 52.300 | [19 empty] | 261 | [11 empty] | 261
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 5.00 MH 77.060 | [16 empty] | 503 | [14 empty] | 503
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 10.00 MH 52.910 | [16 empty] | 698 | [14 empty] | 698
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 5.00 MH 74.560 | [16 empty] | 487 | [14 empty] | 487
$4,014.37 0.6250 MH/CY 20.00 MH | [24 empty] | [ 44.248 ] | [16 empty] | 1688 |  |  | 1810 | [7 empty] | 517 |  |  |  | 4014
=====> Item Totals: $4,014.37 | [9 empty] | 109 0.6250 MH/CY | [6 empty] | - MINERAL AGGREGATE, TYPE 9 20.00 MH | [16 empty] | [ 44.248 ] |  |  |  | 1688 | [6 empty] | 1810 | [7 empty] | 517 |  |  |  | 4014
125.449 32 CY | [37 empty] | 52.75 | [6 empty] | 56.55 | [7 empty] | 16.15 |  |  |  | 125.45
BID ITEM = 110 CLIENT# = 110 Land Item SCHEDULE: 1 100 Description = SURFACE PREP, PRELEVEL Unit = TN Takeoff Quan: 49.000 Engr Quan: 49.000
4ASPH Asphalt Paving sub 1.00 49.00 TN 195.000 9,555 9,555
BID ITEM = 111 CLIENT# = 111 Land Item SCHEDULE: 1 100 Description = SURFACE PREP, PLANE BITUMINOUS PAVEMENT Unit = SY Takeoff Quan: 14,240.000 Engr Quan: 14,240.000
EAS Earthwork 4 Man Crew 22.03 CH Prod: 22.0348 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02A Asphalt trucking and Dump 1.00 1,457.97 TCY 29.000 | [48 empty] | 42281 | [7 empty] | 42281
4MILL | [5 empty] | Milling Sub | [13 empty] | 1 |  |  | 14,240.00 SY | [7 empty] | 2 | [23 empty] | 28480 |  | 28480
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 22.03 HR | [7 empty] | 51.051 | [17 empty] | 1125 | [7 empty] | 1125
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 22.03 HR | [7 empty] | 52.3 | [17 empty] | 1152 | [7 empty] | 1152
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 22.03 MH | [7 empty] | 77.06 | [8 empty] | 2217 | [16 empty] | 2217
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 44.07 MH | [7 empty] | 52.91 | [8 empty] | 3074 | [16 empty] | 3074
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 22.03 MH | [7 empty] | 74.56 | [8 empty] | 2147 | [16 empty] | 2147
$80,476.36 0.0061 MH/SY 88.13 MH [ 0.438 ] | [39 empty] | 7438 | [8 empty] | 42281 |  |  |  | 2277 |  | 28480 |  | 80476
=====> Item Totals: 111 - SURFACE PREP, PLANE BITUMINOUS PAVEMENT
$80,476.36 0.0061 MH/SY 88.13 MH | [30 empty] | [ 0.438 ] | [8 empty] | 7438 | [8 empty] | 42281 |  |  |  | 2277 |  | 28480 |  | 80476
5.651 14240 SY | [39 empty] | 0.52 | [8 empty] | 2.97 |  |  |  | 0.16 |  | 2 |  | 5.65
BID ITEM = 112 CLIENT# = 112 Land Item SCHEDULE: 1 100 Description = PAVEMENT, WMA (CL 1/2 IN) Unit = TN Takeoff Quan: 3,942.000 Engr Quan: 3,942.000
112.01 | [5 empty] | PAVEMENT, WMA (CL 1/2 IN) | [24 empty] | Quan: |  |  | 3,942.00 TN | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 37.88 | [7 empty] | CH |  |  | Prod: | [7 empty] | 37.8856 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
4ASPH | [5 empty] | Asphalt Paving sub | [13 empty] | 1 |  |  | 3,942.00 TN 162.000 | [31 empty] | 638604 |  | 638604
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 37.89 HR 51.051 | [18 empty] | 1934 | [14 empty] | 1934
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 37.89 HR 52.300 | [18 empty] | 1982 | [14 empty] | 1982
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 112 CLIENT# = 112 Land Item SCHEDULE: 1 100 Description = PAVEMENT, WMA (CL 1/2 IN) Unit = TN Takeoff Quan: 3,942.000 Engr Quan: 3,942.000
FOCI | [5 empty] | Civil Forman | [10 empty] | 1 | [5 empty] | 37.89 MH | [10 empty] | 77.06 |  |  |  | 3814 | [14 empty] | 3814
LAG | [5 empty] | General Laborer | [10 empty] | 2 | [5 empty] | 75.77 MH | [10 empty] | 52.91 |  |  |  | 5286 | [14 empty] | 5286
OPE | [5 empty] | Operator - Excavator | [10 empty] | 1 | [5 empty] | 37.89 MH | [10 empty] | 74.56 |  |  |  | 3692 | [14 empty] | 3692
$655,311.60 0.0384 MH/TN 151.55 MH | [33 empty] | [ 2.722 ] |  |  |  | 12792 | [14 empty] | 3916 |  | 638604 |  | 655312
=====> Item Totals: $655,311.60 | [9 empty] | 112 0.0384 MH/TN | [6 empty] | - PAVEMENT, WMA (CL 1/2 IN) 151.55 MH | [16 empty] | [ 2.722 ] |  |  |  | 12792 | [14 empty] | 3916 |  | 638604 |  | 655312
166.238 3942 TN | [37 empty] | 3.24 | [14 empty] | 0.99 |  | 162 |  | 166.24
BID ITEM | [5 empty] | = |  | 113 |  | CLIENT# = | [12 empty] | 113 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [7 empty] | 1 100
Description = | [5 empty] | PAVEMENT PATCH, TEMPORARY | [22 empty] | Unit = |  |  |  |  | TN Takeoff Quan: 1,066.000 Engr Quan: 1,066.000
113.01 | [5 empty] | PAVEMENT PATCH, TEMPORARY | [22 empty] | Quan: |  |  |  |  | 1,066.00 TN Hrs/Shft: 10.00 Cal: X10 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 177.11 | [7 empty] | CH |  |  | Prod: | [7 empty] | 177.1166 CH | [6 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3COLDMIX | [5 empty] | COLD MIX | [13 empty] | 1 |  |  | 1,066.00 TN | [7 empty] | 110 | [17 empty] | 117260 | [5 empty] | 117260
3DEDU02A | [5 empty] | Asphalt trucking and Dump | [13 empty] | 1 |  |  | 1,023.10 TCY | [7 empty] | 29 | [17 empty] | 29670 | [5 empty] | 29670
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 177.12 HR | [7 empty] | 51.051 | [21 empty] | 9042 |  | 9042
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 177.12 HR | [7 empty] | 52.3 | [21 empty] | 9263 |  | 9263
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 177.12 MH | [7 empty] | 77.06 | [8 empty] | 32109 | [14 empty] | 32109
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 354.23 MH | [7 empty] | 52.91 | [8 empty] | 44324 | [14 empty] | 44324
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 177.12 MH | [7 empty] | 74.56 | [8 empty] | 31080 | [14 empty] | 31080
$272,747.93 0.6646 MH/TN 708.47 MH | [28 empty] | [ 85.548 ] | [10 empty] | 107513 | [8 empty] | 146930 |  |  |  | 18306 |  | 272748
=====> Item Totals: 113 - PAVEMENT PATCH, TEMPORARY
$272,747.93 0.6646 MH/TN 708.47 MH | [28 empty] | [ 85.548 ] | [10 empty] | 107513 | [8 empty] | 146930 |  |  |  | 18306 |  | 272748
255.861 1066 TN | [39 empty] | 100.86 | [8 empty] | 137.83 |  |  |  | 17.17 |  | 255.86
BID ITEM = 114 CLIENT# = 114 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC, VARIABLE MIXES, 12 IN Unit = SY Takeoff Quan: 30,990.000 Engr Quan: 30,990.000
114.01 ROADWAY CEM CONC, VARIABLE MIXES, 12 IN Quan: 30,990.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 1652 | [10 empty] | CH |  |  | Prod: | [6 empty] | 1,652.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP3D | [5 empty] | 3 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 10,536.60 CY | [7 empty] | 125.15 | [9 empty] | 1453818 | [11 empty] | 1453818
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 31,180.00 LF | [7 empty] | 15.75 | [9 empty] | 541421 | [11 empty] | 541421
2JOINT | [5 empty] | JOINT MATERIAL@110.2 | [13 empty] | 1 |  |  | 14,058.00 LF | [7 empty] | 2.75 | [9 empty] | 42622 | [11 empty] | 42622
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 4,686.00 EA | [7 empty] | 2.94 | [9 empty] | 15189 | [11 empty] | 15189
3SAWSEAL | [5 empty] | SAWING AND SEALING | [13 empty] | 1 |  |  | 30,990.00 LF | [7 empty] | 3.68 | [17 empty] | 114043 |  |  |  | 114043
CEJ Cement Mason 8.00 | [22 empty] | 13,216.00 MH | [7 empty] | 64.980 1,125,970 | [21 empty] | 1125970
FOCO Concrete Forman 1.00 | [22 empty] | 1,652.00 MH | [7 empty] | 68.980 149,198 | [21 empty] | 149198
$3,442,260.59 0.4797 MH/SY | [22 empty] | 14,868.00 MH | [7 empty] | [ 34.527 ] 1,275,167 | [13 empty] | 2053050 |  |  |  | 114043 |  |  |  | 3442261
=====> Item Totals: 114 - ROADWAY CEM CONC, VARIABLE MIXES, 12 IN $3,442,260.59 0.4797 MH/SY 111.076 30990 SY
14,868.00 MH | [30 empty] | [ 34.527 ] 1,275,167 | [13 empty] | 2053050 |  |  |  | 114043 |  |  |  | 3442261
[31 empty] | 41.15 | [13 empty] | 66.25 |  |  |  | 3.68 |  |  |  | 111.08
BID ITEM = 115 CLIENT# = 115 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC, HES (24 HR), 12 IN Unit = SY Takeoff Quan: 23,997.000 Engr Quan: 23,997.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 115 CLIENT# = 115 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC, HES (24 HR), 12 IN Unit = SY Takeoff Quan: 23,997.000 Engr Quan: 23,997.000
115.01 ROADWAY CEM CONC, HES (24 HR), 12 IN Quan: 23,997.00 SY Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 1279 | [10 empty] | CH |  |  | Prod: | [6 empty] | 1,279.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP1D | [5 empty] | 1 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 8,158.29 CY | [7 empty] | 187.15 | [9 empty] | 1683323 | [11 empty] | 1683323
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 24,144.00 LF | [7 empty] | 15.75 | [9 empty] | 419245 | [11 empty] | 419245
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 3,628.00 SY | [7 empty] | 2.94 | [9 empty] | 11760 | [11 empty] | 11760
3SAWSEAL | [5 empty] | SAWING AND SEALING | [13 empty] | 1 |  |  | 24,144.00 LF | [7 empty] | 3.68 | [17 empty] | 88850 |  |  |  | 88850
CEJ Cement Mason 8.00 | [22 empty] | 10,232.00 MH | [7 empty] | 64.980 1,180,961 | [21 empty] | 1180961
FOCO Concrete Forman 1.00 | [22 empty] | 1,279.00 MH | [7 empty] | 68.980 156,543 | [21 empty] | 156543
$3,540,681.84 0.4796 MH/SY | [22 empty] | 11,511.00 MH | [7 empty] | [ 47.075 ] 1,337,503 | [13 empty] | 2114329 |  |  |  | 88850 |  |  |  | 3540682
=====> Item Totals: 115 - ROADWAY CEM CONC, HES (24 HR), 12 IN $3,540,681.84 0.4796 MH/SY 147.547 23997 SY
11,511.00 MH | [30 empty] | [ 47.075 ] 1,337,503 | [13 empty] | 2114329 |  |  |  | 88850 |  |  |  | 3540682
[31 empty] | 55.74 | [13 empty] | 88.11 |  |  |  | 3.7 |  |  |  | 147.55
BID ITEM = 116 CLIENT# = 116 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC BASE, VARIABLE MIXES, 1 Unit = SY Takeoff Quan: 2,045.000 Engr Quan: 2,045.000
116.01 ROADWAY CEM CONC BASE, VARIABLE MIXES Quan: 2,045.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 109 | [10 empty] | CH |  |  | Prod: | [6 empty] | 109.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP3D | [5 empty] | 3 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 576.15 CY | [7 empty] | 125.15 | [13 empty] | 79496 |  |  |  | 79496
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 2,057.00 LF | [7 empty] | 15.75 | [13 empty] | 35719 |  |  |  | 35719
2JOINT | [5 empty] | JOINT MATERIAL@110.2 | [13 empty] | 1 |  |  | 2,985.00 LF | [7 empty] | 2.75 | [13 empty] | 9050 |  |  |  | 9050
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 309.00 EA | [7 empty] | 2.94 | [13 empty] | 1002 |  |  |  | 1002
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 872.00 MH | [7 empty] | 64.98 | [9 empty] | 74292 | [7 empty] | 74292
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 109.00 MH | [7 empty] | 68.98 | [9 empty] | 9844 | [7 empty] | 9844
209402.55 | [5 empty] | 0.4797 MH/SY | [16 empty] | 981.00 MH | [7 empty] | [ 34.523 ] | [9 empty] | 84136 |  |  |  | 125266 |  |  |  | 209403
=====> Item Totals: | [9 empty] | 116 - ROADWAY CEM CONC BASE, VARIABLE MIXES, 1
209402.55 | [9 empty] | 0.4797 MH/SY 981.00 MH [ 34.523 ] 84,136 125,266 | [42 empty] | 209403
102.397 | [9 empty] | 2045 SY 41.14 61.25 | [42 empty] | 102.4
BID ITEM = 117 CLIENT# = 117 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC BASE, HES (24 HR), 10 I Unit = SY Takeoff Quan: 1,730.000 Engr Quan: 1,730.000
117.01 ROADWAY CEM CONC BASE, HES (24 HR), 10 I Quan: 1,730.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 92 | [10 empty] | CH |  |  | Prod: | [6 empty] | 92.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP1D | [5 empty] | 1 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 473.01 CY | [5 empty] | 187.15 | [15 empty] | 97598 |  |  |  | 97598
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 1,740.00 LF | [5 empty] | 15.75 | [15 empty] | 30214 |  |  |  | 30214
2JOINT | [5 empty] | JOINT MATERIAL@110.2 | [13 empty] | 1 |  |  | 2,525.00 LF | [5 empty] | 2.75 | [15 empty] | 7655 |  |  |  | 7655
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 261.00 EA | [5 empty] | 2.94 | [15 empty] | 846 |  |  |  | 846
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 736.00 MH | [5 empty] | 64.98 | [11 empty] | 62705 | [7 empty] | 62705
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 92.00 MH | [5 empty] | 68.98 | [11 empty] | 8309 | [7 empty] | 8309
$207,327.16 0.4786 MH/SY 828.00 MH [ 34.444 ] 71,014 136,313 207,327
=====> Item Totals: 117 - ROADWAY CEM CONC BASE, HES (24 HR), 10 I $207,327.16 0.4786 MH/SY 119.842 1730 SY
828.00 MH | [30 empty] | [ 34.444 ] | [8 empty] | 71014 |  |  |  |  | 136313 | [7 empty] | 207327
[40 empty] | 41.05 |  |  |  |  | 78.79 | [7 empty] | 119.84
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 118 CLIENT# = 118 Land Item SCHEDULE: 1 100 Description = PCCP PANEL DIAMOND GRIND Unit = FA Takeoff Quan: 20,000.000 Engr Quan: 20,000.000
118.01 PCCP PANEL DIAMOND GRIND Quan: 20,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 20,000.00 FA 0.890 17,800 17,800
=====> Item Totals: 118 - PCCP PANEL DIAMOND GRIND
17800 | [30 empty] | [ ] | [8 empty] | 17800 | [12 empty] | 17800
0.89 | [5 empty] | 20000 FA | [33 empty] | 0.89 | [12 empty] | 0.89
BID ITEM = 119 CLIENT# = 119 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PCCP PANEL REINFORCING | [22 empty] | Unit = |  |  |  |  | EA Takeoff Quan: 916.000 Engr Quan: 916.000
119.01 | [5 empty] | PCCP PANEL REINFORCING | [22 empty] | Quan: |  |  |  |  | 916.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 152.34 | [10 empty] | CH Prod: 152.3473 CH Lab Pcs: 9.00 Eqp Pcs: 0.00
2RB05 | [5 empty] | #5 Rebar@110.25% | [13 empty] | 1.00 225,336.00 LF | [10 empty] | 1.000 248,433 248,433
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 1,218.78 MH | [5 empty] | 64.98 | [8 empty] | 103837 | [6 empty] | 103837
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 152.35 MH | [5 empty] | 68.98 | [8 empty] | 13759 | [6 empty] | 13759
366029.15 | [5 empty] | 1.4968 MH/EA | [13 empty] | 1,371.13 MH | [8 empty] | [ 107.725 ] | [8 empty] | 117596 | [6 empty] | 248433 | [7 empty] | 366029
=====> Item Totals: | [9 empty] | 119 | [6 empty] | - PCCP PANEL REINFORCING
366029.15 | [9 empty] | 1.4968 MH/EA | [6 empty] | 1,371.13 MH | [14 empty] | [ 107.725 ] | [5 empty] | 117596 | [6 empty] | 248433 | [7 empty] | 366029
399.595 | [9 empty] | 916 EA | [27 empty] | 128.38 | [6 empty] | 271.22 | [7 empty] | 399.6
BID ITEM = 120 CLIENT# = 120 Land Item SCHEDULE: 1 100 Description = AREAWAY PROTECTION ZONE 1 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
3AREAWAY AREA WAY PROTECTIO 1.00 1.00 LS 26,000.000 =====> Item Totals: 120 - AREAWAY PROTECTION ZONE 1 $26,000.00 [ ] 26,000.000 1 EA
[38 empty] | 26000 | [14 empty] | 26000
[38 empty] | 26000 | [14 empty] | 26000
[38 empty] | 26000 | [14 empty] | 26000
BID ITEM = 121 CLIENT# = 121 Land Item SCHEDULE: 1 100 Description = AREAWAY PROTECTION ZONE 2 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
3AREAWAY AREA WAY PROTECTIO 1.00 1.00 LS 26,000.000 =====> Item Totals: 121 - AREAWAY PROTECTION ZONE 2 $26,000.00 [ ] 26,000.000 1 EA
[38 empty] | 26000 | [14 empty] | 26000
[38 empty] | 26000 | [14 empty] | 26000
[38 empty] | 26000 | [14 empty] | 26000
BID ITEM = 122 CLIENT# = 122 Land Item SCHEDULE: 1 100 Description = MAINTENANCE HOLE, TYPE 204A Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  | Unit Cost | [11 empty] | Perm Constr Labor Material Matl/Exp | [11 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 122 CLIENT# = 122 Description = MAINTENANCE HOLE, TYPE 204A | [26 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
122.01 | [5 empty] | MAINTENANCE HOLE, TYPE 204A | [20 empty] | Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 32 | [7 empty] | CH | Prod: | [8 empty] | 32.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH204A | [5 empty] | TYPE 204A MAIN@110.2 | [13 empty] | 1 |  |  | 6.00 EA | [5 empty] | 1796 | [15 empty] | 11881 | [9 empty] | 11881
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  | 6.00 EA | [5 empty] | 785 | [15 empty] | 5193 | [9 empty] | 5193
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 36.00 TCY | [5 empty] | 24.5 | [19 empty] | 882 | [5 empty] | 882
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 68.251 | [23 empty] | 2184 |  | 2184
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 78 | [23 empty] | 2496 |  | 2496
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 81.5 | [23 empty] | 2608 |  | 2608
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 77.06 | [11 empty] | 3221 | [13 empty] | 3221
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 64.00 MH | [5 empty] | 53.88 | [11 empty] | 4544 | [13 empty] | 4544
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [11 empty] | 3118 | [13 empty] | 3118
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [11 empty] | 3118 | [13 empty] | 3118
39244.92 | [5 empty] | 26.6666 MH/EA | [13 empty] | 160.00 MH | [8 empty] | [ 1959.113 ] | [11 empty] | 14002 |  |  |  | 17073 |  |  |  | 882 |  |  |  | 7288 |  | 39245
122.02 CHANNEL MH Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 16.00 CH Prod: 2CR040 4000LB READY M@110.2 1.00 24.00 CY 121.150
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
3206 | [56 empty] | 3206
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
$11,466.45 16.0000 MH/EA 96.00 MH [ 1155.382 ]
8261 | 3206 | [15 empty] | 11466
22262 | 20279 |  |  | 882 |  |  |  |  | 7288 | [7 empty] | 50711
=====> Item Totals: 122 - MAINTENANCE HOLE, TYPE 204A $50,711.37 42.6666 MH/EA 256.00 MH [ 3114.495 ] 8,451.895 6 EA 3,710.40 3,379.83 147.00 1,214.67 8,451.90
BID ITEM = 123 CLIENT# = 123 Land Item SCHEDULE: 1 100
Description = | [7 empty] | MAINTENANCE HOLE, TYPE 204.5A | [20 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
123.01 | [7 empty] | MAINTENANCE HOLE, TYPE 204.5A | [20 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [7 empty] | Unerground Utilities 6 Man | [20 empty] | 8 |  | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH2045A | [7 empty] | TYPE 204.5A MA@110.25 | [11 empty] | 1 |  |  | 1.00 EA | [5 empty] | 2225.4 | [15 empty] | 2454 | [9 empty] | 2454
2CPSZ230 | [7 empty] | TYPE 230 CASTI@110.25 | [11 empty] | 1 |  |  | 1.00 EA | [5 empty] | 785 | [15 empty] | 865 | [9 empty] | 865
3DEDU02D | [7 empty] | Dirt Trucking and Dump | [11 empty] | 1 |  |  | 6.00 TCY | [5 empty] | 24.5 | [19 empty] | 147 | [5 empty] | 147
8EX135A | [7 empty] | 135 Excavator W/Attach | [11 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [7 empty] | 200 Excavator | [11 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [7 empty] | 950 Loader | [11 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [7 empty] | Civil Forman | [11 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAP | [7 empty] | Labor Underground Water | [11 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1136 | [13 empty] | 1136
OPE | [7 empty] | Operator - Excavator | [11 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
OPL | [7 empty] | Operator - Loader | [11 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
$8,788.36 40.0000 MH/EA 40.00 MH | [28 empty] | [ 2938.68 ] | [11 empty] | 3500 |  |  |  | 3319 |  |  |  | 147 |  |  |  | 1822 |  | 8788
123.02 | [7 empty] | CHANNEL MH 204.5 | [20 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [7 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 | [11 empty] | 1 |  |  | 2.00 CY | [5 empty] | 4.00 CH Prod: 4.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 267 267
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [8 empty] | 1704 | [12 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [8 empty] | 361 | [12 empty] | 361
$2,332.34 24.0000 MH/EA 24.00 MH [ 1733.07 ]
2065 | 267 | [15 empty] | 2332
5566 | 3586 |  |  | 147 |  |  |  |  | 1822 | [7 empty] | 11121
=====> Item Totals: 123 - MAINTENANCE HOLE, TYPE 204.5A $11,120.70 64.0000 MH/EA 64.00 MH [ 4671.75 ]
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 123 CLIENT# = 123 Land Item SCHEDULE: 1 100 Description = MAINTENANCE HOLE, TYPE 204.5A Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000 11,120.700 1 EA 5,565.60 3,586.10 147.00 1,822.00 11,120.70
BID ITEM = 124 CLIENT# = 124 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MAINTENANCE HOLE, TYPE 204B | [18 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
124.01 | [5 empty] | MAINTENANCE HOLE, TYPE 204B | [18 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [18 empty] | 16 | [5 empty] | CH | Prod: | [8 empty] | 16.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH204B | [5 empty] | TYPE 204B MAIN@110.2 | [13 empty] | 1 |  |  |  |  | 3.00 EA | [5 empty] | 1643.6 | [13 empty] | 5436 | [9 empty] | 5436
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  |  |  | 3.00 EA | [5 empty] | 785 | [13 empty] | 2596 | [9 empty] | 2596
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 15.00 TCY | [5 empty] | 24.5 | [17 empty] | 368 | [5 empty] | 368
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 68.251 | [21 empty] | 1092 |  | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 78 | [21 empty] | 1248 |  | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 81.5 | [21 empty] | 1304 |  | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 77.06 | [9 empty] | 1610 | [13 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 32.00 MH | [5 empty] | 53.88 | [9 empty] | 2272 | [13 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 74.56 | [9 empty] | 1559 | [13 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 74.56 | [9 empty] | 1559 | [13 empty] | 1559
$19,044.89 26.6666 MH/EA 80.00 MH | [30 empty] | [ 1959.12 ] | [9 empty] | 7001 |  |  |  | 8033 |  |  |  | 368 |  |  |  | 3644 |  | 19045
124.02 | [5 empty] | CHANNEL MH 204B | [22 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 | [13 empty] | 1 |  |  |  |  | 5.00 CY |  |  |  | 6.00 CH Prod: 6.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 668 668
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 30.00 MH | [7 empty] | 64.98 | [8 empty] | 2556 | [12 empty] | 2556
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 68.98 | [8 empty] | 542 | [12 empty] | 542
$3,765.64 12.0000 MH/EA 36.00 MH [ 866.537 ]
3098 | 668 | [15 empty] | 3766
10099 | 8700 |  |  | 368 |  |  |  |  | 3644 | [7 empty] | 22811
=====> Item Totals: 124 - MAINTENANCE HOLE, TYPE 204B $22,810.53 38.6666 MH/EA 116.00 MH [ 2825.657 ] 7,603.510 3 EA 3,366.20 2,900.15 122.50 1,214.67 7,603.51
BID ITEM = 125 CLIENT# = 125 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MAINTENANCE HOLE, TYPE 205B | [18 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
125.01 | [5 empty] | MAINTENANCE HOLE, TYPE 205B | [18 empty] | Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [18 empty] | 16 | [5 empty] | CH | Prod: | [9 empty] | 16.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH205B | [5 empty] | TYPE 205B MAIN@110.2 | [13 empty] | 1 |  |  |  |  | 2.00 EA | [5 empty] | 2125.1 | [13 empty] | 4686 | [9 empty] | 4686
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  |  |  | 2.00 EA | [5 empty] | 785 | [13 empty] | 1731 | [9 empty] | 1731
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 15.00 TCY | [5 empty] | 24.5 | [17 empty] | 368 | [5 empty] | 368
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 68.251 | [21 empty] | 1092 |  | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 78 | [21 empty] | 1248 |  | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 16.00 HR | [5 empty] | 81.5 | [21 empty] | 1304 |  | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 77.06 | [10 empty] | 1610 | [12 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 32.00 MH | [5 empty] | 53.88 | [10 empty] | 2272 | [12 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 74.56 | [10 empty] | 1559 | [12 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 16.00 MH | [5 empty] | 74.56 | [10 empty] | 1559 | [12 empty] | 1559
$17,429.07 40.0000 MH/EA 80.00 MH | [30 empty] | [ 2938.68 ] | [10 empty] | 7001 |  |  | 6417 |  |  |  | 368 |  |  |  | 3644 |  | 17429
125.02 | [5 empty] | CHANNEL MH 205B | [24 empty] | Quan: |  |  | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 | [13 empty] | 1 |  |  |  |  | 5.00 CY |  |  |  | 6 |  | CH |  |  | Prod: 6.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 668 668
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 125 CLIENT# = 125 Land Item SCHEDULE: 1 100 Description = MAINTENANCE HOLE, TYPE 205B Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 30.00 MH | [7 empty] | 64.98 | [8 empty] | 2556 | [12 empty] | 2556
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 68.98 | [8 empty] | 542 | [12 empty] | 542
$3,765.64 18.0000 MH/EA 36.00 MH [ 1299.805 ]
3098 | 668 | [15 empty] | 3766
10099 | 7085 |  |  | 368 |  |  |  |  | 3644 | [7 empty] | 21195
=====> Item Totals: 125 - MAINTENANCE HOLE, TYPE 205B $21,194.71 58.0000 MH/EA 116.00 MH [ 4238.485 ] 10,597.355 2 EA 5,049.30 3,542.31 183.75 1,822.00 10,597.36
BID ITEM = 126 CLIENT# = 126 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MAINTENANCE HOLE, TYPE 206B | [18 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
126.01 | [5 empty] | MAINTENANCE HOLE, TYPE 206B | [18 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [18 empty] | 8 | [5 empty] | CH | Prod: | [9 empty] | 8.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH206B | [5 empty] | TYPE 206B MAIN@110.2 | [13 empty] | 1 |  |  |  |  | 1.00 EA |  |  |  | 3754.2 | [15 empty] | 4139 | [9 empty] | 4139
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  |  |  | 1.00 EA |  |  |  | 785 | [15 empty] | 865 | [9 empty] | 865
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 4.00 TCY |  |  |  | 24.5 | [19 empty] | 98 | [5 empty] | 98
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 8.00 HR |  |  |  | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 8.00 HR |  |  |  | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 8.00 HR |  |  |  | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 8.00 MH |  |  |  | 77.06 | [12 empty] | 805 | [12 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 16.00 MH |  |  |  | 53.88 | [12 empty] | 1136 | [12 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 8.00 MH |  |  |  | 74.56 | [12 empty] | 780 | [12 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 8.00 MH |  |  |  | 74.56 | [12 empty] | 780 | [12 empty] | 780
$10,424.87 40.0000 MH/EA 40.00 MH | [28 empty] | [ 2938.68 ] | [12 empty] | 3500 |  |  | 5004 |  |  |  | 98 |  |  |  | 1822 |  | 10425
126.02 | [5 empty] | CHANNEL MH 206B | [24 empty] | Quan: |  |  | 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 | [13 empty] | 1 |  |  |  |  | 4.00 CY |  |  |  | 3 |  | CH |  |  | Prod: 3.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 534 534
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 15.00 MH | [7 empty] | 64.98 | [8 empty] | 1278 | [12 empty] | 1278
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 68.98 | [8 empty] | 271 | [12 empty] | 271
$2,083.17 18.0000 MH/EA 18.00 MH [ 1299.8 ]
1549 | 534 | [15 empty] | 2083
5049 | 5539 |  |  | 98 |  |  |  |  | 1822 | [7 empty] | 12508
=====> Item Totals: 126 - MAINTENANCE HOLE, TYPE 206B $12,508.04 58.0000 MH/EA 58.00 MH [ 4238.48 ] 12,508.040 1 EA 5,049.30 5,538.74 98.00 1,822.00 12,508.04
BID ITEM = 127 CLIENT# = 127 Land Item SCHEDULE: 1 100 Description = MAINTENANCE HOLE, TYPE 207B Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
127.01 |  |  | MAINTENANCE HOLE, TYPE 207B | [23 empty] | Quan: |  |  | 4.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM |  |  | (Mod) Unerground Utilities 6 Man | [19 empty] | 48 |  |  |  | CH |  |  | Prod: | [5 empty] | 48.0000 CH Lab Pcs: 7.00 Eqp Pcs: 4.00
2CPSMH207B | [5 empty] | TYPE 207B MAIN@110.2 | [13 empty] | 1 |  |  | 4.00 EA | [7 empty] | 7451.53 | [13 empty] | 32861 | [11 empty] | 32861
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  | 4.00 EA | [7 empty] | 785 | [13 empty] | 3462 | [11 empty] | 3462
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 60.00 TCY | [7 empty] | 24.5 | [17 empty] | 1470 | [7 empty] | 1470
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 48.00 HR | [7 empty] | 68.251 | [21 empty] | 3276 |  |  |  | 3276
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 48.00 HR | [7 empty] | 78 | [21 empty] | 3744 |  |  |  | 3744
8EX400 | [5 empty] | 400 Excavator | [13 empty] | 1 |  |  | 48.00 HR | [7 empty] | 175.7 | [21 empty] | 8434 |  |  |  | 8434
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 48.00 HR | [7 empty] | 81.5 | [21 empty] | 3912 |  |  |  | 3912
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 48.00 MH | [7 empty] | 77.06 | [8 empty] | 4831 | [16 empty] | 4831
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 96.00 MH | [7 empty] | 53.88 | [8 empty] | 6816 | [16 empty] | 6816
OPE | [5 empty] | Operator - Excavator | [13 empty] | 3 |  |  | 144.00 MH | [7 empty] | 74.56 | [8 empty] | 14033 | [16 empty] | 14033
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 127 CLIENT# = 127 Land Item SCHEDULE: 1 100 Description = MAINTENANCE HOLE, TYPE 207B Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000 OPL Operator - Loader 1.00 $87,516.31 84.0000 MH/EA
48.00 MH | [30 empty] | 74.56 | [8 empty] | 4678 | [16 empty] | 4678
336.00 MH | [30 empty] | [ 6376.393 ] | [8 empty] | 30,358 36,323 | [8 empty] | 1470 |  |  |  | 19366 |  |  |  | 87516
127.02 CHANNEL MH 207B Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 16 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 13.00 CY
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1736 | [56 empty] | 1736
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
$9,997.20 24.0000 MH/EA 96.00 MH [ 1733.073 ]
8261 | 1736 | [15 empty] | 9997
38618 | 38059 |  |  | 1470 |  |  |  |  | 19366 | [7 empty] | 97514
=====> Item $97,513.51 | [6 empty] | Totals: 127 - MAINTENANCE HOLE, T 108.0000 MH/EA 432.00 MH | [23 empty] | YPE 207B [ 8109.465 ]
24378.378 | [6 empty] | 4 EA
9,654.60 9,514.87 367.50 4,841.41 24,378.38
BID ITEM = 128 CLIENT# = 128 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MAINTENANCE HOLE, TYPE 210B | [18 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
128.01 | [5 empty] | MAINTENANCE HOLE, TYPE 210B | [18 empty] | Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | (Mod) Unerground Utilities 6 Man | [18 empty] | 32 | [5 empty] | CH | Prod: | [8 empty] | 32.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 4
2CPSMH210B | [5 empty] | TYPE 210B MAIN@110.2 | [13 empty] | 1 |  |  |  |  | 2.00 EA | [5 empty] | 16006.4 | [13 empty] | 35294 | [9 empty] | 35294
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [13 empty] | 1 |  |  |  |  | 2.00 EA | [5 empty] | 785 | [13 empty] | 1731 | [9 empty] | 1731
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 60.00 TCY | [5 empty] | 24.5 | [17 empty] | 1470 | [5 empty] | 1470
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 32.00 HR | [5 empty] | 68.251 | [21 empty] | 2184 |  | 2184
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 32.00 HR | [5 empty] | 78 | [21 empty] | 2496 |  | 2496
8EX400 | [5 empty] | 400 Excavator | [13 empty] | 1 |  |  |  |  | 32.00 HR | [5 empty] | 175.7 | [21 empty] | 5622 |  | 5622
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 32.00 HR | [5 empty] | 81.5 | [21 empty] | 2608 |  | 2608
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 32.00 MH | [5 empty] | 77.06 | [9 empty] | 3221 | [13 empty] | 3221
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 64.00 MH | [5 empty] | 53.88 | [9 empty] | 4544 | [13 empty] | 4544
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  |  |  | 64.00 MH | [5 empty] | 74.56 | [9 empty] | 6237 | [13 empty] | 6237
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 32.00 MH | [5 empty] | 74.56 | [9 empty] | 3118 | [13 empty] | 3118
68525.44 | [5 empty] | 96.0000 MH/EA | [13 empty] | 192.00 MH | [10 empty] | [ 7189.595 ] | [9 empty] | 17120 |  |  |  | 37025 |  |  |  | 1470 |  |  |  | 12910 |  | 68525
128.02 CHANNEL MH 208B Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 16.00 CH Prod: 2CR040 4000LB READY M@110.2 1.00 17.00 CY 121.150
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2271 | [56 empty] | 2271
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
$10,531.47 48.0000 MH/EA 96.00 MH | [30 empty] | [ 3466.145 ] 8,261 2,271 10,531
=====> Item Totals: 128 - MAINTENANCE HOLE, TYPE 210B
79056.91 | [5 empty] | 144.0000 MH/EA | [16 empty] | 288.00 MH | [7 empty] | [ 10655.74 ] | [6 empty] | 25381 | [6 empty] | 39296 |  |  |  | 1470 |  |  |  | 12910 |  |  | 79057
39528.455 | [5 empty] | 2 EA | [31 empty] | 12690.4 | [6 empty] | 19647.85 |  |  |  | 735 |  |  |  | 6455.21 |  |  | 39528.46
BID ITEM = 129 CLIENT# = 129 Land Item SCHEDULE: 1 100 Description = EXTRA DEPTH, TYPE 204A MAINTENANCE HOLE Unit = VF Takeoff Quan: 16.000 Engr Quan: 16.000
129.01 EXTRA DEPTH, TYPE 204A MAINTENANCE HOL Quan: 16.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 16.00 CH Prod: 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 2CPSED204 EXTRA DEPTH MH@110. 1.00 3DEDU02D Dirt Trucking and Dump 1.00
16.00 LF | [30 empty] | 1 | [8 empty] | 18 | [12 empty] | 18
8.00 TCY | [30 empty] | 24.5 | [17 empty] | 196 |  |  |  | 196
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost | [5 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 129 CLIENT# = 129 Land Item SCHEDULE: 1 EXTRA DEPTH, TYPE 204A MAINTENANCE HOLE Unit = VF Takeoff Quan | [38 empty] | 100 |  |  |  | 16 |  | Engr Quan: |  |  |  | 16
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [10 empty] | 68.251 | [12 empty] | 1092 | [9 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [10 empty] | 78 | [12 empty] | 1248 | [9 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [10 empty] | 81.5 | [12 empty] | 1304 | [9 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [10 empty] | 77.06 | [5 empty] | 1610 | [16 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [10 empty] | 53.88 | [5 empty] | 2272 | [16 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [10 empty] | 74.56 | [5 empty] | 1559 | [16 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [10 empty] | 74.56 | [5 empty] | 1559 | [16 empty] | 1559
$10,858.43 5.0000 MH/VF | [22 empty] | 80.00 MH | [10 empty] | [ 367.335 ] | [5 empty] | 7001 | [6 empty] | 18 |  |  |  | 196 |  | 3644 |  |  |  | 10858
=====> Item Totals: 129 - EXTRA DEPTH, TYPE 204A MAINTENANCE HOLE
$10,858.43 5.0000 MH/VF 80.00 MH | [33 empty] | [ 367.335 ] | [5 empty] | 7001 | [6 empty] | 18 |  |  |  | 196 |  | 3644 |  |  |  | 10858
678.652 16 VF | [39 empty] | 437.55 | [6 empty] | 1.1 |  |  |  | 12.25 |  | 227.75 |  |  |  | 678.65
:
BID ITEM = 130 CLIENT# = 130 Land Item SCHEDULE: 1 100
Description = | [5 empty] | EXTRA DEPTH, TYPE 204B MAINTENANCE HOLE | [24 empty] | Unit = VF Takeoff Quan: 8.000 Engr Quan: 8.000
130.01 | [5 empty] | EXTRA DEPTH, TYPE 204B MAINTENANCE HOL | [24 empty] | Quan: 8.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2CPSED204 | [5 empty] | Unerground Utilities 6 Man 8.00 EXTRA DEPTH MH@110. 1.00 8.00 LF | [24 empty] | CH Prod: 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 1.000 9 9
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 4.00 TCY | [7 empty] | 24.5 | [13 empty] | 98 | [11 empty] | 98
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 68.251 | [21 empty] | 546 |  |  |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 78 | [21 empty] | 624 |  |  |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 81.5 | [21 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 77.06 | [8 empty] | 805 | [16 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [7 empty] | 53.88 | [8 empty] | 1136 | [16 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [8 empty] | 780 | [16 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [8 empty] | 780 | [16 empty] | 780
$5,429.22 5.0000 MH/VF | [22 empty] | 40.00 MH | [7 empty] | [ 367.335 ] | [8 empty] | 3500 |  |  |  |  | 9 |  |  |  | 98 |  |  |  | 1822 |  |  |  | 5429
=====> Item Totals: 130 - EXTRA DEPTH, TYPE 204B MAINTENANCE HOLE
5429.22 | [5 empty] | 5.0000 MH/VF | [13 empty] | 40.00 MH | [10 empty] | [ 367.335 ] | [8 empty] | 3500 |  |  |  |  | 9 |  |  |  | 98 |  |  |  | 1822 |  |  |  | 5429
678.653 | [5 empty] | 8 VF | [33 empty] | 437.55 |  |  |  |  | 1.1 |  |  |  | 12.25 |  |  |  | 227.75 |  |  |  | 678.65
BID ITEM = 131 CLIENT# = 131 Land Item SCHEDULE: 1 100
Description = | [5 empty] | EXTRA DEPTH, TYPE 206B MAINTENANCE HOLE | [24 empty] | Unit = VF Takeoff Quan: 1.000 Engr Quan: 1.000
131.01 | [5 empty] | EXTRA DEPTH, TYPE 206B MAINTENANCE HOL | [24 empty] | Quan: 1.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man 2.00 | [24 empty] | CH Prod: 2.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CPSED206 | [5 empty] | EXTRA DEPTH MH@110. 1.00 1.00 VF | [24 empty] | 1.000 1 1
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 1.00 TCY | [7 empty] | 24.5 | [17 empty] | 25 | [7 empty] | 25
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 68.251 | [21 empty] | 136 |  |  |  | 136
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 78 | [21 empty] | 156 |  |  |  | 156
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 81.5 | [21 empty] | 163 |  |  |  | 163
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 77.06 | [6 empty] | 201 | [18 empty] | 201
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 4.00 MH | [7 empty] | 53.88 | [6 empty] | 284 | [18 empty] | 284
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [6 empty] | 195 | [18 empty] | 195
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [6 empty] | 195 | [18 empty] | 195
$1,356.18 10.0000 MH/VF 10.00 MH [ 734.66 ] 875 1 | [48 empty] | 25 |  |  |  | 455 |  |  |  | 1356
=====> Item Totals: 131 - EXTRA DEPTH, TYPE 206B MAINTENANCE HOLE $1,356.18 10.0000 MH/VF 10.00 MH [ 734.66 ] 875 1 | [48 empty] | 25 |  |  |  | 455 |  |  |  | 1356
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 131 CLIENT# = 131 Land Item SCHEDULE: 1 100 Description = EXTRA DEPTH, TYPE 206B MAINTENANCE HOLE Unit = VF Takeoff Quan: 1.000 Engr Quan: 1.000 1,356.180 1 VF 875.09 1.10 24.50 455.49 1,356.18
BID ITEM = 132 CLIENT# = 132 Land Item SCHEDULE: 1 100 Description = EXTRA DEPTH, TYPE 207B MAINTENANCE HOLE Unit = VF Takeoff Quan: 22.000 Engr Quan: 22.000
132.01 EXTRA DEPTH, TYPE 207B MAINTENANCE HOL Quan: 22.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 33.00 CH Prod: 33.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CPSED207 | [5 empty] | EXTRA DEPTH MH@110. | [12 empty] | 1 |  |  |  | 22.00 VF | [7 empty] | 1.000 24 24
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [12 empty] | 1 |  |  |  | 31.00 TCY | [7 empty] | 24.5 | [17 empty] | 760 | [7 empty] | 760
8EX135A | [5 empty] | 135 Excavator W/Attach | [12 empty] | 1 |  |  |  | 33.00 HR | [7 empty] | 68.251 | [21 empty] | 2252 |  |  |  | 2252
8EX200 | [5 empty] | 200 Excavator | [12 empty] | 1 |  |  |  | 33.00 HR | [7 empty] | 78 | [21 empty] | 2574 |  |  |  | 2574
8LO950 | [5 empty] | 950 Loader | [12 empty] | 1 |  |  |  | 33.00 HR | [7 empty] | 81.5 | [21 empty] | 2689 |  |  |  | 2689
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 33.00 MH | [7 empty] | 77.06 | [6 empty] | 3321 | [18 empty] | 3321
LAP | [5 empty] | Labor Underground Water | [12 empty] | 2 |  |  |  | 66.00 MH | [7 empty] | 53.88 | [6 empty] | 4686 | [18 empty] | 4686
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 33.00 MH | [7 empty] | 74.56 | [6 empty] | 3216 | [18 empty] | 3216
OPL | [5 empty] | Operator - Loader | [12 empty] | 1 |  |  |  | 33.00 MH | [7 empty] | 74.56 | [6 empty] | 3216 | [18 empty] | 3216
22738.65 | [5 empty] | 7.5000 MH/VF | [16 empty] | 165.00 MH | [7 empty] | [ 551.001 ] | [6 empty] | 14439 | [6 empty] | 24 |  |  |  | 760 |  |  |  | 7516 |  |  |  | 22739
=====> Item Totals: 132 - EXTRA DEPTH, TYPE 207 $22,738.65 7.5000 MH/VF 165.00 MH | [30 empty] | B MAINTENAN [ 551.001 ] | [6 empty] | CE HOLE 14,439 | [6 empty] | 24 |  |  |  | 760 |  |  |  | 7516 |  |  |  | 22739
1,033.575 22 VF | [37 empty] | 656.32 | [6 empty] | 1.1 |  |  |  | 34.52 |  |  |  | 341.63 |  |  |  | 1033.58
BID ITEM = 133 CLIENT# = 133 Land Item SCHEDULE: 1 100 Description = EXTRA DEPTH TYPE 210B MAINTENANCE HOLE Unit = VF Takeoff Quan: 4.000 Engr Quan: 4.000
133.01 EXTRA DEPTH TYPE 210B MAINTENANCE HOL Quan: 4.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM (Mod) Unerground Utilities 6 Man 8.00 CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 4.00
2CPSED210 | [5 empty] | EXTRA DEPTH MH@110. | [12 empty] | 1 |  |  |  | 4.00 VF | [7 empty] | 1.000 4 4
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [12 empty] | 1 |  |  |  | 12.00 TCY | [7 empty] | 24.5 | [13 empty] | 294 | [11 empty] | 294
8EX135A | [5 empty] | 135 Excavator W/Attach | [12 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 68.251 | [21 empty] | 546 |  |  |  | 546
8EX200 | [5 empty] | 200 Excavator | [12 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 78 | [21 empty] | 624 |  |  |  | 624
8EX400 | [5 empty] | 400 Excavator | [12 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 175.7 | [21 empty] | 1406 |  |  |  | 1406
8LO950 | [5 empty] | 950 Loader | [12 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 81.5 | [21 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 8.00 MH | [7 empty] | 77.06 | [8 empty] | 805 | [16 empty] | 805
LAP | [5 empty] | Labor Underground Water | [12 empty] | 2 |  |  |  | 16.00 MH | [7 empty] | 53.88 | [8 empty] | 1136 | [16 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [12 empty] | 2 |  |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [16 empty] | 1559
OPL | [5 empty] | Operator - Loader | [12 empty] | 1 |  |  |  | 8.00 MH | [7 empty] | 74.56 | [8 empty] | 780 | [16 empty] | 780
$7,806.01 12.0000 MH/VF | [22 empty] | 48.00 MH | [7 empty] | [ 898.703 ] | [8 empty] | 4280 |  |  |  |  | 4 |  |  |  | 294 |  |  |  | 3228 |  |  |  | 7806
=====> Item $7,806.01 | [5 empty] | Totals: 133 - 12.0000 MH/VF | [12 empty] | EXTRA DEPTH TYPE 210B 48.00 MH | [11 empty] | MAINTENANCE HOLE [ 898.703 ] 4,280 | [13 empty] | 4 |  |  |  | 294 |  |  |  | 3228 |  |  |  | 7806
1951.503 | [5 empty] | 4 VF | [24 empty] | 1070 | [13 empty] | 1.1 |  |  |  | 73.5 |  |  |  | 806.9 |  |  |  | 1951.5
BID ITEM = 134 CLIENT# = 134 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | RECHANNEL MAINTENANCE HOLE | [24 empty] | Unit = |  |  | EA Takeoff Quan: 2.000 Engr Quan: 2.000
| 134.01 |  |  |  |  | RECHANNEL MAINTENANCE HOLE | [24 empty] | Quan: |  |  | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 6.00 CH Prod: 6.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
| Activity Desc Resource Pcs | [21 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 134 CLIENT# = 134 Land Item SCHEDULE: 1 100
Description = | [5 empty] | RECHANNEL MAINTENANCE HOLE | [24 empty] | Unit = |  |  | EA Takeoff Quan: 2.000 Engr Quan: 2.000
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [18 empty] | 8.00 CY | [8 empty] | 121.150 1,069 1,069
CEJ | [5 empty] | Cement Mason | [12 empty] | 5 | [5 empty] | 30.00 MH | [5 empty] | 64.98 | [8 empty] | 2556 | [12 empty] | 2556
FOCO | [5 empty] | Concrete Forman | [12 empty] | 1 | [5 empty] | 6.00 MH | [5 empty] | 68.98 | [8 empty] | 542 | [12 empty] | 542
$4,166.34 18.0000 MH/EA 36.00 MH [ 1299.805 ] 3,098 1,069 4,166
=====> Item Totals: 134 - RECHANNEL MAINTENANCE HOLE
4166.34 | [5 empty] | 18.0000 MH/EA | [16 empty] | 36.00 MH | [7 empty] | [ 1299.805 ] | [6 empty] | 3098 | [6 empty] | 1069 | [7 empty] | 4166
2083.17 | [5 empty] | 2 EA | [31 empty] | 1548.9 | [6 empty] | 534.27 | [7 empty] | 2083.17
BID ITEM = 135 CLIENT# = 135 Land Item SCHEDULE: 1 100 Description = REBUILD MAINTENANCE HOLE Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
135.01 | [5 empty] | REBUILD MAINTENANCE HOLE | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 1 | [5 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 | [12 empty] | 1 | [5 empty] | 1.00 EA 785.000 865 865
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 | [5 empty] | 1.00 HR 51.051 | [19 empty] | 51 | [11 empty] | 51
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 | [5 empty] | 1.00 HR 52.300 | [19 empty] | 52 | [11 empty] | 52
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 | [5 empty] | 1.00 MH 77.060 | [16 empty] | 101 | [14 empty] | 101
LAG | [5 empty] | General Laborer | [12 empty] | 2 | [5 empty] | 2.00 MH 52.910 | [16 empty] | 140 | [14 empty] | 140
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 | [5 empty] | 1.00 MH 74.560 | [16 empty] | 97 | [14 empty] | 97
$1,306.41 4.0000 MH/EA 4.00 MH | [24 empty] | [ 283.19 ] | [16 empty] | 338 |  |  | 865 | [7 empty] | 103 |  |  |  | 1306
=====> Item Totals: 135 - REBUILD MAINTENANCE HOLE
1306.41 | [5 empty] | 4.0000 MH/EA | [12 empty] | 4.00 MH | [5 empty] | [ 283.19 ] | [14 empty] | 338 |  |  |  |  | 865 | [7 empty] | 103 |  |  |  | 1306
1306.41 | [5 empty] | 1 EA | [33 empty] | 337.62 |  |  |  |  | 865.46 | [7 empty] | 103.33 |  |  |  | 1306.41
BID ITEM = 136 CLIENT# = 136 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CATCH BASIN, TYPE 240A | [16 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
136.01 | [5 empty] | CATCH BASIN, TYPE 240A | [16 empty] | Quan: 2.00 EA Hrs/Shft: 10.00 Cal: Z10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 16 | [7 empty] | CH | Prod: | [8 empty] | 16.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSCB240 | [5 empty] | TYPE 240 CATCH@110.2 | [12 empty] | 1 |  |  |  | 2.00 EA | [7 empty] | 1068.4 | [13 empty] | 2356 | [9 empty] | 2356
2CPSZ262 | [5 empty] | TYPE 262 INLET@110.25 | [12 empty] | 1 |  |  |  | 2.00 EA | [7 empty] | 375 | [13 empty] | 827 | [9 empty] | 827
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [12 empty] | 1 |  |  |  | 10.00 TCY | [7 empty] | 24.5 | [17 empty] | 245 | [5 empty] | 245
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 16.00 HR | [7 empty] | 51.051 | [21 empty] | 817 |  | 817
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 16.00 HR | [7 empty] | 52.3 | [21 empty] | 837 |  | 837
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 16.00 MH | [7 empty] | 77.06 | [9 empty] | 2542 | [13 empty] | 2542
LAP | [5 empty] | Labor Underground Water | [12 empty] | 1 |  |  |  | 16.00 MH | [7 empty] | 53.88 | [9 empty] | 1788 | [13 empty] | 1788
OPB | [5 empty] | Operator - Backhoe | [12 empty] | 1 |  |  |  | 16.00 MH | [7 empty] | 74.56 | [9 empty] | 2461 | [13 empty] | 2461
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 16.00 MH | [7 empty] | 74.56 | [9 empty] | 2461 | [13 empty] | 2461
$14,332.59 32.0000 MH/EA 64.00 MH | [30 empty] | [ 3920.84 ] | [9 empty] | 9251 |  |  |  | 3183 |  |  |  | 245 |  |  |  | 1654 |  | 14333
=====> Item $14,332.59 | [5 empty] | Totals: 136 - 32.0000 MH/EA | [12 empty] | CATCH BASIN, TYPE 240A 64.00 MH [ 3920.84 ] | [18 empty] | 9,251 3,183 245 1,654 14,333
7166.295 | [5 empty] | 2 EA | [31 empty] | 4,625.65 1,591.35 122.50 826.80 7,166.30
BID ITEM = 137 CLIENT# = 137 Land Item SCHEDULE: 1 100 Description = CATCH BASIN, TYPE 242A Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 137 CLIENT# = 137 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CATCH BASIN, TYPE 242A | [16 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
137.01 | [5 empty] | CATCH BASIN, TYPE 242A | [16 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: Z10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 24 | [7 empty] | CH | Prod: | [7 empty] | 24.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSCB242 | [5 empty] | TYPE 242 CATCH@110.2 | [13 empty] | 1 |  |  | 3.00 EA | [7 empty] | 1445.33 | [13 empty] | 4780 | [9 empty] | 4780
2CPSZ262 | [5 empty] | TYPE 262 INLET@110.25 | [13 empty] | 1 |  |  | 3.00 EA | [7 empty] | 375 | [13 empty] | 1240 | [9 empty] | 1240
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 15.00 TCY | [7 empty] | 24.5 | [17 empty] | 368 | [5 empty] | 368
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 24.00 HR | [7 empty] | 51.051 | [21 empty] | 1225 |  | 1225
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 24.00 HR | [7 empty] | 52.3 | [21 empty] | 1255 |  | 1255
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 77.06 | [8 empty] | 3813 | [14 empty] | 3813
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 53.88 | [8 empty] | 2681 | [14 empty] | 2681
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 74.56 | [8 empty] | 3691 | [14 empty] | 3691
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 74.56 | [8 empty] | 3691 | [14 empty] | 3691
$22,745.58 32.0000 MH/EA 96.00 MH | [30 empty] | [ 3920.84 ] | [8 empty] | 13877 |  |  |  |  | 6021 |  |  |  | 368 |  |  |  | 2480 |  | 22746
=====> Item Totals: 137 - CATCH BASIN, TYPE 242A $22,745.58 32.0000 MH/EA 96.00 MH [ 3920.84 ] 13,877 6,021 368 2,480 22,746 7,581.860 3 EA 4,625.64 2,006.91 122.50 826.81 7,581.86
BID ITEM = 138 CLIENT# = 138 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CATCH BASIN, TYPE 242B | [16 empty] | Unit = EA Takeoff Quan: 9.000 Engr Quan: 9.000
138.01 | [5 empty] | CATCH BASIN, TYPE 242B | [16 empty] | Quan: 9.00 EA Hrs/Shft: 10.00 Cal: Z10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 72 | [7 empty] | CH | Prod: | [7 empty] | 72.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSCB242 | [5 empty] | TYPE 242 CATCH@110.2 | [13 empty] | 1 |  |  | 9.00 EA | [7 empty] | 1445.33 | [13 empty] | 14341 | [9 empty] | 14341
2CPSZ263 | [5 empty] | TYPE 263 INLET@110.25 | [13 empty] | 1 |  |  | 9.00 EA | [7 empty] | 700 | [13 empty] | 6946 | [9 empty] | 6946
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 45.00 TCY | [7 empty] | 24.5 | [17 empty] | 1103 | [5 empty] | 1103
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 72.00 HR | [7 empty] | 51.051 | [21 empty] | 3676 |  | 3676
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 72.00 HR | [7 empty] | 52.3 | [21 empty] | 3766 |  | 3766
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 77.06 | [8 empty] | 11440 | [14 empty] | 11440
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 53.88 | [8 empty] | 8044 | [14 empty] | 8044
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 74.56 | [8 empty] | 11074 | [14 empty] | 11074
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 74.56 | [8 empty] | 11074 | [14 empty] | 11074
71461.56 | [5 empty] | 32.0000 MH/EA | [13 empty] | 288.00 MH | [10 empty] | [ 3920.84 ] | [8 empty] | 41631 |  |  |  |  | 21287 |  |  |  | 1103 |  |  |  | 7441 |  | 71462
=====> Item $71,461.56 | [5 empty] | Totals: 138 - CATCH BASIN, TYPE 242B 32.0000 MH/EA 288.00 MH [ 3920.84 ] | [31 empty] | 41,631 21,287 1,103 7,441 71,462
7940.173 | [5 empty] | 9 EA | [31 empty] | 4,625.64 2,365.23 122.50 826.81 7,940.17
BID ITEM = 139 CLIENT# = 139 Land Item SCHEDULE: 1 100 Description = INLET, TYPE 250A Unit = EA Takeoff Quan: 14.000 Engr Quan: 14.000
139.01 | [5 empty] | INLET, TYPE 250A | [24 empty] | Quan: |  |  | 14.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man 56.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 56.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2CPSIN250 | [5 empty] | TYPE 250 INLET@110.25 1.00 | [16 empty] | 14.00 EA | [5 empty] | 363 | [15 empty] | 5603 | [11 empty] | 5603
2CPSZ262 | [5 empty] | TYPE 262 INLET@110.25 1.00 | [16 empty] | 14.00 EA | [5 empty] | 375 | [15 empty] | 5788 | [11 empty] | 5788
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 56.00 HR | [5 empty] | 51.051 | [23 empty] | 2859 |  |  |  | 2859
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 56.00 HR | [5 empty] | 52.3 | [23 empty] | 2929 |  |  |  | 2929
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 56.00 MH | [5 empty] | 77.06 | [12 empty] | 7643 | [14 empty] | 7643
LAP | [5 empty] | Labor Underground Water 1.00 | [16 empty] | 56.00 MH | [5 empty] | 53.88 | [12 empty] | 5379 | [14 empty] | 5379
OPB | [5 empty] | Operator - Backhoe 1.00 | [16 empty] | 56.00 MH | [5 empty] | 74.56 | [12 empty] | 7399 | [14 empty] | 7399
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 56.00 MH | [5 empty] | 74.56 | [12 empty] | 7399 | [14 empty] | 7399
Activity Desc Resource | [13 empty] | Pcs |  |  | Quantity | [5 empty] | Unit |  |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  |  | Total
BID ITEM = 139 CLIENT# = 139 Land Item SCHEDULE: 1 100
Description = INLET, TYPE 250A Unit = | [29 empty] | EA |  |  |  |  | Takeoff Quan: | [9 empty] | 14 |  |  |  |  | Engr Quan: |  |  |  |  | 14
$44,999.41 16.0000 MH/EA 224.00 MH
[ 1680.36 ] | [37 empty] | 27821 | [6 empty] | 11391 | [7 empty] | 5788 |  |  |  | 44999
[ 1680.36 ] | [37 empty] | 27821 | [6 empty] | 11391 | [7 empty] | 5788 |  |  |  | 44999
[38 empty] | 1987.2 | [6 empty] | 813.65 | [7 empty] | 413.4 |  |  |  | 3214.24
=====> Item Totals: 139 - INLET, TYPE 250A $44,999.41 16.0000 MH/EA 224.00 MH 3,214.244 14 EA
BID ITEM = 140 CLIENT# = 140 Land Item SCHEDULE: 1 100
Description = | [5 empty] | INLET, TYPE 250B | [13 empty] | Unit = | [13 empty] | EA Takeoff Quan: 39.000 Engr Quan: 39.000
140.01 | [5 empty] | INLET, TYPE 250B | [13 empty] | Quan: | [13 empty] | 39.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 156 | [10 empty] | CH |  |  | Prod: | [6 empty] | 156.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSIN250 | [5 empty] | TYPE 250 INLET@110.25 | [13 empty] | 1 |  |  | 39.00 EA | [7 empty] | 355 | [13 empty] | 15264 | [9 empty] | 15264
2CPSZ263 | [5 empty] | TYPE 263 INLET@110.25 | [13 empty] | 1 |  |  | 39.00 EA | [7 empty] | 700 | [13 empty] | 30098 | [9 empty] | 30098
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 156.00 HR | [7 empty] | 51.051 | [17 empty] | 7964 | [5 empty] | 7964
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 156.00 HR | [7 empty] | 52.3 | [17 empty] | 8159 | [5 empty] | 8159
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 156.00 MH | [7 empty] | 77.06 | [9 empty] | 21292 | [13 empty] | 21292
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 156.00 MH | [7 empty] | 53.88 | [9 empty] | 14985 | [13 empty] | 14985
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 156.00 MH | [7 empty] | 74.56 | [9 empty] | 20612 | [13 empty] | 20612
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 156.00 MH | [7 empty] | 74.56 | [9 empty] | 20612 | [13 empty] | 20612
$138,985.68 16.0000 MH/EA 624.00 MH [ 1680.36 ] | [37 empty] | 77501 | [6 empty] | 45362 |  |  |  | 16123 | [5 empty] | 138986
=====> Item Totals: 140 - INLET, TYPE 250B $138,985.68 16.0000 MH/EA 624.00 MH [ 1680.36 ] | [37 empty] | 77501 | [6 empty] | 45362 |  |  |  | 16123 | [5 empty] | 138986
3,563.735 39 EA 1,987.19 1,163.14 413.40 3,563.74
BID ITEM = 141 CLIENT# = 141 Land Item SCHEDULE: 1 100
Description = | [5 empty] | EXTRA DEPTH, TYPE 204.5A MAINTENANCE HOL | [24 empty] | Unit = LF Takeoff Quan: 3.000 Engr Quan: 3.000
141.01 | [5 empty] | EXTRA DEPTH, TYPE 204.5A MAINTENANCE HO | [24 empty] | Quan: 3.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2CPSED2045 | [5 empty] | Unerground Utilities 6 Man 3.00 EXTRA DEPTH MH@110. 1.00 3.00 LF | [24 empty] | CH Prod: 3.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 1.000 3 3
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 3.00 TCY | [7 empty] | 24.5 | [17 empty] | 74 | [7 empty] | 74
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 68.251 | [21 empty] | 205 |  |  |  | 205
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 78 | [21 empty] | 234 |  |  |  | 234
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 81.5 | [21 empty] | 244 |  |  |  | 244
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 77.06 | [8 empty] | 302 | [16 empty] | 302
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 6.00 MH | [7 empty] | 53.88 | [8 empty] | 426 | [16 empty] | 426
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [16 empty] | 292
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [16 empty] | 292
2072.69 | [5 empty] | 5.0000 MH/LF | [16 empty] | 15.00 MH | [7 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 3 |  |  |  | 74 |  |  |  | 683 |  |  |  | 2073
=====> Item Totals: 141 - EXTRA DEPTH, TYPE 204.5A MAINTENANCE HOL
2072.69 | [5 empty] | 5.0000 MH/LF | [13 empty] | 15.00 MH | [10 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 3 |  |  |  | 74 |  |  |  | 683 |  |  |  | 2073
690.897 | [5 empty] | 3 LF | [33 empty] | 437.55 |  |  |  |  | 1.1 |  |  |  | 24.5 |  |  |  | 227.74 |  |  |  | 690.9
BID ITEM = 142 CLIENT# = 142 Land Item SCHEDULE: 1 100 Description = PIPE, CB CONN, D.I., CL 50, 8 IN Unit = LF Takeoff Quan: 779.000 Engr Quan: 779.000
Activity Desc Resource Pcs | [23 empty] | Quantity |  |  | Unit |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract Total
BID ITEM = 142 CLIENT# = 142 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, CB CONN, D.I., CL 50, 8 IN | [17 empty] | Unit = | [9 empty] | LF Takeoff Quan: 779.000 Engr Quan: 779.000
142.01 | [5 empty] | PIPE, CB CONN, D.I., CL 50, 8 IN | [17 empty] | Quan: | [9 empty] | 779.00 LF Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS 2BI142PIPE | [5 empty] | Underground Utilities 4 M BID ITEM 142 P@110.25 | [10 empty] | an 1.00 | [6 empty] | 165.7 0.97 LS | [5 empty] | 4 CH Prod: 165.7447 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 28,207.550 30,166 30,166
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [10 empty] | 1 | [6 empty] | 165.74 HR | [5 empty] | 51.051 | [22 empty] | 8461 |  |  |  | 8461
8EX100 | [5 empty] | 100 Excavator | [10 empty] | 1 | [6 empty] | 165.74 HR | [5 empty] | 52.3 | [22 empty] | 8668 |  |  |  | 8668
FOCI | [5 empty] | Civil Forman | [10 empty] | 1 | [6 empty] | 165.74 MH | [5 empty] | 77.06 | [7 empty] | 22621 | [18 empty] | 22621
LAP | [5 empty] | Labor Underground Water | [10 empty] | 1 | [6 empty] | 165.74 MH | [5 empty] | 53.88 | [7 empty] | 15921 | [18 empty] | 15921
OPB | [5 empty] | Operator - Backhoe | [10 empty] | 1 | [6 empty] | 165.74 MH | [5 empty] | 74.56 | [7 empty] | 21899 | [18 empty] | 21899
OPE | [5 empty] | Operator - Excavator | [10 empty] | 1 | [6 empty] | 165.74 MH | [5 empty] | 74.56 | [7 empty] | 21899 | [18 empty] | 21899
$129,634.67 0.8510 MH/LF 662.96 MH [ 89.378 ] 82,339 | [44 empty] | 30166 | [7 empty] | 17129 |  |  |  | 129635
=====> Item Totals: $129,634.67 | [9 empty] | 142 0.8510 MH/LF | [6 empty] | - PIPE, CB CONN, D.I., CL 50, 8 IN 662.96 MH | [16 empty] | [ 89.378 ] |  |  |  | 82339 | [6 empty] | 30166 | [7 empty] | 17129 |  |  |  | 129635
166.412 779 LF 105.70 | [44 empty] | 38.72 | [7 empty] | 21.99 |  |  |  | 166.41
BID ITEM | [5 empty] | = |  | 143 | [5 empty] | CLIENT# = | [8 empty] | 143 |  |  | Land Item | [7 empty] | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | PIPE, INLET CONN, D.I., CL 50, 8 IN | [19 empty] | Unit = | [7 empty] | LF Takeoff Quan: 1,286.000 Engr Quan: 1,286.000
143.01 | [5 empty] | PIPE, INLET CONN, D.I., CL 50, 8 IN | [19 empty] | Quan: | [7 empty] | 1,286.00 LF Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS 2BI143PIPE | [5 empty] | Underground Utilities 4 Ma BID ITEM 143 P@110.25 | [12 empty] | n 1.00 |  |  |  | 21 1.00 LS | [5 empty] | 2.00 CH Prod: 212.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 37,985.920 41,879 41,879
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 212.00 HR | [5 empty] | 51.051 | [15 empty] | 10823 | [11 empty] | 10823
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 212.00 HR | [5 empty] | 52.3 | [15 empty] | 11088 | [11 empty] | 11088
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 212.00 MH | [5 empty] | 77.06 | [10 empty] | 28935 | [16 empty] | 28935
LAP | [5 empty] | Labor Underground Water | [12 empty] | 1 |  |  |  | 212.00 MH | [5 empty] | 53.88 | [10 empty] | 20365 | [16 empty] | 20365
OPB | [5 empty] | Operator - Backhoe | [12 empty] | 1 |  |  |  | 212.00 MH | [5 empty] | 74.56 | [10 empty] | 28011 | [16 empty] | 28011
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 212.00 MH | [5 empty] | 74.56 | [10 empty] | 28011 | [16 empty] | 28011
$169,111.20 0.6594 MH/LF 848.00 MH [ 69.253 ] 105,321 41,879 21,910 169,111
=====> Item Totals: 143 - PIPE, INLET CONN, D.I., CL 50, 8 IN $169,111.20 0.6594 MH/LF 131.502 1286 LF
848.00 MH | [30 empty] | [ 69.253 ] | [8 empty] | 105321 |  |  |  |  | 41879 | [7 empty] | 21910 |  |  |  | 169111
[40 empty] | 81.9 |  |  |  |  | 32.57 | [7 empty] | 17.04 |  |  |  | 131.5
BID ITEM = 144 CLIENT# = 144 Land Item SCHEDULE: 1 100
Description = | [5 empty] | DROP CONNECTION, OUTSIDE, 8 IN | [24 empty] | Unit = VF Takeoff Quan: 14.000 Engr Quan: 14.000
144.01 | [5 empty] | DROP CONNECTION, OUTSIDE, 8 IN | [24 empty] | Quan: 14.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 20 |  | CH Prod: 20.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI144PIPE | [5 empty] | BID ITEM 144 P@110.25 1.00 1.00 LS | [24 empty] | 1,552.960 1,712 1,712
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 68.251 | [15 empty] | 1365 | [11 empty] | 1365
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 78 | [15 empty] | 1560 | [11 empty] | 1560
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 20.00 HR | [5 empty] | 81.5 | [15 empty] | 1630 | [11 empty] | 1630
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 77.06 | [8 empty] | 2013 | [18 empty] | 2013
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 40.00 MH | [5 empty] | 53.88 | [8 empty] | 2840 | [18 empty] | 2840
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 74.56 | [8 empty] | 1949 | [18 empty] | 1949
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 20.00 MH | [5 empty] | 74.56 | [8 empty] | 1949 | [18 empty] | 1949
$15,018.15 7.1428 MH/VF 100.00 MH [ 524.763 ] 8,751 | [44 empty] | 1712 | [7 empty] | 4555 |  |  |  | 15018
=====> Item Totals: 144 - DROP CONNECTION, OUTSIDE, 8 IN $15,018.15 7.1428 MH/VF 100.00 MH [ 524.763 ] 8,751 | [44 empty] | 1712 | [7 empty] | 4555 |  |  |  | 15018
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 144 CLIENT# = 144 Land Item SCHEDULE: 1 100 Description = DROP CONNECTION, OUTSIDE, 8 IN Unit = VF Takeoff Quan: 14.000 Engr Quan: 14.000 1,072.725 14 VF 625.07 122.30 325.36 1,072.73
BID ITEM = 145 CLIENT# = 145 Land Item SCHEDULE: 1 100
Description = | [5 empty] | 4 INCH DRAIN PIPE, GIP, SCH 40 | [17 empty] | Unit = EA Takeoff Quan: 59.000 Engr Quan: 59.000
145.01 | [5 empty] | 4 INCH DRAIN PIPE, GIP, SCH 40 | [17 empty] | Quan: 59.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 59 |  | CH Prod: 59.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2BI145PIPE | [5 empty] | BID ITEM 145 P@110.25 | [13 empty] | 1 |  |  |  | 1.00 LS | [6 empty] | 28,483.000 31,403 31,403
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 59.00 HR |  |  |  |  | 51.051 | [15 empty] | 3012 | [11 empty] | 3012
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  | 59.00 HR |  |  |  |  | 52.3 | [15 empty] | 3086 | [11 empty] | 3086
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 59.00 MH |  |  |  |  | 77.06 | [8 empty] | 5938 | [18 empty] | 5938
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  | 118.00 MH |  |  |  |  | 52.91 | [8 empty] | 8232 | [18 empty] | 8232
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 59.00 MH |  |  |  |  | 74.56 | [8 empty] | 5750 | [18 empty] | 5750
$57,419.66 4.0000 MH/EA 236.00 MH | [28 empty] | [ 283.184 ] | [8 empty] | 19919 | [6 empty] | 31403 | [7 empty] | 6098 |  |  |  | 57420
=====> Item Totals: 145 - 4 INCH DRAIN PIPE $57,419.66 4.0000 MH/EA 236.00 MH | [28 empty] | , GIP, SCH 40 [ 283.184 ] | [8 empty] | 19919 | [6 empty] | 31403 | [7 empty] | 6098 |  |  |  | 57420
973.215 59 EA | [37 empty] | 337.62 | [6 empty] | 532.25 | [7 empty] | 103.35 |  |  |  | 973.21
BID ITEM = 146 CLIENT# = 146 Land Item SCHEDULE: 1 100 Description = FLOW CONTROL DEVICE ASSEMBLY Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
UNM Unerground Utilities 6 Man 12.00 CH Prod: 12.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI146PIPE BID ITEM 146 P@110.25 1.00 1.00 LS 4,823.730 5,318 | [56 empty] | 5318
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 68.251 | [17 empty] | 819 | [5 empty] | 819
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 78 | [17 empty] | 936 | [5 empty] | 936
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 12.00 HR | [7 empty] | 81.5 | [17 empty] | 978 | [5 empty] | 978
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 77.06 | [8 empty] | 1208 | [14 empty] | 1208
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 24.00 MH | [7 empty] | 53.88 | [8 empty] | 1704 | [14 empty] | 1704
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 74.56 | [8 empty] | 1169 | [14 empty] | 1169
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 74.56 | [8 empty] | 1169 | [14 empty] | 1169
$13,301.75 20.0000 MH/EA 60.00 MH | [30 empty] | [ 1469.333 ] | [8 empty] | 5251 |  |  |  |  | 5318 |  |  |  | 2733 | [5 empty] | 13302
=====> Item Totals: 146 - FLOW CONTROL DEVICE ASSEMBLY $13,301.75 20.0000 MH/EA 60.00 MH [ 1469.333 ] 5,251 5,318 2,733 13,302 4,433.917 3 EA 1,750.20 1,772.72 911.00 4,433.92
BID ITEM = 147 CLIENT# = 147 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, DETENTION, CONC, 48 IN | [17 empty] | Unit = LF Takeoff Quan: 105.000 Engr Quan: 105.000
147.01 | [5 empty] | PIPE, DETENTION, CONC, 48 IN | [17 empty] | Quan: 105.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | (Mod) Unerground Utilities 6 Man | [17 empty] | 48 | [6 empty] | CH | Prod: | [9 empty] | 48.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 4
2CONPIPE48 | [5 empty] | CONCRETE PIPE @110.2 | [13 empty] | 1 |  |  |  | 1.00 LS |  |  |  |  | 31136 | [12 empty] | 34327 | [12 empty] | 34327
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 48.00 HR |  |  |  |  | 68.251 | [19 empty] | 3276 | [5 empty] | 3276
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  | 48.00 HR |  |  |  |  | 78 | [19 empty] | 3744 | [5 empty] | 3744
8EX400 | [5 empty] | 400 Excavator | [13 empty] | 1 |  |  |  | 48.00 HR |  |  |  |  | 175.7 | [19 empty] | 8434 | [5 empty] | 8434
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  | 48.00 HR |  |  |  |  | 81.5 | [19 empty] | 3912 | [5 empty] | 3912
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 147 CLIENT# = 147 Land Item SCHEDULE: 1 100 Description = PIPE, DETENTION, CONC, 48 IN Unit = LF Takeoff Quan: 105.000 Engr Quan: 105.000
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 48.00 MH | [7 empty] | 77.06 | [8 empty] | 4831 | [12 empty] | 4831
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 96.00 MH | [7 empty] | 53.88 | [8 empty] | 6816 | [12 empty] | 6816
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 96.00 MH | [7 empty] | 74.56 | [8 empty] | 9355 | [12 empty] | 9355
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 48.00 MH | [7 empty] | 74.56 | [8 empty] | 4678 | [12 empty] | 4678
$79,373.05 2.7428 MH/LF 288.00 MH [ 205.417 ] 25,680 34,327 19,366 79,373
=====> Item Totals: 147 - PIPE, DETENTION, CONC, 48 IN $79,373.05 2.7428 MH/LF 755.934 105 LF
288.00 MH | [30 empty] | [ 205.417 ] | [8 empty] | 25680 |  |  |  |  | 34327 | [7 empty] | 19366 |  |  |  | 79373
[40 empty] | 244.57 |  |  |  |  | 326.93 | [7 empty] | 184.43 |  |  |  | 755.93
BID ITEM = 148 CLIENT# = 148 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, DETENTION, POLYPROPYLENE, 48 IN | [23 empty] | Unit = LF Takeoff Quan: 210.000 Engr Quan: 210.000
148.01 | [5 empty] | PIPE, DETENTION, POLYPROPYLENE, 48 IN | [23 empty] | Quan: 210.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2BI148PIPE | [5 empty] | (Mod) Unerground Utilities BID ITEM 148 P@110.25 | [12 empty] | 6 Man 1.00 |  |  |  | 42.0 1.00 LS | [6 empty] | 0 CH Prod: 42.0000 CH Lab Pcs: 6.00 Eqp Pcs: 4.00 38,308.200 42,235 42,235
8EX135A | [5 empty] | 135 Excavator W/Attach | [12 empty] | 1 |  |  |  | 42.00 HR | [6 empty] | 68.251 | [14 empty] | 2867 | [11 empty] | 2867
8EX200 | [5 empty] | 200 Excavator | [12 empty] | 1 |  |  |  | 42.00 HR | [6 empty] | 78 | [14 empty] | 3276 | [11 empty] | 3276
8EX400 | [5 empty] | 400 Excavator | [12 empty] | 1 |  |  |  | 42.00 HR | [6 empty] | 175.7 | [14 empty] | 7379 | [11 empty] | 7379
8LO950 | [5 empty] | 950 Loader | [12 empty] | 1 |  |  |  | 42.00 HR | [6 empty] | 81.5 | [14 empty] | 3423 | [11 empty] | 3423
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 42.00 MH | [6 empty] | 77.06 | [9 empty] | 4227 | [16 empty] | 4227
LAP | [5 empty] | Labor Underground Water | [12 empty] | 2 |  |  |  | 84.00 MH | [6 empty] | 53.88 | [9 empty] | 5964 | [16 empty] | 5964
OPE | [5 empty] | Operator - Excavator | [12 empty] | 2 |  |  |  | 84.00 MH | [6 empty] | 74.56 | [9 empty] | 8186 | [16 empty] | 8186
OPL | [5 empty] | Operator - Loader | [12 empty] | 1 |  |  |  | 42.00 MH | [6 empty] | 74.56 | [9 empty] | 4093 | [16 empty] | 4093
$81,649.68 1.2000 MH/LF 252.00 MH [ 89.87 ] 22,470 | [44 empty] | 42235 | [7 empty] | 16945 |  |  |  | 81650
=====> Item Totals: 148 - PIPE, DETENTION, POLYPROPYLENE, 48 IN
$81,649.68 1.2000 MH/LF 252.00 MH | [29 empty] | [ 89.87 ] | [9 empty] | 22470 |  |  |  |  | 42235 | [7 empty] | 16945 |  |  |  | 81650
388.808 210 LF | [39 empty] | 107 |  |  |  |  | 201.12 | [7 empty] | 80.69 |  |  |  | 388.81
BID ITEM = 149 CLIENT# = 149 Land Item SCHEDULE: 1 100 Description = PIPE, DETENTION, STEEL REINFORCED POLYET Unit = LF Takeoff Quan: 250.000 Engr Quan: 250.000
149.01 PIPE, DETENTION, STEEL REINFORCED POLYE Quan: 250.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM (Mod) Unerground Utilities 6 Man 60.00 CH Prod: 60.0000 CH Lab Pcs: 6.00 Eqp Pcs: 4.00
2BI149PIPE | [5 empty] | BID ITEM 149 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 127,388.660 140,446 140,446
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 60.00 HR | [7 empty] | 68.251 | [13 empty] | 4095 | [11 empty] | 4095
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 60.00 HR | [7 empty] | 78 | [13 empty] | 4680 | [11 empty] | 4680
8EX400 | [5 empty] | 400 Excavator | [13 empty] | 1 |  |  | 60.00 HR | [7 empty] | 175.7 | [13 empty] | 10542 | [11 empty] | 10542
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 60.00 HR | [7 empty] | 81.5 | [13 empty] | 4890 | [11 empty] | 4890
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 60.00 MH | [7 empty] | 77.06 | [8 empty] | 6039 | [16 empty] | 6039
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 120.00 MH | [7 empty] | 53.88 | [8 empty] | 8520 | [16 empty] | 8520
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 120.00 MH | [7 empty] | 74.56 | [8 empty] | 11694 | [16 empty] | 11694
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 60.00 MH | [7 empty] | 74.56 | [8 empty] | 5847 | [16 empty] | 5847
$196,753.02 1.4400 MH/LF | [22 empty] | 360.00 MH | [7 empty] | [ 107.844 ] | [8 empty] | 32100 |  |  |  |  | 140446 | [7 empty] | 24207 |  |  |  | 196753
=====> Item Totals: 149 - PIPE, DETENTION, STEEL REINFORCED POLYET
$196,753.02 1.4400 MH/LF 360.00 MH | [30 empty] | [ 107.844 ] | [8 empty] | 32100 |  |  |  |  | 140446 | [7 empty] | 24207 |  |  |  | 196753
787.012 250 LF | [39 empty] | 128.4 |  |  |  |  | 561.78 | [7 empty] | 96.83 |  |  |  | 787.01
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 150 CLIENT# = 150 Land Item SCHEDULE: 1 100 Description = PIPE,DETENTION PIPE OUTLET CONNECTION,D. Unit = LF Takeoff Quan: 297.000 Engr Quan: 297.000
150.01 PIPE,DETENTION PIPE OUTLET CONNECTION, Quan: 297.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2BI150PIPE |  |  |  |  | Unerground Utilities 6 Man BID ITEM 150 P@110.25 | [13 empty] | 1 |  |  |  | 1.00 LS | [5 empty] | 40 |  | CH Prod: 40.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 12,391.320 13,661 13,661
8EX135A |  |  |  |  | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 40.00 HR | [5 empty] | 68.251 | [15 empty] | 2730 | [11 empty] | 2730
8EX200 |  |  |  |  | 200 Excavator | [13 empty] | 1 |  |  |  | 40.00 HR | [5 empty] | 78 | [15 empty] | 3120 | [11 empty] | 3120
8LO950 |  |  |  |  | 950 Loader | [13 empty] | 1 |  |  |  | 40.00 HR | [5 empty] | 81.5 | [15 empty] | 3260 | [11 empty] | 3260
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 40.00 MH | [5 empty] | 77.06 | [10 empty] | 4026 | [16 empty] | 4026
LAP |  |  |  |  | Labor Underground Water | [13 empty] | 2 |  |  |  | 80.00 MH | [5 empty] | 53.88 | [10 empty] | 5680 | [16 empty] | 5680
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 40.00 MH | [5 empty] | 74.56 | [10 empty] | 3898 | [16 empty] | 3898
OPL |  |  |  |  | Operator - Loader | [13 empty] | 1 |  |  |  | 40.00 MH | [5 empty] | 74.56 | [10 empty] | 3898 | [16 empty] | 3898
$40,273.44 0.6734 MH/LF | [22 empty] | 200.00 MH | [5 empty] | [ 49.473 ] | [10 empty] | 17502 |  |  |  |  | 13661 | [7 empty] | 9110 |  |  |  | 40273
=====> Item Totals: 150 - PIPE,DETENTION PIPE OUTLET CONNECTION,D.
$40,273.44 0.6734 MH/LF 200.00 MH | [28 empty] | [ 49.473 ] | [10 empty] | 17502 |  |  |  |  | 13661 | [7 empty] | 9110 |  |  |  | 40273
135.601 297 LF | [39 empty] | 58.93 |  |  |  |  | 46 | [7 empty] | 30.67 |  |  |  | 135.6
BID ITEM = 151 CLIENT# = 151 Land Item SCHEDULE: 1 100 Description = FLOW SPLITTER DEVICE ASSEMBLY Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
UNM Unerground Utilities 6 Man 8.00 CH Prod: 8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI151PIPE BID ITEM 151 P@110.25 1.00 1.00 LS 3,820.140 4,212 | [56 empty] | 4212
8EX135A |  |  |  |  | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 68.251 | [17 empty] | 546 | [5 empty] | 546
8EX200 |  |  |  |  | 200 Excavator | [13 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 78 | [17 empty] | 624 | [5 empty] | 624
8LO950 |  |  |  |  | 950 Loader | [13 empty] | 1 |  |  |  | 8.00 HR | [7 empty] | 81.5 | [17 empty] | 652 | [5 empty] | 652
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 8.00 MH | [7 empty] | 77.06 | [6 empty] | 805 | [16 empty] | 805
LAP |  |  |  |  | Labor Underground Water | [13 empty] | 2 |  |  |  | 16.00 MH | [7 empty] | 53.88 | [6 empty] | 1136 | [16 empty] | 1136
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [16 empty] | 780
OPL |  |  |  |  | Operator - Loader | [13 empty] | 1 |  |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [16 empty] | 780
$9,534.10 40.0000 MH/EA 40.00 MH | [30 empty] | [ 2938.68 ] | [6 empty] | 3500 | [6 empty] | 4212 |  |  |  | 1822 | [5 empty] | 9534
=====> Ite $9,534.10 |  |  |  |  | m Totals: 151 - 40.0000 MH/EA | [13 empty] | FLOW SPLITTER DEVICE ASSEMBLY 40.00 MH [ 2938.68 ] | [18 empty] | 3,500 4,212 1,822 9,534
9534.1 |  |  |  |  | 1 EA | [32 empty] | 3,500.40 4,211.70 1,822.00 9,534.10
BID ITEM |  |  |  |  | = |  |  | 152 |  |  | CLIENT# = | [11 empty] | 152 | [5 empty] | Land Item SCHEDULE: 1 100
Description = |  |  |  |  | BEDDING, CL B, 8 IN PIPE | [17 empty] | Unit = LF Takeoff Quan: 2,090.000 Engr Quan: 2,090.000
152.01 |  |  |  |  | BEDDING, CL B, 8 IN PIPE | [17 empty] | Quan: 2,090.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 |  |  |  |  | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  |  | 1,051.96 TON | [5 empty] | 29.75 | [8 empty] | 34504 | [14 empty] | 34504
3DEDU02D |  |  |  |  | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  | 743.08 TCY | [5 empty] | 24.5 | [19 empty] | 18205 |  |  |  | 18205
52709.09 | [28 empty] | [ ] | [8 empty] | 34504 | [10 empty] | 18205 |  |  |  | 52709
=====> Item Totals: $52,709.09 | [10 empty] | 152 |  |  | - BEDDING, CL B, 8 IN PIPE | [16 empty] | [ ] | [6 empty] | 34504 | [10 empty] | 18205 |  |  |  | 52709
25.22 | [13 empty] | 2090 LF | [23 empty] | 16.51 | [10 empty] | 8.71 |  |  |  | 25.22
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 153 CLIENT# = 1 BEDDING, CL B, 10 IN PIPE | [16 empty] | 53 Land Item SCHEDULE: 1 100 Unit = LF Takeoff Quan: 136.000 Engr Quan: 136.000
153.01 | [5 empty] | BEDDING, CL B, 10 IN PIPE | [16 empty] | Quan: 136.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  | 68.00 TON | [7 empty] | 29.75 | [6 empty] | 2230 | [14 empty] | 2230
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 48.00 TCY | [7 empty] | 24.5 | [17 empty] | 1176 |  |  |  | 1176
3406.36 | [30 empty] | [ ] | [6 empty] | 2230 | [10 empty] | 1176 |  |  |  | 3406
=====> Item Totals: $3,406.36 | [10 empty] | 153 | [5 empty] | - BEDDING, CL B, 10 IN PIPE | [13 empty] | [ ] | [6 empty] | 2230 | [10 empty] | 1176 |  |  |  | 3406
25.047 | [13 empty] | 136 LF | [23 empty] | 16.4 | [10 empty] | 8.65 |  |  |  | 25.05
BID ITEM | [5 empty] | = |  | 154 |  |  | CLIENT# = | [11 empty] | 154 | Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 12 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 1,526.000 Engr Quan: 1,526.000
154.01 | [5 empty] | BEDDING, CL B, 12 IN PIPE | [16 empty] | Quan: 1,526.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  | 960.00 TON | [5 empty] | 29.75 | [8 empty] | 31487 | [14 empty] | 31487
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 678.00 TCY | [5 empty] | 24.5 | [19 empty] | 16611 |  |  |  | 16611
48098.4 | [28 empty] | [ ] | [8 empty] | 31487 | [10 empty] | 16611 |  |  |  | 48098
=====> Item Totals: $48,098.40 | [10 empty] | 154 |  |  | - BEDDING, CL B, 12 IN PIPE | [19 empty] | [ ] |  |  |  | 31487 | [10 empty] | 16611 |  |  |  | 48098
31.519 | [13 empty] | 1526 LF | [23 empty] | 20.63 | [10 empty] | 10.89 |  |  |  | 31.52
BID ITEM = 155 CLIENT# = 155 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 24 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 14.000 Engr Quan: 14.000
155.01 | [5 empty] | BEDDING, CL B, 24 IN PIPE | [16 empty] | Quan: 14.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  | 8.00 TON | [7 empty] | 29.75 | [6 empty] | 262 | [14 empty] | 262
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 7.00 TCY | [7 empty] | 24.5 | [17 empty] | 172 |  |  |  | 172
433.9 | [30 empty] | [ ] | [6 empty] | 262 | [10 empty] | 172 |  |  |  | 434
=====> $433.90 |  |  |  | Item Totals: | [6 empty] | 155 | [5 empty] | - BEDDING, CL B, 24 IN PIPE | [13 empty] | [ ] | [6 empty] | 262 | [10 empty] | 172 |  |  |  | 434
30.993 | [13 empty] | 14 LF | [23 empty] | 18.74 | [10 empty] | 12.25 |  |  |  | 30.99
BID ITEM = 156 CLIENT# = 156 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 48 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 315.000 Engr Quan: 315.000
156.01 | [5 empty] | BEDDING, CL B, 48 IN PIPE | [16 empty] | Quan: 315.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  | 465.00 TON | [7 empty] | 29.75 | [6 empty] | 15252 | [14 empty] | 15252
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 504.00 TCY | [7 empty] | 24.5 | [17 empty] | 12348 |  |  |  | 12348
27599.71 | [30 empty] | [ ] | [6 empty] | 15252 | [10 empty] | 12348 |  |  |  | 27600
=====> Item Totals: $27,599.71 | [10 empty] | 156 | [5 empty] | - BEDDING, CL B, 48 IN PIPE | [13 empty] | [ ] | [6 empty] | 15252 | [10 empty] | 12348 |  |  |  | 27600
87.618 | [13 empty] | 315 LF | [23 empty] | 48.42 | [10 empty] | 39.2 |  |  |  | 87.62
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 157 CLIENT# = 1 BEDDING, CL B, 72 IN PIPE | [16 empty] | 57 Land Item SCHEDULE: 1 100 Unit = LF Takeoff Quan: 250.000 Engr Quan: 250.000
157.01 | [5 empty] | BEDDING, CL B, 72 IN PIPE | [16 empty] | Quan: 250.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 | [5 empty] | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  | 814.00 TON | [7 empty] | 29.75 | [6 empty] | 26699 | [14 empty] | 26699
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 888.00 TCY | [7 empty] | 24.5 | [17 empty] | 21756 |  |  |  | 21756
48454.69 | [30 empty] | [ ] | [6 empty] | 26699 | [10 empty] | 21756 |  |  |  | 48455
=====> Item Totals: $48,454.69 | [10 empty] | 157 | [5 empty] | - BEDDING, CL B, 72 IN PIPE | [13 empty] | [ ] | [6 empty] | 26699 | [10 empty] | 21756 |  |  |  | 48455
193.819 | [13 empty] | 250 LF | [23 empty] | 106.79 | [10 empty] | 87.02 |  |  |  | 193.82
BID ITEM | [5 empty] | = |  | 158 | [6 empty] | CLIENT# = | [7 empty] | 158 | Land Item | [9 empty] | SCHEDULE: | [7 empty] | 1 100
Description = | [5 empty] | TELEVISION INSPECTION | [16 empty] | Unit = | [10 empty] | LF Takeoff Quan: 3,031.000 Engr Quan: 3,031.000
158.01 | [5 empty] | TELEVISION INSPECTION | [16 empty] | Quan: | [10 empty] | 3,031.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3CCTV | [5 empty] | TV INSPECTION | [8 empty] | 1 | [7 empty] | 40.64 HR | [5 empty] | 250 | [15 empty] | 10160 | [7 empty] | 10160
FOCI | [5 empty] | ==> Civil Forman | [8 empty] | 1 | [7 empty] | 40.64 MH | [5 empty] | 77.06 | [12 empty] | 4090 | [10 empty] | 4090
$14,250.31 0.0134 MH/LF 40.64 MH
[ 1.137 ] | [37 empty] | 4090 | [10 empty] | 10160 |  |  |  | 14250
[ 1.137 ] | [37 empty] | 4090 | [10 empty] | 10160 |  |  |  | 14250
[38 empty] | 1.35 | [10 empty] | 3.35 |  |  |  | 4.7
=====> Item Totals: 158 - TELEVISION INSPECTION $14,250.31 0.0134 MH/LF 40.64 MH 4.702 3031 LF
BID ITEM = 159 CLIENT# = 159 Land Item SCHEDULE: 1 100 Description = PIPE, PSD, CONC REINF, C76 CL III, 24 IN Unit = LF Takeoff Quan: 14.000 Engr Quan: 14.000
159.01 | [5 empty] | PIPE, PSD, CONC REINF, C76 CL III, 24 IN | [24 empty] | Quan: |  |  | 14.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [17 empty] | 2 | [6 empty] | CH |  |  | Prod: | [8 empty] | 2.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CONPIPE24 | [5 empty] | 24 " CONCRETE @110.25 | [13 empty] | 1 |  |  |  | 1.00 LS 806.890 890 890
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 2.00 HR 68.251 | [20 empty] | 136 | [11 empty] | 136
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  | 2.00 HR 78.000 | [20 empty] | 156 | [11 empty] | 156
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  | 2.00 HR 81.500 | [20 empty] | 163 | [11 empty] | 163
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 2.00 MH 77.060 | [18 empty] | 201 | [13 empty] | 201
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  | 4.00 MH 53.880 | [18 empty] | 284 | [13 empty] | 284
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  | 2.00 MH 74.560 | [18 empty] | 195 | [13 empty] | 195
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  | 2.00 MH 74.560 | [18 empty] | 195 | [13 empty] | 195
$2,220.18 0.7142 MH/LF 10.00 MH [ 52.476 ] 875 | [44 empty] | 890 | [7 empty] | 455 |  |  |  | 2220
=====> Item Totals: 159 - PIPE, PSD, CONC RE $2,220.18 0.7142 MH/LF 10.00 MH | [23 empty] | INF, C76 CL III, 24 IN [ 52.476 ] 875 | [20 empty] | 890 | [7 empty] | 455 |  |  |  | 2220
158.584 14 LF | [37 empty] | 62.51 | [6 empty] | 63.54 | [7 empty] | 32.54 |  |  |  | 158.58
BID ITEM = 160 CLIENT# = 160 Land Item SCHEDULE: 1 100
Description = |  |  | PIPE, PSD, D.I., CL 50, 8 IN | [21 empty] | Unit = LF Takeoff Quan: 35.000 Engr Quan: 35.000
160.01 |  |  | PIPE, PSD, D.I., CL 50, 8 IN | [21 empty] | Quan: 35.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2BI160PIPE |  |  | Unerground Utilities 6 Man BID ITEM 160 P@110.25 1.00 | [13 empty] | 1.00 LS | [7 empty] | 5.00 CH Prod: 5.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 1,810.610 1,996 1,996
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 160 CLIENT# = 160 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, PSD, D.I., CL 50, 8 IN | [24 empty] | Unit = |  |  | LF | [5 empty] | Takeoff Quan: | [8 empty] | 35 |  |  |  | Engr Quan: |  |  |  | 35
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 5.00 HR | [10 empty] | 68.251 | [18 empty] | 341 |  |  |  | 341
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 5.00 HR | [10 empty] | 78 | [18 empty] | 390 |  |  |  | 390
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 5.00 HR | [10 empty] | 81.5 | [18 empty] | 407 |  |  |  | 407
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 5.00 MH | [10 empty] | 77.06 | [5 empty] | 503 | [16 empty] | 503
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 10.00 MH | [10 empty] | 53.88 | [5 empty] | 710 | [16 empty] | 710
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 5.00 MH | [10 empty] | 74.56 | [5 empty] | 487 | [16 empty] | 487
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 5.00 MH | [10 empty] | 74.56 | [5 empty] | 487 | [16 empty] | 487
5322.69 | [5 empty] | 0.7142 MH/LF | [13 empty] | 25.00 MH | [10 empty] | [ 52.476 ] | [8 empty] | 2188 |  |  |  |  | 1996 |  |  |  | 1139 | [7 empty] | 5323
=====> Item Totals: 160 - PIPE, PSD, D.I., CL 50, 8 IN
$5,322.69 0.7142 MH/LF 25.00 MH | [30 empty] | [ 52.476 ] | [8 empty] | 2188 |  |  |  |  | 1996 |  |  |  | 1139 | [7 empty] | 5323
152.077 35 LF | [39 empty] | 62.51 |  |  |  |  | 57.03 |  |  |  | 32.54 | [7 empty] | 152.08
BID ITEM | [5 empty] | = |  | 161 | [5 empty] | CLIENT# = | [8 empty] | 161 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | PIPE, PSD, D.I., CL 50, 12 IN | [16 empty] | Unit = | [10 empty] | LF Takeoff Quan: 1,228.000 Engr Quan: 1,228.000
161.01 | [5 empty] | PIPE, PSD, D.I., CL 50, 12 IN | [16 empty] | Quan: | [10 empty] | 1,228.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 200 |  | CH | Prod: | [8 empty] | 200.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI161PIPE | [5 empty] | BID ITEM 161 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [8 empty] | 55626.58 | [8 empty] | 61328 | [15 empty] | 61328
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 200.00 HR | [5 empty] | 68.251 | [19 empty] | 13650 | [5 empty] | 13650
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 200.00 HR | [5 empty] | 78 | [19 empty] | 15600 | [5 empty] | 15600
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 200.00 HR | [5 empty] | 81.5 | [19 empty] | 16300 | [5 empty] | 16300
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 200.00 MH | [5 empty] | 77.06 | [11 empty] | 21325 | [13 empty] | 21325
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 400.00 MH | [5 empty] | 53.88 | [11 empty] | 30072 | [13 empty] | 30072
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 200.00 MH | [5 empty] | 74.56 | [11 empty] | 20646 | [13 empty] | 20646
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 200.00 MH | [5 empty] | 74.56 | [11 empty] | 20646 | [13 empty] | 20646
$199,567.91 0.8143 MH/LF 1,000.00 MH
[ 63.454 ] | [37 empty] | 92689 | [6 empty] | 61328 | [7 empty] | 45550 |  |  |  | 199568
[ 63.454 ] | [37 empty] | 92689 | [6 empty] | 61328 | [7 empty] | 45550 |  |  |  | 199568
[38 empty] | 75.48 | [6 empty] | 49.94 | [7 empty] | 37.09 |  |  |  | 162.51
=====> Item Totals: 161 - PIPE, PSD, D.I., CL 50, 12 IN $199,567.91 0.8143 MH/LF 1,000.00 MH 162.515 1228 LF
BID ITEM = 162 CLIENT# = 162 Land Item SCHEDULE: 1 100 Description = PIPE, PS or PSS, PVC, D3034 SDR 35, 8 IN Unit = LF Takeoff Quan: 12.000 Engr Quan: 12.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI162PIPE BID ITEM 162 P@110.25 1.00 1.00 LS 329.800 364 | [56 empty] | 364
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [8 empty] | 403 | [14 empty] | 403
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 53.88 | [8 empty] | 568 | [14 empty] | 568
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
3024.79 | [5 empty] | 1.6666 MH/LF | [16 empty] | 20.00 MH | [7 empty] | [ 122.443 ] | [8 empty] | 1750 |  |  |  |  | 364 |  |  |  | 911 | [5 empty] | 3025
=====> Item Totals: 162 - PIPE, PS or PSS, PVC, D3034 SDR 35, 8 IN
$3,024.79 1.6666 MH/LF 20.00 MH | [30 empty] | [ 122.443 ] | [8 empty] | 1750 |  |  |  |  | 364 |  |  |  | 911 | [5 empty] | 3025
252.066 12 LF | [39 empty] | 145.85 |  |  |  |  | 30.3 |  |  |  | 75.92 | [5 empty] | 252.07
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 163 CLIENT# = 163 Land Item SCHEDULE: 1 100 Description = PIPE, PS OR PSS, PVC D3034 SDR 35, 10IN Unit = LF Takeoff Quan: 136.000 Engr Quan: 136.000
163.01 | [5 empty] | PIPE, PS OR PSS, PVC D3034 SDR 35, 10IN | [24 empty] | Quan: |  |  | 136.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 18 | [7 empty] | CH |  |  | Prod: | [7 empty] | 18.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI163PIPE | [5 empty] | BID ITEM 163 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS 2,546.080 2,807 2,807
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 18.00 HR 68.251 | [21 empty] | 1229 | [11 empty] | 1229
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 18.00 HR 78.000 | [21 empty] | 1404 | [11 empty] | 1404
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 18.00 HR 81.500 | [21 empty] | 1467 | [11 empty] | 1467
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 18.00 MH 77.060 | [18 empty] | 1812 | [14 empty] | 1812
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 36.00 MH 53.880 | [18 empty] | 2556 | [14 empty] | 2556
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 18.00 MH 74.560 | [18 empty] | 1754 | [14 empty] | 1754
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 18.00 MH 74.560 | [18 empty] | 1754 | [14 empty] | 1754
$14,782.45 0.6617 MH/LF 90.00 MH [ 48.618 ] 7,876 | [44 empty] | 2807 | [7 empty] | 4100 |  |  |  | 14782
=====> Item Totals: 163 - PIPE, PS OR PSS, PVC D3034 SDR 35, 10IN
$14,782.45 0.6617 MH/LF 90.00 MH | [22 empty] | [ 48.618 ] | [18 empty] | 7876 |  |  | 2807 | [7 empty] | 4100 |  |  |  | 14782
108.694 136 LF | [41 empty] | 57.91 |  |  | 20.64 | [7 empty] | 30.14 |  |  |  | 108.69
BID ITEM = 164 CLIENT# = 164 Land Item SCHEDULE: 1 100 Description = TEE, 8 IN, CUT-IN EXISTING CONC PIPE Unit = EA Takeoff Quan: 23.000 Engr Quan: 23.000
164.01 | [5 empty] | TEE, 8 IN, CUT-IN EXISTING CONC PIPE | [24 empty] | Quan: |  |  | 23.00 EA | [7 empty] | Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 46 | [7 empty] | CH |  |  | Prod: | [7 empty] | 46.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3SPUCORE | [5 empty] | SPU CORE TAP | [13 empty] | 1 |  |  | 23.00 EA 150.000 | [25 empty] | 3450 | [7 empty] | 3450
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 46.00 HR 51.051 | [29 empty] | 2348 |  |  |  | 2348
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 46.00 HR 52.300 | [29 empty] | 2406 |  |  |  | 2406
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 46.00 MH 77.060 | [18 empty] | 6278 | [14 empty] | 6278
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 46.00 MH 53.880 | [18 empty] | 4419 | [14 empty] | 4419
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 46.00 MH 74.560 | [18 empty] | 6078 | [14 empty] | 6078
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 46.00 MH 74.560 | [18 empty] | 6078 | [14 empty] | 6078
$31,056.86 8.0000 MH/EA 184.00 MH | [22 empty] | [ 840.18 ] | [16 empty] | 22853 | [8 empty] | 3450 |  |  |  | 4754 |  |  |  | 31057
=====> Item Totals: 164 - TEE, 8 IN, CUT-IN EXISTING CONC PIPE
$31,056.86 8.0000 MH/EA 184.00 MH | [22 empty] | [ 840.18 ] | [16 empty] | 22853 | [8 empty] | 3450 |  |  |  | 4754 |  |  |  | 31057
1,350.298 23 EA | [39 empty] | 993.6 | [8 empty] | 150 |  |  |  | 206.7 |  |  |  | 1350.3
BID ITEM = 165 CLIENT# = 165 Land Item SCHEDULE: 1 100 Description = CASING PIPE, PVC C905 DR 14, 18 IN Unit = LF Takeoff Quan: 18.000 Engr Quan: 18.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI165PIPE BID ITEM 165 P@110.25 1.00 1.00 LS 2,493.610 2,749 | [56 empty] | 2749
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [8 empty] | 546 | [14 empty] | 546
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 53.88 | [8 empty] | 768 | [14 empty] | 768
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 529 | [14 empty] | 529
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 529 | [14 empty] | 529
$6,031.66 1.1111 MH/LF | [22 empty] | 20.00 MH | [7 empty] | [ 111.313 ] | [8 empty] | 2371 |  |  |  |  | 2749 |  |  |  | 911 | [5 empty] | 6032
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 165 CLIENT# = 165 Land Item SCHEDULE: 1 100 Description = CASING PIPE, PVC C905 DR 14, 18 IN Unit = LF Takeoff Quan: 18.000 Engr Quan: 18.000 =====> Item Totals: 165 - CASING PIPE, PVC C905 DR 14, 18 IN $6,031.66 1.1111 MH/LF 335.092 18 LF
20.00 MH | [30 empty] | [ 111.313 ] | [8 empty] | 2,371 2,749 | [12 empty] | 911 |  |  |  | 6032
[40 empty] | 131.75 152.73 | [12 empty] | 50.61 |  |  |  | 335.09
BID ITEM = 166 CLIENT# = 166 Land Item SCHEDULE: 1 100 Description = PERK FILTER CONCRETE CATCH BASIN TRIPLE Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
166.01 PERK FILTER CONCRETE CATCH BASIN TRIPL Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS Underground Utilities 4 Man 16.00 CH Prod: 16.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2BI166PIPE | [5 empty] | BID ITEM 166 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 29,172.000 32,162 32,162
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 20.00 TCY | [7 empty] | 24.5 | [13 empty] | 490 | [10 empty] | 490
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 51.051 | [21 empty] | 817 |  |  | 817
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 52.3 | [21 empty] | 837 |  |  | 837
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 77.06 | [8 empty] | 1610 | [15 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 53.88 | [8 empty] | 1136 | [15 empty] | 1136
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [15 empty] | 1559
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [15 empty] | 1559
$40,170.51 32.0000 MH/EA 64.00 MH | [30 empty] | [ 2464.535 ] | [8 empty] | 5865 |  |  |  |  | 32162 |  |  |  | 490 |  |  |  | 1654 |  |  | 40171
=====> Item Totals: 166 - PERK FILTER CONCRETE CATCH BASIN TRIPLE
40170.51 | [5 empty] | 32.0000 MH/EA | [13 empty] | 64.00 MH | [10 empty] | [ 2464.535 ] 5,865 | [13 empty] | 32162 |  |  |  | 490 |  |  |  | 1654 |  |  | 40171
20085.255 | [5 empty] | 2 EA | [24 empty] | 2932.39 | [13 empty] | 16081.07 |  |  |  | 245 |  |  |  | 826.8 |  |  | 20085.26
BID ITEM = 167 CLIENT# = 167 Land Item SCHEDULE: 1 100 Description = TEE, PVC, 10 IN Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
UNM Unerground Utilities 6 Man 3.00 CH Prod: 3.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI167PIPE BID ITEM 167 P@110.25 1.00 1.00 LS 1,158.750 1,278 | [56 empty] | 1278
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 68.251 | [17 empty] | 205 | [5 empty] | 205
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 78 | [17 empty] | 234 | [5 empty] | 234
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 81.5 | [17 empty] | 244 | [5 empty] | 244
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 77.06 | [8 empty] | 302 | [14 empty] | 302
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 6.00 MH | [7 empty] | 53.88 | [8 empty] | 426 | [14 empty] | 426
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [14 empty] | 292
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [14 empty] | 292
$3,273.40 5.0000 MH/EA 15.00 MH | [30 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 1278 |  |  |  | 683 | [5 empty] | 3273
=====> Item Totals: 167 - TEE, PVC, 10 IN
3273.4 | [5 empty] | 5.0000 MH/EA | [13 empty] | 15.00 MH | [10 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 1278 |  |  |  | 683 | [5 empty] | 3273
1091.133 | [5 empty] | 3 EA | [33 empty] | 437.55 |  |  |  |  | 425.84 |  |  |  | 227.74 | [5 empty] | 1091.13
BID ITEM = 168 CLIENT# = 168 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | TEMPORARY SEWER BYPASS | [21 empty] | Unit = LS
168.01 |  |  | MH 1 TEMP BYPASS | [21 empty] | Quan: 1.0
UNM 3TBMH1 |  |  | Unerground Utilities 6 Man TEMP BYPASS PUMPS 1.00 | [13 empty] | 1.00 LS | [7 empty] | 8.00 CH Pro 7,500.000
d:
8.0000 CH Lab Pcs: | [52 empty] | 5 |  | Eqp Pcs: |  | 3
7500 | [56 empty] | 7500
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  | Unit Cost | [10 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 168 CLIENT# = TEMPORARY SEWER BYPASS | [14 empty] | 168 |  |  |  | Land Item Unit = | [6 empty] | SCHEDULE: 1 LS Takeoff Quan: | [13 empty] | 100 |  |  | 1 |  | Engr Quan: |  |  |  | 1
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [18 empty] | 546 | [8 empty] | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [18 empty] | 624 | [8 empty] | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [18 empty] | 652 | [8 empty] | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [10 empty] | 805 | [16 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [10 empty] | 1136 | [16 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [10 empty] | 780 | [16 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [10 empty] | 780 | [16 empty] | 780
$12,822.40 40.0000 MH/LS | [22 empty] | 40.00 MH | [5 empty] | [ 2938.68 ] | [10 empty] | 3500 | [7 empty] | 7500 |  |  |  |  | 1822 |  |  |  | 12822
168.02 MH 4 TEMP BYPASS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 8 | [10 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3TBMH4 | [5 empty] | TEMP BYPASS MH 4 | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 20000 | [19 empty] | 20000 | [5 empty] | 20000
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1136 | [13 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
$25,322.40 40.0000 MH/LS | [22 empty] | 40.00 MH | [5 empty] | [ 2938.68 ] | [11 empty] | 3500 | [7 empty] | 20000 |  |  |  | 1822 |  | 25322
168.03 MH 6 TEMP BYPASS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 8 | [10 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3TBMH6 | [5 empty] | MH 6 TEMP BYPASS | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 7500 | [19 empty] | 7500 | [5 empty] | 7500
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1136 | [13 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
$12,822.40 40.0000 MH/LS | [22 empty] | 40.00 MH | [5 empty] | [ 2938.68 ] | [11 empty] | 3500 | [7 empty] | 7500 |  |  |  | 1822 |  | 12822
168.04 MH 17 TEMP BYPASS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 8 | [10 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3TBMH17 | [5 empty] | MH 17 TEMP BYPASS | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 15000 | [19 empty] | 15000 | [5 empty] | 15000
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 1092 | [13 empty] | 1092
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1537 | [13 empty] | 1537
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 1057 | [13 empty] | 1057
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 1057 | [13 empty] | 1057
$21,564.86 40.0000 MH/LS | [22 empty] | 40.00 MH | [5 empty] | [ 4007.28 ] | [11 empty] | 4743 | [7 empty] | 15000 |  |  |  | 1822 |  | 21565
168.05 | [5 empty] | MH 10C TEMP BYPASS | [24 empty] | Quan: |  |  | 1.00 LS | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 8 | [10 empty] | CH |  |  | Prod: | [6 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3TBMH10C | [5 empty] | MH 10C TEMP BYPASS | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 7500 | [19 empty] | 7500 | [5 empty] | 7500
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1136 | [13 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 168 CLIENT# = 168 Land Item SCHEDULE: 1 100 Description = TEMPORARY SEWER BYPASS Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 $12,822.40 40.0000 MH/LS 40.00 MH [ 2938.68 ] 3,500 7,500 1,822 12,822
168.06 MH 12 TEMP BYPASS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 8 | [10 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3TBMH12 | [5 empty] | TEMP BYPASS MH 12 | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 7500 | [19 empty] | 7500 | [5 empty] | 7500
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 78 | [23 empty] | 624 |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 805 | [13 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 53.88 | [11 empty] | 1136 | [13 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 780 | [13 empty] | 780
$12,822.40 40.0000 MH/LS | [22 empty] | 40.00 MH | [5 empty] | [ 2938.68 ] | [11 empty] | 3500 | [7 empty] | 7500 |  |  |  | 1822 |  | 12822
=====> Item Totals: 168 - TEMPORARY SEWER BYPASS 65,000 10,932 98,177 65,000.00 10,932.00 98,176.86
98176.86 | [5 empty] | 240.0000 MH/LS | [16 empty] | 240.00 MH | [7 empty] | [ 18700.68 ] | [6 empty] | 22245
98176.86 | [5 empty] | 1 LS | [31 empty] | 22244.86
BID ITEM = 169 CLIENT# = 169 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ADJUST EXISTING MH, CB, OR VC | [22 empty] | Unit = |  |  |  |  | EA Takeoff Quan: 400.000 Engr Quan: 400.000
169.01 | [5 empty] | ADJUST EXISTING MH, CB, OR VC | [22 empty] | Quan: |  |  |  |  | 400.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 358.20 | [24 empty] | CH |  |  | Prod: | [5 empty] | 358.2090 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 358.21 HR | [5 empty] | 51.051 | [19 empty] | 18287 | [5 empty] | 18287
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 358.21 HR | [5 empty] | 52.3 | [19 empty] | 18734 | [5 empty] | 18734
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 358.21 MH | [5 empty] | 77.06 | [10 empty] | 36053 | [14 empty] | 36053
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 716.42 MH | [5 empty] | 52.91 | [10 empty] | 49978 | [14 empty] | 49978
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 358.21 MH | [5 empty] | 74.56 | [10 empty] | 34908 | [14 empty] | 34908
$157,959.51 3.5821 MH/EA 1,432.84 MH | [28 empty] | [ 253.598 ] | [10 empty] | 120938 | [8 empty] | 37021 | [5 empty] | 157960
=====> Item Totals: 169 - ADJUST EXISTING MH, CB, OR VC $157,959.51 3.5821 MH/EA 394.899 400 EA
1,432.84 MH | [30 empty] | [ 253.598 ] | [8 empty] | 120938 | [12 empty] | 37021 |  |  |  | 157960
[40 empty] | 302.35 | [12 empty] | 92.55 |  |  |  | 394.9
BID ITEM = 170 CLIENT# = 170 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ADJUST EXISTING INLET | [16 empty] | Unit = EA Takeoff Quan: 33.000 Engr Quan: 33.000
170.01 | [5 empty] | ADJUST EXISTING INLET | [16 empty] | Quan: 33.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 16 | [7 empty] | CH | Prod: | [8 empty] | 16.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 51.051 | [19 empty] | 817 | [5 empty] | 817
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 52.3 | [19 empty] | 837 | [5 empty] | 837
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 77.06 | [11 empty] | 1610 | [13 empty] | 1610
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 32.00 MH | [5 empty] | 52.91 | [11 empty] | 2232 | [13 empty] | 2232
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [11 empty] | 1559 | [13 empty] | 1559
$7,055.49 1.9393 MH/EA 64.00 MH | [28 empty] | [ 137.302 ] | [11 empty] | 5402 | [7 empty] | 1654 | [5 empty] | 7055
=====> Item Totals: 170 - ADJUST EXISTING $7,055.49 1.9393 MH/EA 64.00 MH | [28 empty] | INLET [ 137.302 ] | [8 empty] | 5402 | [10 empty] | 1654 | [5 empty] | 7055
213.803 33 EA | [37 empty] | 163.69 | [10 empty] | 50.11 | [5 empty] | 213.8
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 171 CLIENT# = 171 Land Item SCHEDULE: 1 100 Description = ADJUST EXISTING VALVE BOX Unit = EA Takeoff Quan: 184.000 Engr Quan: 184.000
171.01 | [5 empty] | ADJUST EXISTING VALVE BOX | [24 empty] | Quan: |  |  | 184.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [17 empty] | 64.64 | [6 empty] | CH |  |  | Prod: | [7 empty] | 64.6486 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 | [5 empty] | 64.65 HR 51.051 | [28 empty] | 3300 |  |  |  | 3300
8EX100 | [5 empty] | 100 Excavator | [11 empty] | 1 | [5 empty] | 64.65 HR 52.300 | [28 empty] | 3381 |  |  |  | 3381
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 | [5 empty] | 64.65 MH 77.060 | [17 empty] | 6507 | [14 empty] | 6507
LAG | [5 empty] | General Laborer | [11 empty] | 2 | [5 empty] | 129.30 MH 52.910 | [17 empty] | 9020 | [14 empty] | 9020
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 | [5 empty] | 64.65 MH 74.560 | [17 empty] | 6300 | [14 empty] | 6300
$28,508.62 1.4054 MH/EA 258.60 MH | [23 empty] | [ 99.499 ] | [13 empty] | 21827 | [14 empty] | 6682 |  |  |  | 28509
=====> Item Totals: $28,508.62 | [9 empty] | 171 1.4054 MH/EA | [7 empty] | - ADJUST EXISTING VALVE BOX 258.60 MH | [15 empty] | [ 99.499 ] |  |  |  | 21827 | [14 empty] | 6682 |  |  |  | 28509
154.938 184 EA | [37 empty] | 118.63 | [14 empty] | 36.31 |  |  |  | 154.94
BID ITEM = 172 CLIENT# = 172 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ADJUST EXISTING HANDHOLE | [16 empty] | Unit = | [10 empty] | EA Takeoff Quan: 225.000 Engr Quan: 225.000
172.01 | [5 empty] | ADJUST EXISTING HANDHOLE | [16 empty] | Quan: | [10 empty] | 225.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 112 | [7 empty] | CH |  |  | Prod: | [5 empty] | 112.0044 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 112.00 HR | [7 empty] | 51.051 | [17 empty] | 5718 | [5 empty] | 5718
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 112.00 HR | [7 empty] | 52.3 | [17 empty] | 5858 | [5 empty] | 5858
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 112.00 MH | [7 empty] | 77.06 | [8 empty] | 11273 | [14 empty] | 11273
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 224.01 MH | [7 empty] | 52.91 | [8 empty] | 15627 | [14 empty] | 15627
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 112.00 MH | [7 empty] | 74.56 | [8 empty] | 10914 | [14 empty] | 10914
$49,389.22 1.9911 MH/EA 448.01 MH | [30 empty] | [ 140.965 ] | [8 empty] | 37814 | [8 empty] | 11575 | [5 empty] | 49389
=====> Item Totals: 172 - ADJUST EXISTING HAND $49,389.22 1.9911 MH/EA 448.01 MH | [30 empty] | HOLE [ 140.965 ] | [6 empty] | 37814 | [10 empty] | 11575 | [5 empty] | 49389
219.508 225 EA | [37 empty] | 168.06 | [10 empty] | 51.45 | [5 empty] | 219.51
BID ITEM = 173 CLIENT# = 173 Land Item SCHEDULE: 1 100
Description = | [5 empty] | UTILITY CASTING, TYPE 230 | [24 empty] | Unit = EA Takeoff Quan: 129.000 Engr Quan: 129.000
173.01 | [5 empty] | UTILITY CASTING, TYPE 230 | [24 empty] | Quan: 129.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 64 |  | CH Prod: 64.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2CPSZ230 | [5 empty] | TYPE 230 CASTI@110.25 1.00 | [16 empty] | 129.00 EA | [7 empty] | 785.000 111,645 111,645
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 |  |  |  |  | 64.00 HR | [5 empty] | 51.051 | [15 empty] | 3267 | [11 empty] | 3267
8EX100 | [5 empty] | 100 Excavator | [11 empty] | 1 |  |  |  |  | 64.00 HR | [5 empty] | 52.3 | [15 empty] | 3347 | [11 empty] | 3347
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 |  |  |  |  | 64.00 MH | [5 empty] | 77.06 | [8 empty] | 6441 | [18 empty] | 6441
LAG | [5 empty] | General Laborer | [11 empty] | 2 |  |  |  |  | 128.00 MH | [5 empty] | 52.91 | [8 empty] | 8929 | [18 empty] | 8929
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 64.00 MH | [5 empty] | 74.56 | [8 empty] | 6237 | [18 empty] | 6237
$139,866.67 1.9844 MH/EA 256.00 MH | [28 empty] | [ 140.494 ] | [8 empty] | 21608 | [6 empty] | 111645 | [7 empty] | 6614 |  |  |  | 139867
=====> Item Totals: | [9 empty] | 173 | [7 empty] | - UTILITY CASTING, TYPE 230
139866.67 | [9 empty] | 1.9844 MH/EA | [7 empty] | 256.00 MH | [13 empty] | [ 140.494 ] | [5 empty] | 21608 | [6 empty] | 111645 | [7 empty] | 6614 |  |  |  | 139867
1,084.238 129 EA | [37 empty] | 167.5 | [6 empty] | 865.46 | [7 empty] | 51.27 |  |  |  | 1084.24
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 174 CLIENT# = 174 L UTILITY CASTING, TYPE 361 (9 1/4-INCH DE | [23 empty] | and Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 29.000 Engr Quan: 29.000
174.01 | [5 empty] | UTILITY CASTING, TYPE 361 (9 1/4-INCH DE | [23 empty] | Quan: 29.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 14.00 CH Prod: 14.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSZ361 TYPE 361 CASTI@110.25 1.00 29.00 EA 800.000 25,578 | [56 empty] | 25578
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 14.00 HR | [6 empty] | 51.051 | [18 empty] | 715 | [5 empty] | 715
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 14.00 HR | [6 empty] | 52.3 | [18 empty] | 732 | [5 empty] | 732
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 14.00 MH | [6 empty] | 77.06 | [7 empty] | 1409 | [16 empty] | 1409
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 28.00 MH | [6 empty] | 52.91 | [7 empty] | 1953 | [16 empty] | 1953
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 14.00 MH | [6 empty] | 74.56 | [7 empty] | 1364 | [16 empty] | 1364
$31,751.56 1.9310 MH/EA 56.00 MH | [29 empty] | [ 136.709 ] | [7 empty] | 4727 | [6 empty] | 25578 |  |  |  | 1447 | [5 empty] | 31752
=====> Item Totals: 174 - UTILITY CASTING, TYPE 361 (9 1/4-INCH $31,751.56 1.9310 MH/EA 56.00 MH [ 136.709 ] | [37 empty] | DE 4,727 | [6 empty] | 25578 |  |  |  | 1447 | [5 empty] | 31752
1,094.881 29 EA | [37 empty] | 162.99 | [6 empty] | 882 |  |  |  | 49.89 | [5 empty] | 1094.88
BID ITEM = 175 CLIENT# = 175 Land Item SCHEDULE: 1 100 Description = UTILITY CASTING, TYPE 230 (13-INCH DEPTH Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
175.01 UTILITY CASTING, TYPE 230 (13-INCH DEPTH Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 1.50 CH Prod: 1.5000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSZ230D TYPE 230 DEEP @110.25 1.00 3.00 EA 800.000 2,646 | [56 empty] | 2646
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 1.50 HR | [7 empty] | 51.051 | [17 empty] | 77 | [5 empty] | 77
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 1.50 HR | [7 empty] | 52.3 | [17 empty] | 78 | [5 empty] | 78
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 1.50 MH | [7 empty] | 77.06 | [8 empty] | 151 | [14 empty] | 151
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 3.00 MH | [7 empty] | 52.91 | [8 empty] | 209 | [14 empty] | 209
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 1.50 MH | [7 empty] | 74.56 | [8 empty] | 146 | [14 empty] | 146
$3,307.45 2.0000 MH/EA 6.00 MH | [30 empty] | [ 141.59 ] | [8 empty] | 506 |  |  |  |  | 2646 |  |  |  | 155 | [5 empty] | 3307
=====> Item Totals: 175 - UTILITY CASTING, TYPE 230 (13-INCH DEPTH
3307.45 | [5 empty] | 2.0000 MH/EA | [13 empty] | 6.00 MH | [10 empty] | [ 141.59 ] | [8 empty] | 506 |  |  |  |  | 2646 |  |  |  | 155 | [5 empty] | 3307
1102.483 | [5 empty] | 3 EA | [33 empty] | 168.81 |  |  |  |  | 882 |  |  |  | 51.67 | [5 empty] | 1102.48
BID ITEM = 176 CLIENT# = 176 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | PIPE LINING, 6IN | [24 empty] | Unit = LF Takeoff Quan: 22.000 Engr Quan: 22.000
| 176.01 |  |  |  |  | PIPE LINING, 6IN | [24 empty] | Quan: 22.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4LINE |  |  |  |  | PIPE LINING SUB | [13 empty] | 1 |  |  | 22.00 LF | [7 empty] | 300.000 6,600 6,600
BID ITEM = 177 CLIENT# = 177 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE LINING, 8IN | [13 empty] | Unit = | [13 empty] | LF Takeoff Quan: 84.000 Engr Quan: 84.000
177.01 | [5 empty] | PIPE LINING, 8IN | [13 empty] | Quan: | [13 empty] | 84.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LINE | [5 empty] | PIPE LINING SUB | [13 empty] | 1 |  |  | 84.00 LF | [7 empty] | 300.000 25,200 25,200
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 178 CLIENT# = 178 Land Item SCHEDULE: 1 100 Description = CONSTRUCTION STORMWATER & EROSION CONTR Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
178.01 CONSTRUCTION STORMWATER & EROSION CO Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3EROSION | [5 empty] | EROSION CONTROL MA | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 50000 | [8 empty] | 50000 | [12 empty] | 50000
3SWEEPER | [5 empty] | SWEEPER TRUCK | [13 empty] | 1 |  |  | 1,000.00 HR | [7 empty] | 225 | [8 empty] | 225000 | [12 empty] | 225000
275000 | [30 empty] | [ ] | [8 empty] | 275000 | [12 empty] | 275000
=====> Item Totals: 178 - CONSTRUCTION STORMWATER & EROSION CONTRO
275000 | [30 empty] | [ ] | [8 empty] | 275000 | [12 empty] | 275000
275000 | [5 empty] | 1 LS | [33 empty] | 275000 | [12 empty] | 275000
BID ITEM = 179 CLIENT# = 179 Land Item SCHEDULE: 1 100 Description = TREE, VEGETATION & SOIL PROTECTION PLAN Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
179.01 | [5 empty] | MAKE TREE BOXES | [24 empty] | Quan: |  |  | 150.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [13 empty] | 50 | [10 empty] | CH |  |  | Prod: | [7 empty] | 50.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
3TREEBOX | [5 empty] | TREE BOX | [13 empty] | 1 |  |  | 150.00 EA | [5 empty] | 150 | [19 empty] | 22500 |  |  |  | 22500
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 100.00 MH | [5 empty] | 52.91 | [12 empty] | 6976 | [10 empty] | 6976
$29,476.03 0.6666 MH/EA 100.00 MH | [28 empty] | [ 38.801 ] | [12 empty] | 6976 | [6 empty] | 22500 |  |  |  | 29476
179.02 | [5 empty] | INSTALL TREE BOX | [24 empty] | Quan: 400.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [13 empty] | 80 | [10 empty] | CH Prod: 80.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 160.00 MH | [28 empty] | 52.91 | [8 empty] | 11162 | [10 empty] | 11162
$11,161.65 0.4000 MH/EA 160.00 MH | [28 empty] | [ 23.28 ] | [8 empty] | 11162 | [10 empty] | 11162
179.03 | [5 empty] | REMOVE TREE BOX | [24 empty] | Quan: 400.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [13 empty] | 80 | [10 empty] | CH Prod: 80.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 160.00 MH | [28 empty] | 52.91 | [8 empty] | 11162 | [10 empty] | 11162
$11,161.65 0.4000 MH/EA 160.00 MH | [28 empty] | [ 23.28 ] | [8 empty] | 11162 | [10 empty] | 11162
=====> Item Totals: 179 - TREE, VEGETATION & SOIL PROTECTION PLAN
51799.33 | [5 empty] | 420.0000 MH/LS | [13 empty] | 420.00 MH | [8 empty] | [ 24444.42 ] | [8 empty] | 29299 | [10 empty] | 22500 |  |  |  | 51799
51799.33 | [5 empty] | 1 LS | [31 empty] | 29299.33 | [10 empty] | 22500 |  |  |  | 51799.33
BID ITEM = 180 CLIENT# = 180 Land Item SCHEDULE: 1 100 LS Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | SPILL PLAN (SP) | [23 empty] | Unit =
180.01 |  |  | SPILL PLAN | [23 empty] | Quan:
3SP |  |  | SPILL PLAN | [10 empty] | 1 |  |  | 1.00 LS | [9 empty] | 5
0 | [37 empty] | 5000 | [14 empty] | 5000
[ ] | [37 empty] | 5000 | [14 empty] | 5000
[38 empty] | 5000 | [14 empty] | 5000
=====> Item Totals: 180 - SPILL PLAN (SP) $5,000.00 5,000.000 1 LS
BID ITEM = 181 CLIENT# = 181 Land Item SCHEDULE: 1 100 Description = TEMPORARY DISCHARGE PLAN (TDP) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 181 CLIENT# = 181 Land Item SCHEDULE: 1 100
Description = TEMPORARY DISCHARGE PLAN (TDP) Unit = LS Takeoff Quan: 1.000 | [53 empty] | Engr Quan: |  |  | 1
181.01 TEMPORARY DISCHARGE PLAN (TDP) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 3TDP TEMPORARY DISCHAR 1.00 1.00 LS 5,000.000 5,000 | [53 empty] | WC: WAAVG |  |  | 5000
=====> Item Totals $5,000.00 | [8 empty] | : 181 - TEMPORARY DI | [17 empty] | SCHARGE PLAN (TDP) [ ] | [10 empty] | 5000 | [15 empty] | 5000
5000 | [8 empty] | 1 LS | [28 empty] | 5000 | [15 empty] | 5000
BID ITEM = 182 CLIENT# = 182 Land Item SCHEDULE: 1 100 Description = SEEDED LAWN INSTALATIONS Unit = SF Takeoff Quan: 5,510.000 Engr Quan: 5,510.000
4LAND Landscape sub 1.00 5,510.00 SF 1.500 8,265 8,265
BID ITEM = 183 CLIENT# = 183 Land Item SCHEDULE: 1 100 Description = TREE, DECIDUOUS, 1-1/2 IN TO 1-3/4 IN CA Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
4LAND Landscape sub 1.00 1.00 EA 750.000 750 750
BID ITEM = 184 CLIENT# = 184 Land Item SCHEDULE: 1 100 Description = TREE, DECIDUOUS, 1-3/4 IN TO 2 IN CAL Unit = EA Takeoff Quan: 85.000 Engr Quan: 85.000
4LAND Landscape sub 1.00 85.00 EA 750.000 63,750 63,750
BID ITEM = 185 CLIENT# = 185 Land Item SCHEDULE: 1 100 Description = SHRUB, DECIDUOUS, 5 GAL Unit = EA Takeoff Quan: 450.000 Engr Quan: 450.000
4LAND Landscape sub 1.00 450.00 EA 45.000 20,250 20,250
BID ITEM = 186 CLIENT# = 186 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | GROUND COVER, 4 IN POT | [24 empty] | Unit = |  |  | EA Takeoff Quan: 732.000 Engr Quan: 732.000
| 186.01 |  |  |  |  | GROUND COVER, 4 IN POT | [24 empty] | Quan: |  |  | 732.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND Landscape sub 1.00 732.00 EA 5.000 3,660 3,660
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract Total
BID ITEM = 187 CLIENT# = 187 Land Item SCHEDULE: 1 100 Description = TOPSOIL, TYPE A Unit = CY Takeoff Quan: 354.000 Engr Quan: 354.000
187.01 |  |  | TOPSOIL, TYPE A | [23 empty] | Quan: |  |  | 354.00 CY | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 354.00 CY | [12 empty] | 85 | [5 empty] | 30,090 30,090
BID ITEM = 188 CLIENT# = 188 Land Item SCHEDULE: 1 100 Description = GROUND COVER, 1 GAL Unit = EA Takeoff Quan: 1,087.000 Engr Quan: 1,087.000
188.01 |  |  | GROUND COVER, 1 GAL | [23 empty] | Quan: |  |  | 1,087.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 1,087.00 EA | [12 empty] | 18 | [5 empty] | 19,566 19,566
BID ITEM = 189 CLIENT# = 189 Land Item SCHEDULE: 1 100
Description = |  |  | GROUND COVER, 2 GAL | [23 empty] | Unit = EA Takeoff Quan: 48.000 Engr Quan: 48.000
189.01 |  |  | GROUND COVER, 2 GAL | [23 empty] | Quan: 48.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 48.00 EA | [9 empty] | 30.000 1,440 1,440
BID ITEM = 190 CLIENT# = 190 Land Item SCHEDULE: 1 100
Description = |  |  | MULCH, BARK | [23 empty] | Unit = CY Takeoff Quan: 71.000 Engr Quan: 71.000
190.01 |  |  | MULCH, BARK | [23 empty] | Quan: 71.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 71.00 CY | [9 empty] | 110.000 7,810 7,810
BID ITEM = 191 CLIENT# = 191 Land Item SCHEDULE: 1 100 Description = TREE ROOT BARRIER Unit = LF Takeoff Quan: 1,176.000 Engr Quan: 1,176.000
191.01 |  |  | TREE ROOT BARRIER | [23 empty] | Quan: |  |  | 1,176.00 LF | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 1,176.00 LF | [12 empty] | 20 | [5 empty] | 23,520 23,520
BID ITEM = 192 CLIENT# = 192 Land Item SCHEDULE: 1 100 Description = LANDSCAPE ESTABLISHMENT, MIN. BID = $40, Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
192.01 LANDSCAPE ESTABLISHMENT, MIN. BID = $40, Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND Landscape sub 1.00 1.00 LS 40,000.000 40,000 40,000
BID ITEM = 193 CLIENT# = 193 Land Item SCHEDULE: 1 100 Description = FLEXIBLE POROUS SURFACE TREATMENT Unit = SF Takeoff Quan: 16,859.000 Engr Quan: 16,859.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 193 CLIENT# = 193 Land Item SCHEDULE: 1 100 Description = FLEXIBLE POROUS SURFACE TREATMENT Unit = SF Takeoff Quan: 16,859.000 Engr Quan: 16,859.000
193.01 FLEXIBLE POROUS SURFACE TREATMENT Quan: 16,859.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 400.00 CH Prod: 400.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2FLEXIPAVE | [5 empty] | FLEXI PAVE MAT@110.2 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 113461 | [13 empty] | 125091 | [7 empty] | 125091
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 2,000.00 MH | [7 empty] | 64.98 | [8 empty] | 170395 | [12 empty] | 170395
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 400.00 MH | [7 empty] | 68.98 | [8 empty] | 36125 | [12 empty] | 36125
$331,611.03 0.1423 MH/SF | [22 empty] | 2,400.00 MH | [7 empty] | [ 10.28 ] | [8 empty] | 206520 |  |  |  |  | 125091 | [7 empty] | 331611
=====> Item Totals: 193 - FLEXIBLE POROUS SURFACE TREATMENT
$331,611.03 0.1423 MH/SF 2,400.00 MH | [30 empty] | [ 10.28 ] 206,520 | [13 empty] | 125091 | [7 empty] | 331611
19.670 16859 SF | [30 empty] | 12.25 | [13 empty] | 7.42 | [7 empty] | 19.67
BID ITEM = 194 CLIENT# = 194 Land Item SCHEDULE: 1 100 Description = PEDESTRIAN ENHANCEMENTS ON MADISON ST I- Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
194.01 | [5 empty] | 1-5 PLANTERS | [24 empty] | Quan: |  |  | 50.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 8.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2PLANTERS | [5 empty] | PLANTERS@110.25% 1.00 | [16 empty] | 50.00 EA | [5 empty] | 2,730.980 150,545 150,545
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 8.00 HR | [5 empty] | 51.051 | [15 empty] | 408 | [11 empty] | 408
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 8.00 HR | [5 empty] | 52.3 | [15 empty] | 418 | [11 empty] | 418
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [14 empty] | 780
$154,073.02 0.6400 MH/EA 32.00 MH | [28 empty] | [ 45.31 ] | [12 empty] | 2701 |  |  | 150545 | [7 empty] | 827 |  |  |  | 154073
194.02 | [5 empty] | 1-5 DECRITIVE PANELS | [24 empty] | Quan: |  |  | 550.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ | [5 empty] | SITE FURNISHINGS CREW 32.00 | [24 empty] | CH |  |  | Prod: 32.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
60953 | [56 empty] | 60953
2DECPANELS DECRATIVE PANE@110. 1.00 550.00 LF 100.520
LAG General Laborer 2.00 | [22 empty] | 64.00 MH | [7 empty] | 52.91 | [8 empty] | 4465 | [12 empty] | 4465
$65,417.48 0.1163 MH/LF | [22 empty] | 64.00 MH | [7 empty] | [ 6.772 ] | [8 empty] | 4,465 60,953 | [12 empty] | 65417
194.03 4LAND | [5 empty] | I-5 LANDSCAPING Landscape sub | [13 empty] | 1 |  |  | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG 1.00 LS 30,000.000 30,000 30,000
=====> Item Totals: 194 - PEDESTRIAN ENHANCEMENTS ON MADISON ST I- $249,490.50 96.0000 MH/LS 96.00 MH [ 5990.34 ] 7,166 211,498 827 30,000 249,491 249,490.500 1 LS 7,165.61 211,498.09 826.80 30,000.00 249,490.50
BID ITEM = 195 CLIENT# = 195 Land Item SCHEDULE: 1 100 Description = ROOT PRUNING AND TRIM VEGETATION Unit = FA Takeoff Quan: 50,000.000 Engr Quan: 50,000.000
195.01 ROOT PRUNING AND TRIM VEGETATION Quan: 50,000.00 FA Hrs/Shft: | [44 empty] | 10.00 Cal: 510 | [6 empty] | WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 50,000.00 FA 0.890 | [44 empty] | 44500 | [9 empty] | 44500
=====> Item Totals: 195 - ROOT PRUNING AND TRIM VEGETATION $44,500.00 [ ] | [44 empty] | 44500 | [9 empty] | 44500
0.890 50000 FA | [44 empty] | 0.89 | [9 empty] | 0.89
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 196 CLIENT# = 196 Land Item SCHEDULE: 1 100 Description = REPAIR IRRIGATION SYSTEM Unit = FA Takeoff Quan: 50,000.000 Engr Quan: 50,000.000
196.01 REPAIR IRRIGATION SYSTEM Quan: 50,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 50,000.00 FA 0.890 44,500 44,500
=====> Item Totals: 196 - REPAIR IRRIGATION SYSTEM
44500 | [30 empty] | [ ] | [8 empty] | 44500 | [12 empty] | 44500
0.89 | [5 empty] | 50000 FA | [33 empty] | 0.89 | [12 empty] | 0.89
BID ITEM = 197 CLIENT# = 197 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CURB, CEM CONC W/ 25% POZZOLANS | [23 empty] | Unit = |  |  |  | LF Takeoff Quan: 14,654.000 Engr Quan: 14,654.000
197.01 | [5 empty] | CURB, CEM CONC W/ 25% POZZOLANS | [23 empty] | Quan: |  |  |  | 14,654.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
COM Concrete 6 Man Crew 669.17 CH Prod: 669.1795 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR025 2500LB READY M@110.2 1.02 138.61 CY | [29 empty] | 115.35 | [7 empty] | 17628 | [14 empty] | 17628
2CRUBHOOP CURB HOOPS@110.25% 1.00 4,885.01 EA | [29 empty] | 2 | [7 empty] | 10771 | [14 empty] | 10771
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 3,345.90 MH | [6 empty] | 64.98 | [7 empty] | 301923 | [14 empty] | 301923
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 669.18 MH | [6 empty] | 68.98 | [7 empty] | 64016 | [14 empty] | 64016
394337.97 | [5 empty] | 0.2739 MH/LF | [16 empty] | 4,015.08 MH | [6 empty] | [ 20.985 ] | [7 empty] | 365939 | [6 empty] | 28399 | [7 empty] | 394338
=====> Item Totals: 197 - CURB, CEM CONC W/ $394,337.97 0.2739 MH/LF 4,015.08 MH | [29 empty] | 25% POZZOLANS [ 20.985 ] | [7 empty] | 365939 | [6 empty] | 28399 | [7 empty] | 394338
26.910 14654 LF | [37 empty] | 24.97 | [6 empty] | 1.94 | [7 empty] | 26.91
BID ITEM = 198 CLIENT# = 198 Land Item SCHEDULE: 1 100 Description = CURB AND GUTTER, CEM CONC W/ 25% POZZOL Unit = LF Takeoff Quan: 522.000 Engr Quan: 522.000
198.01 CURB AND GUTTER, CEM CONC W/ 25% POZZO Quan: 522.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 117.800
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 40 |  | CH
2CR030 | [5 empty] | 3000LB READY M@110.2 1.02 | [16 empty] | 43.86 CY
40.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
5696 | [56 empty] | 5696
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 200.00 MH | [7 empty] | 64.98 | [8 empty] | 17039 | [12 empty] | 17039
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 40.00 MH | [7 empty] | 68.98 | [8 empty] | 3613 | [12 empty] | 3613
26348.32 | [5 empty] | 0.4597 MH/LF | [16 empty] | 240.00 MH | [7 empty] | [ 33.201 ] | [8 empty] | 20652 |  |  |  |  | 5696 | [7 empty] | 26348
=====> Item Totals: 198 - CURB AND GUTTER, CEM CONC W/ 25% POZZOL
$26,348.32 0.4597 MH/LF 240.00 MH | [30 empty] | [ 33.201 ] | [8 empty] | 20652 |  |  |  |  | 5696 | [7 empty] | 26348
50.476 522 LF | [39 empty] | 39.56 |  |  |  |  | 10.91 | [7 empty] | 50.48
BID ITEM = 199 CLIENT# = 199 Land Item SCHEDULE: 1 100
Description = |  |  | CURB, TRAFFIC, PRECAST | [23 empty] | Unit = |  |  | LF Takeoff Quan: 64.000 Engr Quan: 64.000
199.01 |  |  | CURB, TRAFFIC, PRECAST | [23 empty] | Quan: |  |  | 64.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 64.00 LF 60.000 3,840 3,840
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 200 CLIENT# = 200 Land Item SCHEDULE: 1 100 Description = LANE MARKER, TYPE 2 Unit = EA Takeoff Quan: 685.000 Engr Quan: 685.000
| 200.01 |  |  |  |  | LANE MARKER, TYPE 2 | [24 empty] | Quan: |  |  | 685.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4STRI |  |  |  |  | Striping sub | [13 empty] | 1 |  |  | 685.00 EA | [10 empty] | 5.5 | [7 empty] | 3,768 3,768
BID ITEM = 201 CLIENT# = 201 Land Item SCHEDULE: 1 100 Description = FLEXIBLE DELINEATOR POST, 28" Unit = EA Takeoff Quan: 110.000 Engr Quan: 110.000
4STRI Striping sub 1.00 110.00 EA 145.000 15,950 15,950
BID ITEM = 202 CLIENT# = 202 Land Item SCHEDULE: 1 100
Description = | [5 empty] | FLEXIBLE DELINEATOR POST, 48" | [24 empty] | Unit = EA Takeoff Quan: 66.000 Engr Quan: 66.000
202.01 | [5 empty] | FLEXIBLE DELINEATOR POST, 48" | [24 empty] | Quan: 66.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 66.00 EA | [7 empty] | 175 | [21 empty] | 11550 |  |  |  | 11550
BID ITEM = 203 CLIENT# = 203 Land Item SCHEDULE: 1 100
Description = | [5 empty] | FLEXIBLE DELINEATOR POST, 66" | [19 empty] | Unit = EA Takeoff Quan: 9.000 Engr Quan: 9.000
203.01 | [5 empty] | FLEXIBLE DELINEATOR POST, 66" | [19 empty] | Quan: 9.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 | [5 empty] | 9.00 EA |  |  |  |  | 200 | [21 empty] | 1800 |  |  |  | 1800
BID ITEM = 204 CLIENT# = 204 Land Item SCHEDULE: 1 100 Description = PLASTIC CURB WITH POST Unit = EA Takeoff Quan: 141.000 Engr Quan: 141.000
4STRI Striping sub 1.00 141.00 EA 350.000 49,350 49,350
BID ITEM = 205 CLIENT# = 205 Land Item SCHEDULE: 1 100 Description = RESET MONUMENT AND MONUMENT FRAME AND Unit = EA Takeoff Quan: 43.000 Engr Quan: 43.000
205.01 RESET MONUMENT AND MONUMENT FRAME A Quan: 43.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 21 | [10 empty] | CH | Prod: | [8 empty] | 21.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
4SURV | [5 empty] | Surveying sub | [13 empty] | 1 |  |  | 43.00 EA | [5 empty] | 1500 | [25 empty] | 64500 |  | 64500
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 21.00 HR | [5 empty] | 51.051 | [19 empty] | 1072 | [7 empty] | 1072
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 21.00 HR | [5 empty] | 52.3 | [19 empty] | 1098 | [7 empty] | 1098
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 21.00 MH | [5 empty] | 77.06 | [11 empty] | 2114 | [15 empty] | 2114
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 42.00 MH | [5 empty] | 52.91 | [11 empty] | 2930 | [15 empty] | 2930
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 21.00 MH | [5 empty] | 74.56 | [11 empty] | 2046 | [15 empty] | 2046
$73,760.33 1.9534 MH/EA 84.00 MH | [28 empty] | [ 138.299 ] | [11 empty] | 7090 | [7 empty] | 2170 | [5 empty] | 64500 |  | 73760
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 205 CLIENT# = 205 Land Item SCHEDULE: 1 100 Description = RESET MONUMENT AND MONUMENT FRAME AND Unit = EA Takeoff Quan: 43.000 Engr Quan: 43.000 =====> Item Totals: 205 - RESET MONUMENT AND MONUMENT FRAME AND CO $73,760.33 1.9534 MH/EA 1,715.357 43 EA
84.00 MH | [30 empty] | [ 138.299 ] | [8 empty] | 7090 | [12 empty] | 2,170 64,500 |  |  |  | 73760
[40 empty] | 164.88 | [12 empty] | 50.47 1,500.00 |  |  |  | 1715.36
BID ITEM | [5 empty] | = |  | 206 | [5 empty] | CLIENT# = | [8 empty] | 206 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | CURB RAMP | [7 empty] | Unit = | [19 empty] | SY Takeoff Quan: 2,085.000 Engr Quan: 2,085.000
206.01 | [5 empty] | CURB RAMP | [7 empty] | Quan: | [19 empty] | 286.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
COM Concrete 6 Man Crew 725.00 CH Prod: 725.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR025 2500LB READY M@110.2 1.00 349.00 CY | [30 empty] | 145.35 | [13 empty] | 55927 | [7 empty] | 55927
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 3,625.00 MH | [7 empty] | 64.98 | [6 empty] | 418392 | [6 empty] | 418392
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 725.00 MH | [7 empty] | 68.98 | [6 empty] | 88736 | [6 empty] | 88736
$563,054.33 15.2097 MH/EA 4,350.00 MH [ 1497.708 ] | [37 empty] | 507128 | [6 empty] | 55927 | [7 empty] | 563054
=====> Item Totals: 206 - CURB RAMP $563,054.33 2.0863 MH/SY 4,350.00 MH [ 205.441 ] | [37 empty] | 507128 | [6 empty] | 55927 | [7 empty] | 563054
270.050 2085 SY | [37 empty] | 243.23 | [6 empty] | 26.82 | [7 empty] | 270.05
BID ITEM = 207 CLIENT# = 207 Land Item SCHEDULE: 1 100 Description = DETECTABLE WARNING PLATE RETROFIT Unit = SF Takeoff Quan: 13.000 Engr Quan: 13.000
COM Concrete 6 Man Crew 4.00 CH Prod: 2TRUNK TRUNKATED DOME@11 1.00 13.00 SF 13.850
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
199 | [56 empty] | 199
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [8 empty] | 2308 |  |  |  |  | 2308
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [8 empty] | 490 |  |  |  |  | 490
$2,996.46 1.8461 MH/SF 24.00 MH [ 181.791 ] 2,798 | [44 empty] | 199 | [7 empty] | 2996
=====> Item Totals: 207 - DETECTABLE WARNING PLATE RETROFIT $2,996.46 1.8461 MH/SF 230.497 13 SF
24.00 MH | [30 empty] | [ 181.791 ] | [8 empty] | 2798 |  |  |  |  | 199 | [7 empty] | 2996
[40 empty] | 215.23 |  |  |  |  | 15.27 | [7 empty] | 230.5
BID ITEM = 208 CLIENT# = 208 Land Item SCHEDULE: 1 100 Description = DETECTABLE WARNING PLATE Unit = SF Takeoff Quan: 2,794.000 Engr Quan: 2,794.000
208.01 | [5 empty] | DETECTABLE WARNING PLATE | [23 empty] | Quan: |  |  |  | 2,794.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2TRUNK | [5 empty] | TRUNKATED DOME@11 1.00 2,794.00 SF | [27 empty] | 13.850 42,663 42,663
=====> Item Totals: 208 - DETECTABLE WARNI $42,663.33 | [29 empty] | NG PLATE [ ] | [7 empty] | 42663 | [14 empty] | 42663
15.27 | [5 empty] | 2794 SF | [31 empty] | 15.27 | [14 empty] | 15.27
BID ITEM = 209 CLIENT# = 209 Land Item SCHEDULE: 1 100 Description = SIDEWALK, CEM CONC W/ 25% POZZOLANS Unit = SY Takeoff Quan: 17,608.000 Engr Quan: 17,608.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 209 CLIENT# = 209 Land Item SCHEDULE: 1 100 Description = SIDEWALK, CEM CONC W/ 25% POZZOLANS Unit = SY Takeoff Quan: 17,608.000 Engr Quan: 17,608.000
209.01 SIDEWALK, CEM CONC W/ 25% POZZOLANS Quan: 17,608.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [16 empty] | 1866.51 | [7 empty] | CH |  |  | Prod: 1,866.5197 CH | [14 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2CR025 | [5 empty] | 2500LB READY M@110.2 1.02 | [16 empty] | 1,975.44 CY | [10 empty] | 115.350 251,223 | [22 empty] | 251223
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 9,332.60 MH | [7 empty] | 64.98 | [8 empty] | 842144 | [8 empty] | 842144
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 1,866.52 MH | [7 empty] | 68.98 | [8 empty] | 178557 | [8 empty] | 178557
$1,271,924.09 0.6360 MH/SY 11,199.12 MH [ 48.713 ] 1,020,701 251,223 1,271,924
=====> Item Totals: 209 - SIDEWALK, CEM CONC W/ 25% POZZOLANS $1,271,924.09 0.6360 MH/SY 72.236 17608 SY
11,199.12 MH | [30 empty] | [ 48.713 ] 1,020,701 | [13 empty] | 251223 | [7 empty] | 1271924
[31 empty] | 57.97 | [13 empty] | 14.27 | [7 empty] | 72.24
BID ITEM = 210 CLIENT# = 210 Land Item SCHEDULE: 1 100 Description = SIDEWALK, THICKENED EDGE W/ 25% POZZOLAN Unit = LF Takeoff Quan: 18,647.000 Engr Quan: 18,647.000
210.01 SIDEWALK, THICKENED EDGE W/ 25% POZZOL Quan: 18,647.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2CR025 2500LB READY M@110.2 1.50 1,294.39 CY 115.350
164612 | [8 empty] | 164612
POZZOLAN 164,612 | [8 empty] | 164612
8.83 | [8 empty] | 8.83
=====> Item Totals: 210 - SIDEWALK, THICKENED EDGE W/ 25% $164,611.94 [ ] 8.828 18647 LF
BID ITEM = 211 CLIENT# = 211 Land Item SCHEDULE: 1 100 Description = STREET NAME LETTER INLAY Unit = EA Takeoff Quan: 434.000 Engr Quan: 434.000
211.01 | [7 empty] | STREET NAME LETTER INLAY | [22 empty] | Quan: |  |  | 434.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [7 empty] | Concrete 6 Man Crew | [15 empty] | 20 | [6 empty] | CH |  |  | Prod: | [7 empty] | 20.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2BRONZEINLEY BRONZE INLEYS@110.2 | [19 empty] | 1 |  |  |  | 434.00 EA 65.000 | [17 empty] | 31,102 31,102
3SANDBLAST | [7 empty] | SANDBLAST FINISH | [11 empty] | 1 |  |  |  | 1.00 LS 5,000.000 | [20 empty] | 5000 | [7 empty] | 5000
CEJ | [7 empty] | Cement Mason | [11 empty] | 5 |  |  |  | 100.00 MH 64.980 | [17 empty] | 8520 | [10 empty] | 8520
FOCO | [7 empty] | Concrete Forman | [11 empty] | 1 |  |  |  | 20.00 MH 68.980 | [17 empty] | 1806 | [10 empty] | 1806
$46,427.55 0.2764 MH/EA 120.00 MH | [23 empty] | [ 19.966 ] | [13 empty] | 10326 | [6 empty] | 31102 |  |  |  | 5000 |  |  |  | 46428
=====> Item Totals: $46,427.55 | [9 empty] | 211 0.2764 MH/EA | [6 empty] | - STREET NAME LETTER INLAY 120.00 MH | [16 empty] | [ 19.966 ] |  |  |  | 10326 | [6 empty] | 31102 |  |  |  | 5000 |  |  |  | 46428
106.976 434 EA | [37 empty] | 23.79 | [6 empty] | 71.66 |  |  |  | 11.52 |  |  |  | 106.98
BID ITEM = 212 CLIENT# = 212 Land Item SCHEDULE: 1 100 Description = I-5 SPRING STREET CURB RAMP Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
212.01 | [5 empty] | REMOVE 1-5 SPRING CURB RAMP | [24 empty] | Quan: |  |  | 1.00 LS | [7 empty] | Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [12 empty] | 8 | [11 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
4SAWC | [5 empty] | Sawcutting | [12 empty] | 1.00 1.00 LS | [9 empty] | 0.58 | [25 empty] | 1 |  | 1
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1.00 8.00 HR | [9 empty] | 51.051 | [23 empty] | 408 |  |  |  | 408
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1.00 8.00 HR | [9 empty] | 52.3 | [23 empty] | 418 |  |  |  | 418
FOCI | [5 empty] | Civil Forman | [12 empty] | 1.00 8.00 MH | [9 empty] | 77.06 | [12 empty] | 1092 | [14 empty] | 1092
LAG | [5 empty] | General Laborer | [12 empty] | 2.00 16.00 MH | [9 empty] | 52.91 | [12 empty] | 1510 | [14 empty] | 1510
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 212 CLIENT# = 212 Land Item SCHEDULE: 1 100 Description = I-5 SPRING STREET CURB RAMP Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 OPE Operator - Excavator $4,486.16 32.0000 MH/LS
1 | [22 empty] | 8.00 MH | [7 empty] | 74.56 | [8 empty] | 1057 | [16 empty] | 1057
[23 empty] | 32.00 MH | [7 empty] | [ 3089.28 ] | [8 empty] | 3659 | [12 empty] | 827 |  | 1 |  | 4486
212.02 I-5 SPRING STREET CURB RAMP Quan: 1.00 LS Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
COM Concrete 6 Man Crew 8.00 CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR025 2500LB READY M@110.2 1.00 10.00 CY | [30 empty] | 115.35 | [6 empty] | 1272 | [14 empty] | 1272
2TRUNK TRUNKATED DOME@11 1.00 8.00 SF | [30 empty] | 13.85 | [6 empty] | 122 | [14 empty] | 122
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [6 empty] | 4617 | [6 empty] | 4617
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [6 empty] | 979 | [6 empty] | 979
$6,989.78 48.0000 MH/LS 48.00 MH [ 4726.56 ] 5,596 | [44 empty] | 1394 | [11 empty] | 6990
=====> Item Totals: 212 - I-5 SPRING STREET CURB RAMP
11475.94 | [5 empty] | 80.0000 MH/LS | [13 empty] | 80.00 MH | [10 empty] | [ 7815.84 ] 9,255 1,394 827 1 11,476
11475.94 | [5 empty] | 1 LS | [24 empty] | 9,254.67 1,393.89 826.80 0.58 11,475.94
BID ITEM = 213 CLIENT# = 213 Land Item SCHEDULE: 1 100 Takeoff Quan: 57.000 Engr Quan: 57.000
Description = |  |  | BRICK PAVING | [23 empty] | Unit = SY
213.01 |  |  | BRICK PAVING | [23 empty] | Quan: 57.0
COM 2BRICK |  |  | Concrete 6 Man Crew BRICK PAVING M@110.2 1.00 | [13 empty] | 1.00 LS | [7 empty] | 24 |  | CH Pr 500.000
od:
24.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
551 | [56 empty] | 551
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 120.00 MH | [7 empty] | 64.98 | [6 empty] | 10224 | [6 empty] | 10224
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 68.98 | [6 empty] | 2168 | [6 empty] | 2168
$12,942.47 2.5263 MH/SY 144.00 MH [ 182.429 ] | [37 empty] | 12391 | [6 empty] | 551 | [7 empty] | 12942
=====> Item Totals: 213 - BRICK PAVING $12,942.47 2.5263 MH/SY 144.00 MH [ 182.429 ] | [37 empty] | 12391 | [6 empty] | 551 | [7 empty] | 12942
227.061 57 SY | [37 empty] | 217.39 | [6 empty] | 9.67 | [7 empty] | 227.06
BID ITEM | [5 empty] | = |  | 214 | [5 empty] | CLIENT# = | [8 empty] | 214 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | DRIVEWAY, CEM CONC, HES (24 HRS), 8 IN | [22 empty] | Unit = |  |  |  |  | SY Takeoff Quan: 1,692.000 Engr Quan: 1,692.000
214.01 | [5 empty] | DRIVEWAY, CEM CONC, HES (24 HRS), 8 IN | [22 empty] | Quan: |  |  |  |  | 1,692.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 314.00 CH Prod: 314.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CRP1D | [5 empty] | 1 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 431.46 CY | [7 empty] | 187.15 | [13 empty] | 89024 | [7 empty] | 89024
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 1,570.00 MH | [7 empty] | 64.98 | [8 empty] | 133760 | [12 empty] | 133760
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 314.00 MH | [7 empty] | 68.98 | [8 empty] | 28358 | [12 empty] | 28358
$251,142.80 1.1134 MH/SY | [22 empty] | 1,884.00 MH | [7 empty] | [ 80.406 ] | [8 empty] | 162118 |  |  |  |  | 89024 | [7 empty] | 251143
=====> Item Totals: 214 - DRIVEWAY, CEM CONC, HES (24 HRS), 8 IN
$251,142.80 1.1134 MH/SY 1,884.00 MH | [30 empty] | [ 80.406 ] 162,118 | [13 empty] | 89024 | [7 empty] | 251143
148.430 1692 SY | [30 empty] | 95.81 | [13 empty] | 52.61 | [7 empty] | 148.43
BID ITEM = 215 CLIENT# = 215 Land Item SCHEDULE: 1 100
Description = |  |  | SIGN, TRAFFIC, MAST ARM MOUNTED | [23 empty] | Unit = |  |  | EA Takeoff Quan: 69.000 Engr Quan: 69.000
215.01 |  |  | SIGN, TRAFFIC, MAST ARM MOUNTED | [23 empty] | Quan: |  |  | 69.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 215 CLIENT# = 215 Land Item SCHEDULE: 1 100 Description = SIGN, TRAFFIC, MAST ARM MOUNTED Unit = EA Takeoff Quan: 69.000 Engr Quan: 69.000
2SIGNTMAST | [5 empty] | TRAFFIC SIGN M@110.2 | [13 empty] | 1 |  |  | 69.00 EA | [7 empty] | 110 | [6 empty] | 8368 | [18 empty] | 8368
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 69.00 EA | [7 empty] | 340 | [21 empty] | 23460 |  |  |  | 23460
31827.98 | [30 empty] | [ ] | [6 empty] | 8368 | [14 empty] | 23460 |  |  |  | 31828
=====> Item Totals: | [10 empty] | 215 | [5 empty] | - SIGN, TRAFFIC, MAST ARM MOUNTED
31827.98 | [16 empty] | [ ] | [20 empty] | 8368 | [14 empty] | 23460 |  |  |  | 31828
461.275 | [13 empty] | 69 EA | [23 empty] | 121.28 | [14 empty] | 340 |  |  |  | 461.28
BID ITEM = 216 CLIENT# = 216 Land Item SCHEDULE: 1 100 Description = SIGN, TRAFFIC, POLE MOUNTED Unit = EA Takeoff Quan: 61.000 Engr Quan: 61.000
216.01 SIGN, TRAFFIC, POLE MOUNTED | [30 empty] | Quan: |  |  | 61.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [18 empty] | 30 | [11 empty] | CH |  |  | Prod: | [7 empty] | 30.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
2SIGNPM | [5 empty] | SIGN TRAFFIC P@110.25 | [12 empty] | 1.00 61.00 EA | [9 empty] | 110.000 7,398 7,398
LAG | [5 empty] | General Laborer | [12 empty] | 1.00 30.00 MH | [9 empty] | 52.910 2,093 2,093
$9,490.59 0.4918 MH/EA 30.00 MH [ 28.623 ] 2,093 7,398 9,491
=====> Item Totals: 216 - SIGN, TRAFFIC, POLE MOUNTED $9,490.59 0.4918 MH/EA 155.583 61 EA
30.00 MH | [30 empty] | [ 28.623 ] | [8 empty] | 2093 |  |  |  |  | 7398 | [7 empty] | 9491
[40 empty] | 34.31 |  |  |  |  | 121.28 | [7 empty] | 155.58
BID ITEM = 217 CLIENT# = 217 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SIGN, TRAFFIC, SPAN WIRE MOUNTED | [24 empty] | Unit = EA Takeoff Quan: 13.000 Engr Quan: 13.000
217.01 | [5 empty] | SIGN, TRAFFIC, SPAN WIRE MOUNTED | [24 empty] | Quan: 13.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2SIGNTSP | [5 empty] | TRAFFIC SIGN S@110.25 | [13 empty] | 1 |  |  | 13.00 EA | [7 empty] | 100 | [6 empty] | 1433 | [18 empty] | 1433
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 13.00 EA | [7 empty] | 340 | [21 empty] | 4420 |  |  |  | 4420
5853.25 | [30 empty] | [ ] | [6 empty] | 1433 | [14 empty] | 4420 |  |  |  | 5853
=====> Item Totals: | [10 empty] | 217 | [5 empty] | - SIGN, TRAFFIC, SPAN WIRE MOUNTED
5853.25 | [16 empty] | [ ] | [20 empty] | 1433 | [14 empty] | 4420 |  |  |  | 5853
450.25 | [13 empty] | 13 EA | [23 empty] | 110.25 | [14 empty] | 340 |  |  |  | 450.25
BID ITEM = 218 CLIENT# = 218 Land Item SCHEDULE: 1 100 Description = SIGN, TRAFFIC, POST MOUNTED Unit = EA Takeoff Quan: 446.000 Engr Quan: 446.000
ZZZ SIGN CREW 223.00 CH 2SIGNTRAFFIC TRAFFIC SIGN@110.25% 1.00 446.00 EA LAG General Laborer 1.00 223.00 MH $49,976.59 0.5000 MH/EA 223.00 MH
Prod: 223.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 1 |  | Eqp Pcs: |  | 0
70.000 34,420 | [56 empty] | 34420
52.910 15,557 | [56 empty] | 15557
[ 29.1 ] | [37 empty] | 15557 | [6 empty] | 34420 |  |  |  | 49977
[ 29.1 ] | [37 empty] | 15557 | [6 empty] | 34420 |  |  |  | 49977
[38 empty] | 34.88 | [6 empty] | 77.18 |  |  |  | 112.06
=====> Item Totals: 218 - SIGN, TRAFFIC, POST MOUNTED $49,976.59 0.5000 MH/EA 223.00 MH 112.055 446 EA
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 219 CLIENT# = 219 Land Item SCHEDULE: 1 100 Description = SIGN, STREET DESIGNATION, SPAN WIRE MOUN Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
219.01 SIGN, STREET DESIGNATION, SPAN WIRE MOU Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2SIGNSDSP SIGN STEET DES@110.25 1.00 2.00 EA | [30 empty] | 200 | [8 empty] | 441 | [16 empty] | 441
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 2.00 EA | [7 empty] | 340 | [21 empty] | 680 |  |  |  | 680
1121 | [30 empty] | [ ] | [8 empty] | 441 | [12 empty] | 680 |  |  |  | 1121
=====> Item Totals: 219 - SIGN, STREET DESIGNATION, SPAN WIRE MOUN
1121 | [30 empty] | [ ] | [8 empty] | 441 | [12 empty] | 680 |  |  |  | 1121
560.5 | [5 empty] | 2 EA | [33 empty] | 220.5 | [12 empty] | 340 |  |  |  | 560.5
BID ITEM = 220 CLIENT# = 220 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SIGN, STREET DESIGNATION, MAST ARM MOUNT | [24 empty] | Unit = EA Takeoff Quan: 52.000 Engr Quan: 52.000
220.01 | [5 empty] | SIGN, STREET DESIGNATION, MAST ARM MOU | [24 empty] | Quan: 52.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2SIGNSDMAS | [5 empty] | SIGN STREET DE@110.2 | [13 empty] | 1 |  |  | 52.00 EA | [7 empty] | 200 | [8 empty] | 11466 | [16 empty] | 11466
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 52.00 EA | [7 empty] | 340 | [21 empty] | 17680 |  |  |  | 17680
29146 | [30 empty] | [ ] | [8 empty] | 11466 | [12 empty] | 17680 |  |  |  | 29146
=====> Item Totals: 220 - SIGN, STREET DESIGNATION, MAST ARM MOUNT
29146 | [19 empty] | [ ] | [19 empty] | 11466 | [12 empty] | 17680 |  |  |  | 29146
560.5 | [5 empty] | 52 EA | [33 empty] | 220.5 | [12 empty] | 340 |  |  |  | 560.5
BID ITEM = 221 CLIENT# = 221 Land Item SCHEDULE: 1 100 Description = SIGN, STREET DESIGNATION, POLE MOUNTED Unit = EA Takeoff Quan: 46.000 Engr Quan: 46.000
221.01 SIGN, STREET DESIGNATION, POLE MOUNTED Quan: 46.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW 23.00 CH Prod:
23.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 1 |  | Eqp Pcs: |  | 0
10143 | [56 empty] | 10143
2SIGNSDPM | [5 empty] | SIGN STREET DE@110.2 | [13 empty] | 1 |  |  | 46.00 EA | [7 empty] | 200
LAG | [5 empty] | General Laborer | [13 empty] | 1 |  |  | 23.00 MH | [7 empty] | 52.91
$11,747.48 0.5000 MH/EA 23.00 MH | [30 empty] | [ 29.1 ]
1604 | [52 empty] | 1604
1604 | [44 empty] | 10143 | [7 empty] | 11747
=====> Item Totals: 221 - SIGN, STR $11,747.48 0.5000 MH/EA 255.380 46 EA
EET DESIGNATI 23.00 MH | [30 empty] | ON, POLE MO [ 29.1 ] | [6 empty] | UNTED 1,604 | [6 empty] | 10143 | [7 empty] | 11747
[38 empty] | 34.88 | [6 empty] | 220.5 | [7 empty] | 255.38
BID ITEM = 222 CLIENT# = 222 Land Item SCHEDULE: 1 100 Description = SIGN, STREET NAME, OWNER FURNISHED, STEE Unit = EA Takeoff Quan: 49.000 Engr Quan: 49.000
222.01 SIGN, STREET NAME, OWNER FURNISHED, STE Quan: 49.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 49.00 EA 200.000 9,800 9,800
BID ITEM = 223 CLIENT# = 223 Land Item SCHEDULE: 1 100 Description = SIGN, BUS ZONE, OWNER FURNISHED Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 223 CLIENT# = 223 Land Item SCHEDULE: 1 100 Description = SIGN, BUS ZONE, OWNER FURNISHED Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
223.01 SIGN, BUS ZONE, OWNER FURNISHED | [30 empty] | Quan: |  |  | 8.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [21 empty] | 4 | [8 empty] | CH |  |  | Prod: | [7 empty] | 4.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 4.00 MH | [21 empty] | 52.91 | [19 empty] | 279 | [10 empty] | 279
$279.04 0.5000 MH/EA 4.00 MH | [21 empty] | [ 29.1 ] | [19 empty] | 279 | [10 empty] | 279
=====> Item Totals: 223 - SIGN, BUS ZONE, OWNER FURNISHED
279.04 | [5 empty] | 0.5000 MH/EA | [15 empty] | 4.00 MH [ 29.1 ] | [19 empty] | 279 | [10 empty] | 279
34.88 | [5 empty] | 8 EA | [35 empty] | 34.88 | [10 empty] | 34.88
BID ITEM = 224 CLIENT# = 224 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SIGN, TRAFFIC, SIGNAL HEAD MOUNTED | [24 empty] | Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
224.01 | [5 empty] | SIGN, TRAFFIC, SIGNAL HEAD MOUNTED | [24 empty] | Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 8.00 EA | [7 empty] | 150 | [21 empty] | 1200 |  |  |  | 1200
BID ITEM = 225 CLIENT# = 225 Land Item SCHEDULE: 1 100 Description = POST, TRAFFIC SIGN Unit = EA Takeoff Quan: 223.000 Engr Quan: 223.000
ZZZ SIGN CREW 111.50 CH 2SIGNPOST SIGN POST TRAF@110.2 1.00 223.00 EA LAG General Laborer 1.00 111.50 MH $37,281.18 0.5000 MH/EA 111.50 MH
Prod: 111.5000 CH | [48 empty] | Lab Pcs: |  |  |  | 1 |  | Eqp Pcs: |  | 0
120.000 29,503 | [56 empty] | 29503
52.910 7,778 | [56 empty] | 7778
[ 29.1 ] | [37 empty] | 7778 | [6 empty] | 29503 |  |  |  | 37281
[ 29.1 ] | [37 empty] | 7778 | [6 empty] | 29503 |  |  |  | 37281
[38 empty] | 34.88 | [6 empty] | 132.3 |  |  |  | 167.18
=====> Item Totals: 225 - POST, TRAFFIC SIGN $37,281.18 0.5000 MH/EA 111.50 MH 167.180 223 EA
BID ITEM = 226 CLIENT# = 226 Land Item SCHEDULE: 1 100 Description = POST, STREET NAME Unit = EA Takeoff Quan: 23.000 Engr Quan: 23.000
226.01 POST, STREET NAME | [30 empty] | Quan: |  |  | 23.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [7 empty] | 12.5 | [22 empty] | CH |  |  | Prod: | [7 empty] | 12.5000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
2SIGNPOSTSN | [7 empty] | SIGN POST STRE@110.2 1.00 | [14 empty] | 23.00 EA | [5 empty] | 200.000 5,072 5,072
LAG | [7 empty] | General Laborer 1.00 | [14 empty] | 12.50 MH | [5 empty] | 52.910 872 872
$5,943.51 0.5434 MH/EA 12.50 MH
[ 31.631 ] | [37 empty] | 872 | [6 empty] | 5072 | [7 empty] | 5944
[ 31.631 ] | [37 empty] | 872 | [6 empty] | 5072 | [7 empty] | 5944
[38 empty] | 37.91 | [6 empty] | 220.5 | [7 empty] | 258.41
=====> Item Totals: 226 - POST, STREET NAME $5,943.51 0.5434 MH/EA 12.50 MH 258.413 23 EA
BID ITEM = 227 CLIENT# = 227 Land Item SCHEDULE: 1 100 Description = POST, BUS ZONE Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 227 CLIENT# = 227 Land Item SCHEDULE: 1 100 Description = POST, BUS ZONE Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
227.01 |  |  | POST, BUS ZONE | [23 empty] | Quan: |  |  | 8.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ |  |  | SIGN CREW | [21 empty] | 4 |  | CH |  |  | Prod: | [5 empty] | 4.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
2SIGNPOSTBUS SIGN POST BUS @110.25 1.00 | [22 empty] | 8.00 EA | [7 empty] | 120.000 1,058 1,058
LAG General Laborer 1.00 $1,337.44 0.5000 MH/EA | [22 empty] | 4.00 MH 4.00 MH | [7 empty] | 52.910 279 279 [ 29.1 ] 279 1,058 1,337
=====> Item T $1,337.44 | [7 empty] | otals: 227 0.5000 MH/EA | [10 empty] | POST, BUS ZONE 4.00 MH | [11 empty] | [ 29.1 ] | [6 empty] | 279 | [6 empty] | 1058 | [7 empty] | 1337
167.18 | [7 empty] | 8 EA | [29 empty] | 34.88 | [6 empty] | 132.3 | [7 empty] | 167.18
-
BID ITEM = 228 CLIENT# = 228 Land Item SCHEDULE: 1 100
Description = | [5 empty] | RELOCATE SIGN, TRAFFIC | [24 empty] | Unit = |  |  | EA Takeoff Quan: 134.000 Engr Quan: 134.000
228.01 | [5 empty] | RELOCATE SIGN, TRAFFIC | [24 empty] | Quan: |  |  | 134.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ | [5 empty] | SIGN CREW | [13 empty] | 134.00 CH Prod: 134.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG | [5 empty] | General Laborer | [13 empty] | 1.00 134.00 MH 52.910 9,348 9,348
9347.88 | [5 empty] | 1.0000 MH/EA 134.00 MH [ 58.201 ] 9,348 9,348
=====> Item Totals: 228 - RELOCA $9,347.88 1.0000 MH/EA 69.760 134 EA
TE SIGN, TRAFFI 134.00 MH | [30 empty] | C [ 58.201 ] | [6 empty] | 9348 | [14 empty] | 9348
[38 empty] | 69.76 | [14 empty] | 69.76
BID ITEM = 229 CLIENT# = 229 Land Item SCHEDULE: 1 100
Description = | [5 empty] | RELOCATE SIGN, STREET NAME | [18 empty] | Unit = | [8 empty] | EA Takeoff Quan: 91.000 Engr Quan: 91.000
229.01 | [5 empty] | RELOCATE SIGN, STREET NAME | [18 empty] | Quan: | [8 empty] | 91.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ | [5 empty] | SIGN CREW | [22 empty] | 91 |  | CH Prod: 91.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG | [5 empty] | General Laborer | [13 empty] | 1 |  |  |  |  | 91.00 MH | [5 empty] | 52.910 6,348 6,348
6348.19 | [5 empty] | 1.0000 MH/EA | [13 empty] | 91.00 MH [ 58.201 ] 6,348 6,348
=====> Item Totals: 229 - RELOCATE SIGN, STREET NAME $6,348.19 1.0000 MH/EA 91.00 MH [ 58.201 ] 6,348 6,348 69.760 91 EA 69.76 69.76
BID ITEM = 230 CLIENT# = 230 Land Item SCHEDULE: 1 100 Description = RELOCATE SIGN, BUS ZONE Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
230.01 RELOCATE SIGN, BUS ZONE | [30 empty] | Quan: |  |  | 2.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW | [23 empty] | 2 | [6 empty] | CH |  |  | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
LAG General Laborer 1.00 2.00 MH | [23 empty] | 52.91 | [17 empty] | 140 | [10 empty] | 140
$139.52 1.0000 MH/EA 2.00 MH | [23 empty] | [ 58.2 ] | [17 empty] | 140 | [10 empty] | 140
=====> Item Totals: 230 - RELOCATE SIGN, BUS ZONE
139.52 | [5 empty] | 1.0000 MH/EA | [17 empty] | 2.00 MH [ 58.2 ] | [17 empty] | 140 | [10 empty] | 140
69.76 | [5 empty] | 2 EA | [35 empty] | 69.76 | [10 empty] | 69.76
Activity Desc Resource Pcs | [16 empty] | Quantity | [5 empty] | Unit |  |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  |  | Total
BID ITEM = 231 CLIENT# = 231 Land Item SCHEDULE: 1 100
Description = |  |  | SIGN FOOTING, KCM, TYPE III | [23 empty] | Unit = EA
231.01 |  |  | SIGN FOOTING, KCM, TYPE III | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [14 empty] | 5.00 CY | [6 empty] | 8 |  | CH Pro 121.150
Takeoff Quan: 1.000 Engr Quan: 1.000 d:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
668 | [56 empty] | 668
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [10 empty] | 64.98 |  |  |  | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 68.98 |  |  |  | 723 | [6 empty] | 723
4798.24 | [5 empty] | 48.0000 MH/EA | [13 empty] | 48.00 MH | [13 empty] | [ 3466.14 ] |  |  |  | 4130 | [6 empty] | 668 | [7 empty] | 4798
=====> Item Totals: $4,798.24 | [9 empty] | 231 48.0000 MH/EA | [6 empty] | - SIGN FOOTING, KCM, TYPE III 48.00 MH | [16 empty] | [ 3466.14 ] |  |  |  | 4130 | [6 empty] | 668 | [7 empty] | 4798
4798.24 | [9 empty] | 1 EA | [27 empty] | 4130.4 | [6 empty] | 667.84 | [7 empty] | 4798.24
BID ITEM | [5 empty] | = |  | 232 | [5 empty] | CLIENT# = | [8 empty] | 232 | [5 empty] | Land Item SCHEDULE: 1 100
Description = | [5 empty] | PAVEMENT MARKING, PAINT, 6 IN STRIPE | [22 empty] | Unit = LF Takeoff Quan: 3,148.000 Engr Quan: 3,148.000
232.01 | [5 empty] | PAVEMENT MARKING, PAINT, 6 IN STRIPE | [22 empty] | Quan: 3,148.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 3,148.00 LF 3.000 9,444 9,444
BID ITEM = 233 CLIENT# = 233 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, THERMOPLASTIC, 8 IN ST Unit = LF Takeoff Quan: 44,997.000 Engr Quan: 44,997.000
4STRI Striping sub 1.00 44,997.00 LF 5.950 267,732 267,732
BID ITEM = 234 CLIENT# = 234 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, THERMOPLASTIC, LEGEND/ Unit = EA Takeoff Quan: 484.000 Engr Quan: 484.000
234.01 PAVEMENT MARKING, THERMOPLASTIC, LEG Quan: 484.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 484.00 EA 200.000 96,800 96,800
BID ITEM = 235 CLIENT# = 235 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, THERMOPLASTIC, BIKE DE Unit = EA Takeoff Quan: 100.000 Engr Quan: 100.000
235.01 PAVEMENT MARKING, THERMOPLASTIC, BIKE Quan: 100.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 100.00 EA 125.000 12,500 12,500
BID ITEM = 236 CLIENT# = 236 Land Item SCHEDULE: 1 100
Description = |  |  | PAVEMENT MARKING, MMA, 4 IN STRIPE | [23 empty] | Unit = |  |  | LF Takeoff Quan: 41,895.000 Engr Quan: 41,895.000
236.01 |  |  | PAVEMENT MARKING, MMA, 4 IN STRIPE | [23 empty] | Quan: |  |  | 41,895.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Activity |  |  | Desc | [13 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 236 CLIENT# = 236 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, 4 IN STRIPE Unit = LF Takeoff Quan: 41,895.000 Engr Quan: 41,895.000 4STRI Striping sub 1.00 41,895.00 LF 2.250 94,264 94,264
BID ITEM = 237 CLIENT# = 237 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, 6 IN STRIPE Unit = LF Takeoff Quan: 26,816.000 Engr Quan: 26,816.000
237.01 PAVEMENT MARKING, MMA, 6 IN STRIPE Quan: 26,816.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 26,816.00 LF 2.750 73,744 73,744
BID ITEM = 238 CLIENT# = 238 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, 8 IN STRIPE Unit = LF Takeoff Quan: 5,209.000 Engr Quan: 5,209.000
238.01 PAVEMENT MARKING, MMA, 8 IN STRIPE Quan: 5,209.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 5,209.00 LF 6.000 31,254 31,254
BID ITEM = 239 CLIENT# = 239 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, LEGEND/SYMBOL Unit = EA Takeoff Quan: 240.000 Engr Quan: 240.000
239.01 PAVEMENT MARKING, MMA, LEGEND/SYMBOL Quan: 240.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 240.00 EA 200.000 48,000 48,000
BID ITEM = 240 CLIENT# = 240 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, GREEN Unit = SF Takeoff Quan: 7,778.000 Engr Quan: 7,778.000
240.01 PAVEMENT MARKING, MMA, GREEN Quan: 7,778.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 7,778.00 SF 13.000 101,114 101,114
BID ITEM = 241 CLIENT# = 241 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, RED Unit = SF Takeoff Quan: 41,983.000 Engr Quan: 41,983.000
241.01 PAVEMENT MARKING, MMA, RED Quan: 41,983.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 41,983.00 SF 10.500 440,822 440,822
BID ITEM = 242 CLIENT# = 242 Land Item SCHEDULE: 1 100 Description = PAVEMENT MARKING, MMA, BLACK Unit = SF Takeoff Quan: 1,809.000 Engr Quan: 1,809.000
242.01 PAVEMENT MARKING, MMA, BLACK Quan: 1,809.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 1,809.00 SF 15.000 27,135 27,135
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 243 CLIENT# = 243 Land Item SCHEDULE: 1 100 Description = TEMPORARY PAVEMENT MARKING, PAINT, 4 IN Unit = LF Takeoff Quan: 104,000.000 Engr Quan: 104,000.000
243.01 TEMPORARY PAVEMENT MARKING, PAINT, 4 I Quan: 104,000.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 104,000.00 LF 1.000 104,000 104,000
BID ITEM = 244 CLIENT# = 244 Land Item SCHEDULE: 1 100 Description = TEMPORARY PAVEMENT MARKING, PAINT, LEGEN Unit = EA Takeoff Quan: 50.000 Engr Quan: 50.000
244.01 TEMPORARY PAVEMENT MARKING, PAINT, LE Quan: 50.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 50.00 EA 65.000 3,250 3,250
BID ITEM = 245 CLIENT# = 245 Land Item SCHEDULE: 1 100 Description = SIGN, PROJECT IDENTIFICATION, OWNER FURN Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
245.01 SIGN, PROJECT IDENTIFICATION, OWNER FUR Quan: | [33 empty] | 4.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 2.00 CH | [33 empty] | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 2.00 HR | [10 empty] | 51.051 | [18 empty] | 102 |  |  |  | 102
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 2.00 HR | [10 empty] | 52.3 | [18 empty] | 105 |  |  |  | 105
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 2.00 MH | [10 empty] | 77.06 | [7 empty] | 201 | [14 empty] | 201
LAG |  |  |  |  | General Laborer | [13 empty] | 2 |  |  |  | 4.00 MH | [10 empty] | 52.91 | [7 empty] | 279 | [14 empty] | 279
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 2.00 MH | [10 empty] | 74.56 | [7 empty] | 195 | [14 empty] | 195
$881.92 2.0000 MH/EA 8.00 MH | [33 empty] | [ 141.59 ] | [7 empty] | 675 | [10 empty] | 207 |  |  |  | 882
=====> Ite $881.92 |  |  |  |  | m Totals: 245 - 2.0000 MH/EA | [13 empty] | SIGN, PROJECT IDENTIFICATION, OWN 8.00 MH [ 141.59 ] | [18 empty] | ER FURN 675 | [14 empty] | 207 |  |  |  | 882
220.48 |  |  |  |  | 4 EA | [32 empty] | 168.81 | [14 empty] | 51.67 |  |  |  | 220.48
BID ITEM = 246 CLIENT# = 246 Land Item SCHEDULE: 1 100 Description = LUMINAIRE, LED, COLLECTOR ARTERIAL Unit = EA Takeoff Quan: 65.000 Engr Quan: 65.000
4ELEC Electrical sub 1.00 65.00 EA 810.000 52,650 52,650
BID ITEM = 247 CLIENT# = 247 Land Item SCHEDULE: 1 100 Description = LUMINAIRE, LED, PRINCIPAL ARTERIAL Unit = EA Takeoff Quan: 31.000 Engr Quan: 31.000
4ELEC Electrical sub 1.00 31.00 EA 1,120.000 34,720 34,720
BID ITEM = 248 CLIENT# = 248 Land Item SCHEDULE: 1 100 Description = LUMINAIRE, LED, PEDESTRIAN SCALE Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 248 CLIENT# = 248 LUMINAIRE, LED, PEDESTRIAN SCALE | [20 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
248.01 | [5 empty] | LUMINAIRE, LED, PEDESTRIAN SCALE | [20 empty] | Quan: 30.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 30.00 EA 3,650.000 109,500 109,500
BID ITEM = 249 CLIENT# = 249 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | INSTALL GROUND ROD | [24 empty] | Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
| 249.01 |  |  |  |  | INSTALL GROUND ROD | [24 empty] | Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 5.00 EA | [7 empty] | 340.000 1,700 1,700
BID ITEM = 250 CLIENT# = 250 Land Item SCHEDULE: 1 100 Description = TEMPORARY STREET LIGHTING Unit = FA Takeoff Quan: 39,000.000 Engr Quan: 39,000.000
250.01 TEMPORARY STREET LIGHTING Quan: 39,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 39,000.00 FA 0.890 34,710 34,710
=====> Item Totals: 250 - TEMPORARY STREET LIGHTING
34710 | [30 empty] | [ ] | [8 empty] | 34710 | [12 empty] | 34710
0.89 | [5 empty] | 39000 FA | [33 empty] | 0.89 | [12 empty] | 0.89
BID ITEM = 251 CLIENT# = 251 Land Item SCHEDULE: 1 100 Description = TEMPORARY STREET LIGHTING PLAN SUBMITTAL Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
251.01 TEMPORARY STREET LIGHTING PLAN SUBMIT Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 2,500.000 2,500 2,500
BID ITEM = 252 CLIENT# = 252 Land Item SCHEDULE: 1 100 Description = RECONNECT EXISTING STREET LIGHTING SYSTE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
252.01 RECONNECT EXISTING STREET LIGHTING SYS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 30,300.000 30,300 30,300
BID ITEM = 253 CLIENT# = 253 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 1) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
253.01 WIRING, STREET LIGHTING, (SCHEMATIC 1) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,800.000 1,800 1,800
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 254 CLIENT# = 254 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 2) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
254.01 WIRING, STREET LIGHTING, (SCHEMATIC 2) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 2,700.000 2,700 2,700
BID ITEM = 255 CLIENT# = 255 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 3) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
255.01 WIRING, STREET LIGHTING, (SCHEMATIC 3) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 7,900.000 7,900 7,900
BID ITEM = 256 CLIENT# = 256 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 4) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
256.01 WIRING, STREET LIGHTING, (SCHEMATIC 4) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 5,200.000 5,200 5,200
BID ITEM = 257 CLIENT# = 257 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 5) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
257.01 WIRING, STREET LIGHTING, (SCHEMATIC 5) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,900.000 1,900 1,900
BID ITEM = 258 CLIENT# = 258 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 6) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
258.01 WIRING, STREET LIGHTING, (SCHEMATIC 6) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 8,800.000 8,800 8,800
BID ITEM = 259 CLIENT# = 259 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 7) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
259.01 WIRING, STREET LIGHTING, (SCHEMATIC 7) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,200.000 3,200 3,200
BID ITEM | [5 empty] | = |  | 260 | [5 empty] | CLIENT# = 260 | [14 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | WIRING, STREET | [5 empty] | LIGHTING, (SCHEMATIC 8) | [14 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 260 CLIENT# = 260 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 8) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
260.01 WIRING, STREET LIGHTING, (SCHEMATIC 8) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,000.000 10,000 10,000
BID ITEM = 261 CLIENT# = 261 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 9) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
261.01 WIRING, STREET LIGHTING, (SCHEMATIC 9) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 41,400.000 41,400 41,400
BID ITEM = 262 CLIENT# = 262 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 10) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
262.01 WIRING, STREET LIGHTING, (SCHEMATIC 10) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 25,200.000 25,200 25,200
BID ITEM = 263 CLIENT# = 263 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 11) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
263.01 WIRING, STREET LIGHTING, (SCHEMATIC 11) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 6,300.000 6,300 6,300
BID ITEM = 264 CLIENT# = 264 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 12) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
264.01 WIRING, STREET LIGHTING, (SCHEMATIC 12) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,200.000 3,200 3,200
BID ITEM = 265 CLIENT# = 265 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 13) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
265.01 WIRING, STREET LIGHTING, (SCHEMATIC 13) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 12,400.000 12,400 12,400
BID ITEM | [5 empty] | = |  | 266 | [5 empty] | CLIENT# = 266 | [14 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | WIRING, STREET | [5 empty] | LIGHTING, (SCHEMATIC 14) | [14 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 266 CLIENT# = 266 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 14) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
266.01 WIRING, STREET LIGHTING, (SCHEMATIC 14) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,900.000 10,900 10,900
BID ITEM = 267 CLIENT# = 267 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 15) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
267.01 WIRING, STREET LIGHTING, (SCHEMATIC 15) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 11,100.000 11,100 11,100
BID ITEM = 268 CLIENT# = 268 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 16) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
268.01 WIRING, STREET LIGHTING, (SCHEMATIC 16) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,500.000 10,500 10,500
BID ITEM = 269 CLIENT# = 269 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 17) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
269.01 WIRING, STREET LIGHTING, (SCHEMATIC 17) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 9,400.000 9,400 9,400
BID ITEM = 270 CLIENT# = 270 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 18) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
270.01 WIRING, STREET LIGHTING, (SCHEMATIC 18) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,100.000 3,100 3,100
BID ITEM = 271 CLIENT# = 271 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 19) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
271.01 WIRING, STREET LIGHTING, (SCHEMATIC 19) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,200.000 10,200 10,200
BID ITEM | [5 empty] | = |  | 272 | [5 empty] | CLIENT# = 272 | [14 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | WIRING, STREET | [5 empty] | LIGHTING, (SCHEMATIC 20) | [14 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 272 CLIENT# = 272 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 20) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
272.01 WIRING, STREET LIGHTING, (SCHEMATIC 20) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,200.000 3,200 3,200
BID ITEM = 273 CLIENT# = 273 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 21) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
273.01 WIRING, STREET LIGHTING, (SCHEMATIC 21) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 5,500.000 5,500 5,500
BID ITEM = 274 CLIENT# = 274 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 22) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
274.01 WIRING, STREET LIGHTING, (SCHEMATIC 22) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 7,000.000 7,000 7,000
BID ITEM = 275 CLIENT# = 275 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 23) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
275.01 WIRING, STREET LIGHTING, (SCHEMATIC 23) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 500.000 500 500
BID ITEM = 276 CLIENT# = 276 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 24) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
276.01 WIRING, STREET LIGHTING, (SCHEMATIC 24) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 7,000.000 7,000 7,000
BID ITEM = 277 CLIENT# = 277 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 25) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
277.01 WIRING, STREET LIGHTING, (SCHEMATIC 25) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 8,600.000 8,600 8,600
BID ITEM | [5 empty] | = |  | 278 | [5 empty] | CLIENT# = 278 | [14 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | WIRING, STREET | [5 empty] | LIGHTING, (SCHEMATIC 26) | [14 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 278 CLIENT# = 278 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 26) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
278.01 WIRING, STREET LIGHTING, (SCHEMATIC 26) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 8,700.000 8,700 8,700
BID ITEM = 279 CLIENT# = 279 Land Item SCHEDULE: 1 100 Description = WIRING, STREET LIGHTING, (SCHEMATIC 27) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
279.01 WIRING, STREET LIGHTING, (SCHEMATIC 27) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,200.000 1,200 1,200
BID ITEM = 280 CLIENT# = 280 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURN. TRAF. SIG. CNTRL. CA Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
280.01 INSTALL OWNER FURN. TRAF. SIG. CNTRL. CA Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 1,700.000 1,700 1,700
BID ITEM = 281 CLIENT# = 281 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURN. TRAF. SIG. CNTRL. CA Unit = EA Takeoff Quan: 33.000 Engr Quan: 33.000
281.01 INSTALL OWNER FURN. TRAF. SIG. CNTRL. CA Quan: 33.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 33.00 EA 2,570.000 84,810 84,810
BID ITEM = 282 CLIENT# = 282 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, VEHICLE, 3 SECTION 1-WAY Unit = EA Takeoff Quan: 216.000 Engr Quan: 216.000
282.01 SIGNAL HEAD, VEHICLE, 3 SECTION 1-WAY Quan: 216.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 216.00 EA 1,280.000 276,480 276,480
BID ITEM = 283 CLIENT# = 283 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, VEHICLE, 3 SECTION 1-WAY, O Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
283.01 SIGNAL HEAD, VEHICLE, 3 SECTION 1-WAY, O Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 6.00 EA 2,150.000 12,900 12,900
BID ITEM | [5 empty] | = |  | 284 |  |  |  |  | CLIENT# = 284 | [15 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | SIGNAL HEAD, |  |  |  |  | BICYCLE, 3-SECTION 8" | [15 empty] | Unit = EA Takeoff Quan: | [21 empty] | 2 |  | Engr Quan: |  |  |  | 2
Activity |  |  | Desc | [13 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 284 CLIENT# = 284 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, BICYCLE, 3-SECTION 8" Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
284.01 SIGNAL HEAD, BICYCLE, 3-SECTION 8" Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 1,450.000 2,900 2,900
BID ITEM = 285 CLIENT# = 285 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, BICYCLE, 3-SECTION 4" Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
285.01 SIGNAL HEAD, BICYCLE, 3-SECTION 4" Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 1,450.000 2,900 2,900
BID ITEM = 286 CLIENT# = 286 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, VEHICLE, 3-SECTION 8" Unit = EA Takeoff Quan: 9.000 Engr Quan: 9.000
186.01 SIGNAL HEAD, VEHICLE, 3-SECTION 8" Quan: 9.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 9.00 EA 1,240.000 11,160 11,160
BID ITEM = 287 CLIENT# = 287 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, TRANSIT, 3-SECTION 8" Unit = EA Takeoff Quan: 11.000 Engr Quan: 11.000
287.01 SIGNAL HEAD, TRANSIT, 3-SECTION 8" Quan: 11.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 11.00 EA 1,530.000 16,830 16,830
BID ITEM = 288 CLIENT# = 288 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, VEHICLE, 4 SECTION 1-WAY Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
288.01 SIGNAL HEAD, VEHICLE, 4 SECTION 1-WAY Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 10.00 EA 1,600.000 16,000 16,000
BID ITEM = 289 CLIENT# = 289 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, VEHICLE, 4 SECTION 1-WAY, B Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
289.01 SIGNAL HEAD, VEHICLE, 4 SECTION 1-WAY, B Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 5.00 EA 1,600.000 8,000 8,000
BID ITEM = 290 CLIENT# = 290 Land Item SCHEDULE: 1 100 Description = SIGNAL HEAD, PEDESTRIAN COUNTDOWN, LED Unit = EA Takeoff Quan: 191.000 Engr Quan: 191.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 290 CLIENT# = 290 Lan SIGNAL HEAD, PEDESTRIAN COUNTDOWN, LED | [24 empty] | d Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 191.000 Engr Quan: 191.000
290.01 | [5 empty] | SIGNAL HEAD, PEDESTRIAN COUNTDOWN, LE | [24 empty] | Quan: 191.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 191.00 EA 790.000 150,890 150,890
BID ITEM = 291 CLIENT# = 291 Land Item SCHEDULE: 1 100 Description = BICYCLE PUSHBUTTON ASSEMBLY Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
4ELEC Electrical sub 1.00 3.00 EA 1,230.000 3,690 3,690
BID ITEM = 292 CLIENT# = 292 Land Item SCHEDULE: 1 100 Description = APS PEDESTRIAN PUSHBUTTON ASSEMBLY Unit = EA Takeoff Quan: 242.000 Engr Quan: 242.000
4ELEC Electrical sub 1.00 242.00 EA 1,390.000 336,380 336,380
BID ITEM = 293 CLIENT# = 293 Land Item SCHEDULE: 1 100 Description = BOOM TRUCK AND OPERATOR FOR INSPECTOR Unit = HR Takeoff Quan: 20.000 Engr Quan: 20.000
293.01 BOOM TRUCK AND OPERATOR FOR INSPECTO Quan: 20.00 HR Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 20.00 HR 160.000 3,200 3,200
BID ITEM = 294 CLIENT# = 294 Land Item SCHEDULE: 1 100 Description = DETECTOR LOOP, 6 FT DIA. Unit = EA Takeoff Quan: 184.000 Engr Quan: 184.000
4ELEC Electrical sub 1.00 184.00 EA 1,630.000 299,920 299,920
BID ITEM = 295 CLIENT# = 295 Land Item SCHEDULE: 1 100 Description = DETECTOR LOOP, PREFORMED, 6 FT DIA Unit = EA Takeoff Quan: 135.000 Engr Quan: 135.000
4ELEC Electrical sub 1.00 135.00 EA 1,300.000 175,500 175,500
BID ITEM = 296 CLIENT# = 296 Land Item SCHEDULE: 1 100 Description = DETECTOR LOOP, PARALLELOGRAM Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 296 CLIENT# = 296 DETECTOR LOOP, PARALLELOGRAM | [20 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
296.01 | [5 empty] | DETECTOR LOOP, PARALLELOGRAM | [20 empty] | Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 8.00 EA 3,000.000 24,000 24,000
BID ITEM = 297 CLIENT# = 297 Land Item SCHEDULE: 1 100 Description = DETECTOR LOOP, PREFORMED, PARALLELOGRAM Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
297.01 DETECTOR LOOP, PREFORMED, PARALLELOG Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 8.00 EA 1,300.000 10,400 10,400
BID ITEM = 298 CLIENT# = 298 Land Item SCHEDULE: 1 100 Description = AERIAL INNERDUCT Unit = LF Takeoff Quan: 545.000 Engr Quan: 545.000
| 298.01 |  |  |  |  | AERIAL INNERDUCT | [24 empty] | Quan: |  |  | 545.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 545.00 EA | [10 empty] | 20 | [7 empty] | 10,900 10,900
BID ITEM = 299 CLIENT# = 299 Land Item SCHEDULE: 1 100 Description = INTERCONNECT CABLE, AERIAL Unit = LF Takeoff Quan: 235.000 Engr Quan: 235.000
4ELEC Electrical sub 1.00 235.00 LF 80.000 18,800 18,800
BID ITEM = 300 CLIENT# = 300 Land Item SCHEDULE: 1 100 Description = INTERCONNECT CABLE, UNDERGROUND Unit = LF Takeoff Quan: 175.000 Engr Quan: 175.000
4ELEC Electrical sub 1.00 175.00 LF 100.000 17,500 17,500
BID ITEM = 301 CLIENT# = 301 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | TERMINAL CABINET | [24 empty] | Unit = EA Takeoff Quan: 88.000 Engr Quan: 88.000
| 301.01 |  |  |  |  | TERMINAL CABINET | [24 empty] | Quan: 88.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 88.00 EA | [7 empty] | 1,060.000 93,280 93,280
BID ITEM = 302 CLIENT# = 302 Land Item SCHEDULE: 1 100 Description = SPAN WIRE Unit = LF Takeoff Quan: 525.000 Engr Quan: 525.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract Total
BID ITEM = 302 CLIENT# = 302 Land Item SCHEDULE: 1 100 Description = SPAN WIRE Unit = LF Takeoff Quan: 525.000 Engr Quan: 525.000
302.01 |  |  | SPAN WIRE | [23 empty] | Quan: |  |  | 525.00 LF | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC |  |  | Electrical sub | [10 empty] | 1 |  |  | 525.00 LF | [12 empty] | 20 | [6 empty] | 10,500 10,500
BID ITEM = 303 CLIENT# = 303 Land Item SCHEDULE: 1 100 Description = RELOCATE PEDESTRIAN SIGNAL HEAD Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 EA 400.000 400 400
BID ITEM = 304 CLIENT# = 304 Land Item SCHEDULE: 1 100 Description = RELOCATE CCTV CAMERA Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
4ELEC Electrical sub 1.00 2.00 EA 5,700.000 11,400 11,400
BID ITEM = 305 CLIENT# = 305 Land Item SCHEDULE: 1 100 Description = RELOCATE EMERGENCY VEHICLE DETECTOR Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
305.01 RELOCATE EMERGENCY VEHICLE DETECTOR Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 600.000 600 600
BID ITEM = 306 CLIENT# = 306 Land Item SCHEDULE: 1 100 Description = EMERGENCY VEHICLE PREEMPTION DETECTOR, O Unit = EA Takeoff Quan: 38.000 Engr Quan: 38.000
306.01 EMERGENCY VEHICLE PREEMPTION DETECT Quan: 38.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 38.00 EA 1,650.000 62,700 62,700
BID ITEM = 307 CLIENT# = 307 Land Item SCHEDULE: 1 100 Description = VIDEO DETECTION CAMERA Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
4ELEC Electrical sub 1.00 4.00 EA 11,400.000 45,600 45,600
BID ITEM = 308 CLIENT# = 308 Land Item SCHEDULE: 1 100 Description = CCTV CAMERA, PTZ Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
Activity Desc Resource | [17 empty] | Pcs |  |  |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 308 CLIE CCTV CAMERA, PTZ | [11 empty] | NT# = 3 |  |  |  |  | 08 Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
308.01 | [5 empty] | CCTV CAMERA, PTZ | [16 empty] | Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [11 empty] | 1 |  |  |  |  | 10.00 EA 13,870.000 138,700 138,700
BID ITEM = 309 CLIENT# = 309 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | WIRELESS SENSOR | [24 empty] | Unit = EA Takeoff Quan: 174.000 Engr Quan: 174.000
| 309.01 |  |  |  |  | WIRELESS SENSOR | [24 empty] | Quan: 174.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 174.00 EA | [7 empty] | 1,470.000 255,780 255,780
BID ITEM = 310 CLIENT# = 310 Land Item SCHEDULE: 1 100 Description = WIRELESS SENSOR ACCESS POINT Unit = EA Takeoff Quan: 38.000 Engr Quan: 38.000
4ELEC Electrical sub 1.00 38.00 EA 6,310.000 239,780 239,780
BID ITEM = 311 CLIENT# = 311 Land Item SCHEDULE: 1 100 Description = WIRELESS SENSOR REPEATER Unit = EA Takeoff Quan: 25.000 Engr Quan: 25.000
4ELEC Electrical sub 1.00 25.00 EA 4,420.000 110,500 110,500
BID ITEM = 312 CLIENT# = 312 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | SERVICE CABINET | [24 empty] | Unit = EA Takeoff Quan: 25.000 Engr Quan: 25.000
| 312.01 |  |  |  |  | SERVICE CABINET | [24 empty] | Quan: 25.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 25.00 EA | [7 empty] | 4,040.000 101,000 101,000
BID ITEM = 313 CLIENT# = 313 Land Item SCHEDULE: 1 100 Description = SERVICE CABINET WITH STEP-DOWN TRANSFORM Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
313.01 SERVICE CABINET WITH STEP-DOWN TRANSF Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 5.00 EA 10,700.000 53,500 53,500
BID ITEM = 314 CLIENT# = 314 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-MINOR) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 314 CLIENT# = 314 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-MINOR) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
314.01 SERVICE WIRING (MADISON-MINOR) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 5,700.000 5,700 5,700
BID ITEM = 315 CLIENT# = 315 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-BOYLSTON) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
315.01 SERVICE WIRING (MADISON-BOYLSTON) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,000.000 3,000 3,000
BID ITEM = 316 CLIENT# = 316 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-BROADWAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
316.01 SERVICE WIRING (MADISON-BROADWAY) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,500.000 1,500 1,500
BID ITEM = 317 CLIENT# = 317 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-11TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
317.01 SERVICE WIRING (MADISON-11TH) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,100.000 1,100 1,100
BID ITEM = 318 CLIENT# = 318 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-12TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
318.01 SERVICE WIRING (MADISON-12TH) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 4,400.000 4,400 4,400
BID ITEM = 319 CLIENT# = 319 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-13TH MIDBLOCK) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
319.01 SERVICE WIRING (MADISON-13TH MIDBLOCK) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 2,100.000 2,100 2,100
BID ITEM | [5 empty] | = |  | 320 | [5 empty] | CLIENT# = 320 | [14 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | SERVICE WIRING | [5 empty] | (MADISON-14TH) | [14 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 320 CLIENT# = 320 SERVICE WIRING (MADISON-14TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
320.01 | [5 empty] | SERVICE WIRING (MADISON-14TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,000.000 1,000 1,000
BID ITEM = 321 CLIENT# = 321 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-15TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,300.000 1,300 1,300
BID ITEM = 322 CLIENT# = 322 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-16TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,800.000 1,800 1,800
BID ITEM = 323 CLIENT# = 323 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-17TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,600.000 1,600 1,600
BID ITEM = 324 CLIENT# = 324 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-18TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,100.000 1,100 1,100
BID ITEM = 325 CLIENT# = 325 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-19TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,500.000 1,500 1,500
BID ITEM = 326 CLIENT# = 326 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-20TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 326 CLIENT# = 326 SERVICE WIRING (MADISON-20TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
326.01 | [5 empty] | SERVICE WIRING (MADISON-20TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,300.000 1,300 1,300
BID ITEM = 327 CLIENT# = 327 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-E DENNY WAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
327.01 SERVICE WIRING (MADISON-E DENNY WAY) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,500.000 1,500 1,500
BID ITEM = 328 CLIENT# = 328 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-JOHN) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,000.000 1,000 1,000
BID ITEM = 329 CLIENT# = 329 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-MLK WAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,500.000 1,500 1,500
BID ITEM = 330 CLIENT# = 330 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MLK WAY-HARRISON) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 2,000.000 2,000 2,000
BID ITEM = 331 CLIENT# = 331 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (UNION-19TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,200.000 1,200 1,200
BID ITEM = 332 CLIENT# = 332 Land Item SCHEDULE: 1 100 Description = SERVICE WIRING (MADISON-10TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 332 CLIENT# = 332 SERVICE WIRING (MADISON-10TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
332.01 | [5 empty] | SERVICE WIRING (MADISON-10TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 4,300.000 4,300 4,300
BID ITEM = 333 CLIENT# = 333 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-1ST) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 8,400.000 8,400 8,400
BID ITEM = 334 CLIENT# = 334 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-2ND) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,500.000 1,500 1,500
BID ITEM = 335 CLIENT# = 335 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-3RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 14,600.000 14,600 14,600
BID ITEM = 336 CLIENT# = 336 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-4TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,700.000 1,700 1,700
BID ITEM = 337 CLIENT# = 337 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-5TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 300.000 300 300
BID ITEM = 338 CLIENT# = 338 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-6TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [23 empty] | Quantity |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 338 CLIENT# = 33 SIGNAL WIRING (SPRING-6TH) | [17 empty] | 8 Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
338.01 | [5 empty] | SIGNAL WIRING (SPRING-6TH) | [17 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,600.000 1,600 1,600
BID ITEM = 339 CLIENT# = 339 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-7TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 7,300.000 7,300 7,300
BID ITEM = 340 CLIENT# = 340 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-8TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 10,000.000 10,000 10,000
BID ITEM = 341 CLIENT# = 341 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (SPRING-9TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 11,800.000 11,800 11,800
BID ITEM = 342 CLIENT# = 342 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-1ST) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 9,800.000 9,800 9,800
BID ITEM = 343 CLIENT# = 343 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-2ND) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 400.000 400 400
BID ITEM = 344 CLIENT# = 344 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-3RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 344 CLIENT# = 344 SIGNAL WIRING (MADISON-3RD) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
344.01 | [5 empty] | SIGNAL WIRING (MADISON-3RD) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 13,100.000 13,100 13,100
BID ITEM = 345 CLIENT# = 345 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-4TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 2,500.000 2,500 2,500
BID ITEM = 346 CLIENT# = 346 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-6TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 6,400.000 6,400 6,400
BID ITEM = 347 CLIENT# = 347 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-7TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 13,800.000 13,800 13,800
BID ITEM = 348 CLIENT# = 348 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-8TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 13,200.000 13,200 13,200
BID ITEM = 349 CLIENT# = 349 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-9TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,600.000 18,600 18,600
BID ITEM = 350 CLIENT# = 350 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-TERRY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 350 CLIENT# = 350 SIGNAL WIRING (MADISON-TERRY) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
350.01 | [5 empty] | SIGNAL WIRING (MADISON-TERRY) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 13,300.000 13,300 13,300
BID ITEM = 351 CLIENT# = 351 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-BOREN) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 31,900.000 31,900 31,900
BID ITEM = 352 CLIENT# = 352 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-MINOR) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 11,300.000 11,300 11,300
BID ITEM = 353 CLIENT# = 353 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-SUMMIT) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 11,400.000 11,400 11,400
BID ITEM = 354 CLIENT# = 354 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-BOYLSTON) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,900.000 18,900 18,900
BID ITEM = 355 CLIENT# = 355 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-BROADWAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 24,200.000 24,200 24,200
BID ITEM = 356 CLIENT# = 356 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-11TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 356 CLIENT# = 356 SIGNAL WIRING (MADISON-11TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
356.01 | [5 empty] | SIGNAL WIRING (MADISON-11TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,600.000 10,600 10,600
BID ITEM = 357 CLIENT# = 357 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-12TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 23,800.000 23,800 23,800
BID ITEM = 358 CLIENT# = 358 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-13TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 13,000.000 13,000 13,000
BID ITEM = 359 CLIENT# = 359 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-14TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 22,100.000 22,100 22,100
BID ITEM = 360 CLIENT# = 360 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-15TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 12,400.000 12,400 12,400
BID ITEM = 361 CLIENT# = 361 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-16TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 10,300.000 10,300 10,300
BID ITEM = 362 CLIENT# = 362 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-17TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 362 CLIENT# = 362 SIGNAL WIRING (MADISON-17TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
362.01 | [5 empty] | SIGNAL WIRING (MADISON-17TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 14,100.000 14,100 14,100
BID ITEM = 363 CLIENT# = 363 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-18TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 7,600.000 7,600 7,600
BID ITEM = 364 CLIENT# = 364 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-19TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 13,700.000 13,700 13,700
BID ITEM = 365 CLIENT# = 365 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-20TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,400.000 18,400 18,400
BID ITEM = 366 CLIENT# = 366 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-E DENNY WAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 10,700.000 10,700 10,700
BID ITEM = 367 CLIENT# = 367 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-23RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 4,500.000 4,500 4,500
BID ITEM = 368 CLIENT# = 368 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-JOHN) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 368 CLIENT# = 368 SIGNAL WIRING (MADISON-JOHN) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
368.01 | [5 empty] | SIGNAL WIRING (MADISON-JOHN) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 11,900.000 11,900 11,900
BID ITEM = 369 CLIENT# = 369 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-MLK WAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,400.000 18,400 18,400
BID ITEM = 370 CLIENT# = 370 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MLK WAY-HARRISON) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 8,000.000 8,000 8,000
BID ITEM = 371 CLIENT# = 371 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (UNION-19TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 10,700.000 10,700 10,700
BID ITEM = 372 CLIENT# = 372 Land Item SCHEDULE: 1 100 Description = SIGNAL WIRING (MADISON-10TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 4,300.000 4,300 4,300
BID ITEM = 373 CLIENT# = 373 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (SPRING-1ST) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 8,200.000 8,200 8,200
BID ITEM = 374 CLIENT# = 374 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (SPRING-3RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 374 CLIENT# = 374 TEMPORARY SIGNAL (SPRING-3RD) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
374.01 | [5 empty] | TEMPORARY SIGNAL (SPRING-3RD) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 10,900.000 10,900 10,900
BID ITEM = 375 CLIENT# = 375 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (SPRING-5TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 8,200.000 8,200 8,200
BID ITEM = 376 CLIENT# = 376 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (SPRING-7TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,000.000 18,000 18,000
BID ITEM = 377 CLIENT# = 377 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-1ST) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 19,000.000 19,000 19,000
BID ITEM = 378 CLIENT# = 378 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-3RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 11,500.000 11,500 11,500
BID ITEM = 379 CLIENT# = 379 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-6TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 14,100.000 14,100 14,100
BID ITEM = 380 CLIENT# = 380 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-7TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 380 CLIENT# = 380 TEMPORARY SIGNAL (MADISON-7TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
380.01 | [5 empty] | TEMPORARY SIGNAL (MADISON-7TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 32,200.000 32,200 32,200
BID ITEM = 381 CLIENT# = 381 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-8TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 31,500.000 31,500 31,500
BID ITEM = 382 CLIENT# = 382 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-9TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 31,500.000 31,500 31,500
BID ITEM = 383 CLIENT# = 383 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-TERRY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 24,800.000 24,800 24,800
BID ITEM = 384 CLIENT# = 384 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-BOREN) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 36,300.000 36,300 36,300
BID ITEM = 385 CLIENT# = 385 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-MINOR) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 23,000.000 23,000 23,000
BID ITEM = 386 CLIENT# = 386 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-SUMMIT) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 386 CLIENT# = 386 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-SUMMIT) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
386.01 TEMPORARY SIGNAL (MADISON-SUMMIT) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 15,600.000 15,600 15,600
BID ITEM = 387 CLIENT# = 387 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-BOYLSTON) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
387.01 TEMPORARY SIGNAL (MADISON-BOYLSTON) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 18,200.000 18,200 18,200
BID ITEM = 388 CLIENT# = 388 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-BROADWAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
388.01 TEMPORARY SIGNAL (MADISON-BROADWAY) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 50,500.000 50,500 50,500
BID ITEM = 389 CLIENT# = 389 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-11TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
389.01 TEMPORARY SIGNAL (MADISON-11TH) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 40,600.000 40,600 40,600
BID ITEM = 390 CLIENT# = 390 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-12TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
390.01 TEMPORARY SIGNAL (MADISON-12TH) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 56,600.000 56,600 56,600
BID ITEM = 391 CLIENT# = 391 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-13TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
391.01 TEMPORARY SIGNAL (MADISON-13TH) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 50,200.000 50,200 50,200
BID ITEM | [5 empty] | = |  | 392 |  |  |  | CLIENT# = 392 | [16 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | TEMPORARY |  |  |  | SIGNAL (MADISON-14TH) | [16 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 392 CLIENT# = 392 TEMPORARY SIGNAL (MADISON-14TH) | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
392.01 | [5 empty] | TEMPORARY SIGNAL (MADISON-14TH) | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 86,900.000 86,900 86,900
BID ITEM = 393 CLIENT# = 393 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-15TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 18,200.000 18,200 18,200
BID ITEM = 394 CLIENT# = 394 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-16TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 15,600.000 15,600 15,600
BID ITEM = 395 CLIENT# = 395 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-17TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 15,600.000 15,600 15,600
BID ITEM = 396 CLIENT# = 396 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-19TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 15,600.000 15,600 15,600
BID ITEM = 397 CLIENT# = 397 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-20TH) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 24,100.000 24,100 24,100
BID ITEM = 398 CLIENT# = 398 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-DENNY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 398 CLIENT# = 398 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-DENNY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
398.01 TEMPORARY SIGNAL (MADISON-DENNY) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 20,800.000 20,800 20,800
BID ITEM = 399 CLIENT# = 399 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-23RD) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
399.01 TEMPORARY SIGNAL (MADISON-23RD) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 15,600.000 15,600 15,600
BID ITEM = 400 CLIENT# = 400 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-JOHN) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
400.01 TEMPORARY SIGNAL (MADISON-JOHN) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 36,500.000 36,500 36,500
BID ITEM = 401 CLIENT# = 401 Land Item SCHEDULE: 1 100 Description = TEMPORARY SIGNAL (MADISON-MLK WAY) Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
401.01 TEMPORARY SIGNAL (MADISON-MLK WAY) Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 36,500.000 36,500 36,500
BID ITEM = 402 CLIENT# = 402 Land Item SCHEDULE: 1 100 Description = DETECTION INDICATOR, LED BICYCLE BLUE LI Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
402.01 DETECTION INDICATOR, LED BICYCLE BLUE L Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 600.000 1,200 1,200
BID ITEM = 403 CLIENT# = 403 Land Item SCHEDULE: 1 100 Description = POLE, STEEL STRAIN, TYPE T Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
403.01 POLE, STEEL STRAIN, TYPE T Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 11,200.000 11,200 11,200
BID ITEM | [5 empty] | = |  | 404 |  |  |  | CLIENT# = 404 | [16 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | POLE, STEEL |  |  |  | STRAIN, TYPE X | [16 empty] | Unit = EA Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 404 CLIENT# = 404 Land Item SCHEDULE: 1 100 Description = POLE, STEEL STRAIN, TYPE X Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
404.01 POLE, STEEL STRAIN, TYPE X Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 18,800.000 18,800 18,800
BID ITEM = 405 CLIENT# = 405 Land Item SCHEDULE: 1 100 Description = POLE, STEEL STRAIN, TYPE Z Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
405.01 POLE, STEEL STRAIN, TYPE Z Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 21,400.000 21,400 21,400
BID ITEM = 406 CLIENT# = 406 Land Item SCHEDULE: 1 100 Description = POLE, STEEL MAST ARM Unit = EA Takeoff Quan: 32.000 Engr Quan: 32.000
406.01 POLE, STEEL MAST ARM Quan: 32.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 32.00 EA 13,930.000 445,760 445,760
BID ITEM = 407 CLIENT# = 407 Land Item SCHEDULE: 1 100 Description = POLE, STEEL DOUBLE MAST ARM Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
407.01 POLE, STEEL DOUBLE MAST ARM Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 19,800.000 39,600 39,600
BID ITEM = 408 CLIENT# = 408 Land Item SCHEDULE: 1 100 Description = POLE, PEDESTRIAN, ALUMINUM LIGHTING, 14 Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
408.01 POLE, PEDESTRIAN, ALUMINUM LIGHTING, 14 Quan: 30.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 30.00 EA 2,770.000 83,100 83,100
BID ITEM = 409 CLIENT# = 409 Land Item SCHEDULE: 1 100 Description = POLE, STEEL LIGHTING 25 to 35 FT Unit = EA Takeoff Quan: 20.000 Engr Quan: 20.000
409.01 POLE, STEEL LIGHTING 25 to 35 FT Quan: 20.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 20.00 EA 4,600.000 92,000 92,000
BID ITEM | [5 empty] | = |  | 410 |  |  | CLIENT# = 410 | [17 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | PEDESTAL, |  |  | ALUMINUM, 10 FT | [17 empty] | Unit = EA Takeoff Quan: | [21 empty] | 32 |  | Engr Quan: |  |  |  | 32
Activity Desc Resource Pcs | [23 empty] | Quantity |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 410 CLIENT# = 41 PEDESTAL, ALUMINUM, 10 FT | [17 empty] | 0 Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 32.000 Engr Quan: 32.000
410.01 | [5 empty] | PEDESTAL, ALUMINUM, 10 FT | [17 empty] | Quan: 32.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 32.00 EA 3,680.000 117,760 117,760
BID ITEM = 411 CLIENT# = 411 Land Item SCHEDULE: 1 100 Description = PEDESTAL, ALUMINUM, 12 FT Unit = EA Takeoff Quan: 20.000 Engr Quan: 20.000
4ELEC Electrical sub 1.00 20.00 EA 4,660.000 93,200 93,200
BID ITEM = 412 CLIENT# = 412 Land Item SCHEDULE: 1 100 Description = PEDESTAL, ALUMINUM, 14 FT Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
4ELEC Electrical sub 1.00 3.00 EA 4,930.000 14,790 14,790
BID ITEM = 413 CLIENT# = 413 Land Item SCHEDULE: 1 100 Description = MAST ARM, 30 FT AND LESS Unit = EA Takeoff Quan: 43.000 Engr Quan: 43.000
4ELEC Electrical sub 1.00 43.00 EA 9,030.000 388,290 388,290
BID ITEM = 414 CLIENT# = 414 Land Item SCHEDULE: 1 100 Description = MAST ARM, 31 FT TO 40 FT Unit = EA Takeoff Quan: 18.000 Engr Quan: 18.000
4ELEC Electrical sub 1.00 18.00 EA 10,760.000 193,680 193,680
BID ITEM = 415 CLIENT# = 415 Land Item SCHEDULE: 1 100 Description = MAST ARM, 41 FT TO 50 FT Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
4ELEC Electrical sub 1.00 6.00 EA 14,930.000 89,580 89,580
BID ITEM = 416 CLIENT# = 416 Land Item SCHEDULE: 1 100 Description = PEDESTRIAN PUSH-BUTTON POST Unit = EA Takeoff Quan: 112.000 Engr Quan: 112.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 416 CLIENT# = 416 Land Item SCHEDULE: 1 100 Description = PEDESTRIAN PUSH-BUTTON POST Unit = EA Takeoff Quan: 112.000 Engr Quan: 112.000
416.01 PEDESTRIAN PUSH-BUTTON POST Quan: 112.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 112.00 EA 1,100.000 123,200 123,200
BID ITEM = 417 CLIENT# = 417 Land Item SCHEDULE: 1 100 Description = PEDESTRIAN PUSH-BUTTON, BRIDGE MOUNT Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
417.01 PEDESTRIAN PUSH-BUTTON, BRIDGE MOUNT Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 5.00 EA 400.000 2,000 2,000
BID ITEM = 418 CLIENT# = 418 Land Item SCHEDULE: 1 100 Description = FOUNDATION, JOINT SIGNAL CONTROLLER/SERV Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
418.01 FOUNDATION, JOINT SIGNAL CONTROLLER/SE Quan: 21.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 21.00 EA 6,380.000 133,980 133,980
BID ITEM = 419 CLIENT# = 419 Land Item SCHEDULE: 1 100 Description = FOUNDATION, TRAFFIC SIGNAL CONTROL. CAB. Unit = EA Takeoff Quan: 11.000 Engr Quan: 11.000
419.01 FOUNDATION, TRAFFIC SIGNAL CONTROL. CA Quan: 11.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 11.00 EA 4,110.000 45,210 45,210
BID ITEM = 420 CLIENT# = 420 Land Item SCHEDULE: 1 100 Description = FOUNDATION, SERVICE CABINET Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
420.01 FOUNDATION, SERVICE CABINET Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 4.00 EA 4,100.000 16,400 16,400
BID ITEM = 421 CLIENT# = 421 Land Item SCHEDULE: 1 100 Description = FOUNDATION, SERVICE CABINET WITH STEP- D Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
421.01 FOUNDATION, SERVICE CABINET WITH STEP- Quan: 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 5.00 EA 4,100.000 20,500 20,500
BID ITEM | [5 empty] | = |  | 422 |  |  |  |  | CLIENT# = 422 | [15 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | FOUNDATION, |  |  |  |  | POLE TYPE T | [15 empty] | Unit = EA Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 422 CLIENT# = 4 FOUNDATION, POLE TYPE T | [16 empty] | 22 Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
422.01 | [5 empty] | FOUNDATION, POLE TYPE T | [16 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 4,800.000 4,800 4,800
BID ITEM = 423 CLIENT# = 423 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE TYPE X Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 EA 4,800.000 4,800 4,800
BID ITEM = 424 CLIENT# = 424 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE TYPE Z Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 EA 7,500.000 7,500 7,500
BID ITEM = 425 CLIENT# = 425 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE PEDESTRIAN LIGHTING Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
425.01 FOUNDATION, POLE PEDESTRIAN LIGHTING Quan: 30.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 30.00 EA 2,370.000 71,100 71,100
BID ITEM = 426 CLIENT# = 426 Land Item SCHEDULE: 1 100 Description = FOUNDATION, STREET LIGHT POLE Unit = EA Takeoff Quan: 20.000 Engr Quan: 20.000
4ELEC Electrical sub 1.00 20.00 EA 4,820.000 96,400 96,400
BID ITEM = 427 CLIENT# = 427 Land Item SCHEDULE: 1 100 Description = FOUNDATION, PEDESTAL Unit = EA Takeoff Quan: 55.000 Engr Quan: 55.000
4ELEC Electrical sub 1.00 55.00 EA 2,400.000 132,000 132,000
BID ITEM = 428 CLIENT# = 428 Land Item SCHEDULE: 1 100 Description = FOUNDATION, PEDESTRIAN PUSH BUTTON POST Unit = EA Takeoff Quan: 112.000 Engr Quan: 112.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 428 CLIENT# = 428 Land Item SCHEDULE: 1 100 Description = FOUNDATION, PEDESTRIAN PUSH BUTTON POST Unit = EA Takeoff Quan: 112.000 Engr Quan: 112.000
428.01 FOUNDATION, PEDESTRIAN PUSH BUTTON POS Quan: 112.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 112.00 EA 1,400.000 156,800 156,800
BID ITEM = 429 CLIENT# = 429 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE, MAST ARM 30 FT & LESS Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
429.01 FOUNDATION, POLE, MAST ARM 30 FT & LESS Quan: 21.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 21.00 EA 2,910.000 61,110 61,110
BID ITEM = 430 CLIENT# = 430 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE, MAST ARM 31 FT TO 40 F Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
430.01 FOUNDATION, POLE, MAST ARM 31 FT TO 40 F Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 10.00 EA 4,200.000 42,000 42,000
BID ITEM = 431 CLIENT# = 431 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE, MAST ARM 41 FT TO 50 F Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
431.01 FOUNDATION, POLE, MAST ARM 41 FT TO 50 F Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 4,200.000 4,200 4,200
BID ITEM = 432 CLIENT# = 432 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE DOUBLE MAST ARM Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
432.01 FOUNDATION, POLE DOUBLE MAST ARM Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 4,200.000 4,200 4,200
BID ITEM = 433 CLIENT# = 433 Land Item SCHEDULE: 1 100 Description = REMOVE FOUNDATION OBSTRUCTIONS Unit = FA Takeoff Quan: 92,000.000 Engr Quan: 92,000.000
433.01 REMOVE FOUNDATION OBSTRUCTIONS Quan: 92,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE |  |  |  | FORCE ACCOUNT | [15 empty] | 1.00 92,000.00 FA | [10 empty] | 0.89 | [6 empty] | 81880 | [14 empty] | 81880
=====> |  |  |  | Item Totals: | [6 empty] | 433 |  |  | - REMOVE FOUNDATION OBSTRUCTIONS
81880 | [13 empty] | [ ] | [23 empty] | 81880 | [14 empty] | 81880
0.89 | [13 empty] | 92000 FA | [23 empty] | 0.89 | [14 empty] | 0.89
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 434 CLIENT# = 434 Land Item SCHEDULE: 1 100 Description = TEMPORARY POLE SUPPORT Unit = FA Takeoff Quan: 18,000.000 Engr Quan: 18,000.000
434.01 TEMPORARY POLE SUPPORT Quan: 18,000.00 FA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
9FORCE FORCE ACCOUNT 1.00 18,000.00 FA 0.890 16,020 16,020
=====> Item Totals: 434 - TEMPORARY POLE SUPPORT $16,020.00 [ ] 16,020 16,020 0.890 18000 FA 0.89 0.89
BID ITEM = 435 CLIENT# = 435 Land Item SCHEDULE: 1 100 Description = GROUT EXISTING POLE Unit = FA Takeoff Quan: 20,000.000 Engr Quan: 20,000.000
| 435.01 |  |  |  |  | GROUT EXISTING POLE | [24 empty] | Quan: |  |  | 20,000.00 FA | [7 empty] | Hrs/Shft: | [6 empty] | 10.00 Cal: 510 |  |  |  |  | WC: WAAVG
| 9FORCE |  |  |  |  | FORCE ACCOUNT | [13 empty] | 1 |  |  | 20,000.00 FA | [10 empty] | 0.89 | [14 empty] | 17800 | [7 empty] | 17800
=====> Item Totals: | [11 empty] | 435 |  | - GROUT EXISTING POLE
17800 | [30 empty] | [ ] | [6 empty] | 17800 | [14 empty] | 17800
0.89 | [13 empty] | 20000 FA | [23 empty] | 0.89 | [14 empty] | 0.89
BID ITEM = 436 CLIENT# = 436 Land Item SCHEDULE: 1 100 Description = INSTALL POLE, KCM SA-201X/SA-201X(C), OW Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
436.01 INSTALL POLE, KCM SA-201X/SA-201X(C), OW Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 2,000.000 4,000 4,000
BID ITEM = 437 CLIENT# = 437 Land Item SCHEDULE: 1 100 Description = INSTALL POLE, KCM SA-201Z/SA-201Z(C), OW Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
437.01 INSTALL POLE, KCM SA-201Z/SA-201Z(C), OW Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 8.00 EA 1,980.000 15,840 15,840
BID ITEM = 438 CLIENT# = 438 Land Item SCHEDULE: 1 100 Description = INSTALL POLE, KCM SA-201ZZ, OWNER FURNIS Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
438.02 INSTALL POLE, KCM SA-201ZZ, OWNER FURNIS Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 8.00 EA 1,980.000 15,840 15,840
BID ITEM = 439 CLIENT# = 439 Land Item SCHEDULE: 1 100 Description = INSTALL POLE, KCM SA-201ZZZ, OWNER FURNI Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
439.01 INSTALL POLE, KCM SA-201ZZZ, OWNER FURNI Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 439 CLIENT# = 439 Land Item SCHEDULE: 1 100 Description = INSTALL POLE, KCM SA-201ZZZ, OWNER FURNI Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000 4ELEC Electrical sub 1.00 3.00 EA 1,970.000 5,910 5,910
BID ITEM = 440 CLIENT# = 440 Land Item SCHEDULE: 1 100 Description = CHIEF SEATTLE BASE AND COLLAR, CAST ALUM Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
440.01 CHIEF SEATTLE BASE AND COLLAR, CAST ALU Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 2.00 EA 22,050.000 44,100 44,100
BID ITEM = 441 CLIENT# = 441 Land Item SCHEDULE: 1 100 Description = CHIEF SEATTLE BASE AND COLLAR, CAST ALUM Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
441.01 CHIEF SEATTLE BASE AND COLLAR, CAST ALU Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 4.00 EA 22,050.000 88,200 88,200
BID ITEM = 442 CLIENT# = 442 Land Item SCHEDULE: 1 100
Description = |  |  | BRACKET ARM, 15 FT | [23 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
442.01 |  |  | BRACKET ARM, 15 FT | [23 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC |  |  | Electrical sub | [10 empty] | 1 |  |  | 1.00 EA | [9 empty] | 1,500.000 1,500 1,500
BID ITEM = 443 CLIENT# = 443 Land Item SCHEDULE: 1 100 Description = ALADDIN BRACKET ARM ASSEMBLY, 8 FT Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
4ELEC Electrical sub 1.00 4.00 EA 2,550.000 10,200 10,200
BID ITEM = 444 CLIENT# = 444 Land Item SCHEDULE: 1 100 Description = BRACKET ARM, 6 FT, STEEL Unit = EA Takeoff Quan: 14.000 Engr Quan: 14.000
4ELEC Electrical sub 1.00 14.00 EA 690.000 9,660 9,660
BID ITEM = 445 CLIENT# = 445 Land Item SCHEDULE: 1 100
Description = |  |  | BRACKET ARM, 8 FT, STEEL | [23 empty] | Unit = |  |  | EA Takeoff Quan: 69.000 Engr Quan: 69.000
445.01 |  |  | BRACKET ARM, 8 FT, STEEL | [23 empty] | Quan: |  |  | 69.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 69.00 EA 780.000 53,820 53,820
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 446 CLIENT# = 446 Land Item SCHEDULE: 1 100 BRACKET ARM, 10 FT, STEEL Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
446.01 | [5 empty] | BRACKET ARM, 10 FT, STEEL | [16 empty] | Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 4.00 EA 900.000 3,600 3,600
BID ITEM = 447 CLIENT# = 447 Land Item SCHEDULE: 1 100 Description = BRACKET ARM, 12 FT, STEEL Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
4ELEC Electrical sub 1.00 4.00 EA 1,280.000 5,120 5,120
BID ITEM = 448 CLIENT# = 448 Land Item SCHEDULE: 1 100 Description = FOUNDATION, BICYCLE PUSHBUTTON POST Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
4ELEC Electrical sub 1.00 3.00 EA 1,400.000 4,200 4,200
BID ITEM = 449 CLIENT# = 449 Land Item SCHEDULE: 1 100 Description = BICYCLE PUSHBUTTON POST Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
4ELEC Electrical sub 1.00 3.00 EA 1,170.000 3,510 3,510
BID ITEM = 450 CLIENT# = 450 Land Item SCHEDULE: 1 100 Description = FOUNDATION, POLE, JU/STEEL MAST ARM Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
4ELEC Electrical sub 1.00 30.00 EA 8,370.000 251,100 251,100
BID ITEM = 451 CLIENT# = 451 Land Item SCHEDULE: 1 100 Description = POLE, KCM SA-201X/SA-201X(C) Unit = EA Takeoff Quan: 26.000 Engr Quan: 26.000
4ELEC Electrical sub 1.00 26.00 EA 17,170.000 446,420 446,420
BID ITEM = 452 CLIENT# = 452 Land Item SCHEDULE: 1 100 Description = POLE, KCM SA-201Z/SA-201Z(C) Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000
Activity Desc Resource Pcs | [23 empty] | Quantity |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 452 CLIENT# = 45 POLE, KCM SA-201Z/SA-201Z(C) | [17 empty] | 2 Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000
451.01 | [5 empty] | POLE, KCM SA-201Z/SA-201Z(C) | [17 empty] | Quan: 22.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 22.00 EA 23,380.000 514,360 514,360
BID ITEM = 453 CLIENT# = 453 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | POLE, KCM SA-201ZZ | [16 empty] | Unit = EA Takeoff Quan: 32.000 Engr Quan: 32.000
| 453.01 |  |  |  |  | POLE, KCM SA-201ZZ | [16 empty] | Quan: 32.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 32.00 EA 26,910.000 861,120 861,120
BID ITEM = 454 CLIENT# = 454 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | POLE, KCM SA-201ZZZ | [16 empty] | Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
| 454.01 |  |  |  |  | POLE, KCM SA-201ZZZ | [16 empty] | Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 10.00 EA 34,630.000 346,300 346,300
BID ITEM = 455 CLIENT# = 455 Land Item SCHEDULE: 1 100 Description = FOUNDATION, KCM SA-213D Unit = EA Takeoff Quan: 26.000 Engr Quan: 26.000
4ELEC Electrical sub 1.00 26.00 EA 4,670.000 121,420 121,420
BID ITEM = 456 CLIENT# = 456 Land Item SCHEDULE: 1 100 Description = FOUNDATION, KCM SA-213F Unit = EA Takeoff Quan: 41.000 Engr Quan: 41.000
4ELEC Electrical sub 1.00 41.00 EA 7,360.000 301,760 301,760
BID ITEM = 457 CLIENT# = 457 Land Item SCHEDULE: 1 100 Description = FOUNDATION, KCM SA-213H Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
4ELEC Electrical sub 1.00 8.00 EA 12,510.000 100,080 100,080
BID ITEM = 458 CLIENT# = 458 Land Item SCHEDULE: 1 100 Description = OFFSET FOUNDATION, KCM SA-211 Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
Activity |  |  | Desc | [13 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 458 CLIENT# = 458 Land Item SCHEDULE: 1 100 Description = OFFSET FOUNDATION, KCM SA-211 Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
458.01 OFFSET FOUNDATION, KCM SA-211 Quan: 4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 4.00 EA 6,200.000 24,800 24,800
BID ITEM = 459 CLIENT# = 459 Land Item SCHEDULE: 1 100 Description = PEDESTAL, ALUMINUM, 20 FT Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
459.01 PEDESTAL, ALUMINUM, 20 FT Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 6,500.000 6,500 6,500
BID ITEM = 460 CLIENT# = 460 Land Item SCHEDULE: 1 100 Description = OFFSET FOUNDATION, POLE, JU/STEEL MAST A Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
460.01 OFFSET FOUNDATION, POLE, JU/STEEL MAST Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 7,500.000 7,500 7,500
BID ITEM = 461 CLIENT# = 461 Land Item SCHEDULE: 1 100 Description = INSTALL MAST ARM, 30 FT AND LESS, OWNER Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
461.01 INSTALL MAST ARM, 30 FT AND LESS, OWNER Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 EA 1,300.000 1,300 1,300
BID ITEM = 462 CLIENT# = 462 Land Item SCHEDULE: 1 100 Description = CONDUIT, PVC, 1 IN Unit = LF Takeoff Quan: 1,950.000 Engr Quan: 1,950.000
462.01 CONDUIT, PVC, 1 IN Quan: 1,950.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1,950.00 LF 11.600 22,620 22,620
BID ITEM = 463 CLIENT# = 463 Land Item SCHEDULE: 1 100 Description = CONDUIT, PVC, 2 IN Unit = LF Takeoff Quan: 41,694.000 Engr Quan: 41,694.000
463.01 CONDUIT, PVC, 2 IN Quan: 41,694.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 41,694.00 LF 13.600 567,038 567,038
BID ITEM = 464 CLIENT# = 464 Land Item SCHEDULE: 1 100 Description = CONDUIT, PVC, 3 IN Unit = LF Takeoff Quan: 62,883.000 Engr Quan: 62,883.000
Activity Desc Resource | [17 empty] | Pcs |  |  |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 464 CLIE CONDUIT, PVC, 3 IN | [11 empty] | NT# = |  |  |  |  | 464 Land Item SCHEDULE: 1 100 Unit = LF Takeoff Quan: 62,883.000 Engr Quan: 62,883.000
464.01 | [5 empty] | CONDUIT, PVC, 3 IN | [16 empty] | Quan: 62,883.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [11 empty] | 1 |  |  |  |  | 62,883.00 LF 21.300 1,339,408 1,339,408
BID ITEM = 465 CLIENT# = 465 Land Item SCHEDULE: 1 100 Description = CONDUIT, PVC, 4 IN Unit = LF Takeoff Quan: 382.000 Engr Quan: 382.000
| 465.01 |  |  |  |  | CONDUIT, PVC, 4 IN | [24 empty] | Quan: |  |  | 382.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 382.00 LF | [10 empty] | 33 | [8 empty] | 12,606 12,606
BID ITEM = 466 CLIENT# = 466 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 3/4 IN Unit = LF Takeoff Quan: 130.000 Engr Quan: 130.000
| 466.01 |  |  |  |  | CONDUIT, RGS, 3/4 IN | [24 empty] | Quan: |  |  | 130.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 130.00 LF | [10 empty] | 34.6 | [8 empty] | 4,498 4,498
BID ITEM = 467 CLIENT# = 467 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 1 IN Unit = LF Takeoff Quan: 1,800.000 Engr Quan: 1,800.000
| 467.01 |  |  |  |  | CONDUIT, RGS, 1 IN | [24 empty] | Quan: |  |  | 1,800.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 1,800.00 LF | [10 empty] | 19.8 | [8 empty] | 35,640 35,640
BID ITEM = 468 CLIENT# = 468 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 2 IN Unit = LF Takeoff Quan: 3,835.000 Engr Quan: 3,835.000
| 468.01 |  |  |  |  | CONDUIT, RGS, 2 IN | [24 empty] | Quan: |  |  | 3,835.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 3,835.00 LF | [10 empty] | 32.8 | [8 empty] | 125,788 125,788
BID ITEM = 469 CLIENT# = 469 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 3 IN Unit = LF Takeoff Quan: 865.000 Engr Quan: 865.000
| 469.01 |  |  |  |  | CONDUIT, RGS, 3 IN | [24 empty] | Quan: |  |  | 865.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 865.00 LF | [10 empty] | 60.8 | [8 empty] | 52,592 52,592
BID ITEM = 470 CLIENT# = 470 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 4 IN Unit = LF Takeoff Quan: 20.000 Engr Quan: 20.000
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 470 CLIENT# = 470 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 4 IN Unit = LF Takeoff Quan: 20.000 Engr Quan: 20.000
470.01 CONDUIT, RGS, 4 IN Quan: 20.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 20.00 LF 160.000 3,200 3,200
BID ITEM = 471 CLIENT# = 471 Land Item SCHEDULE: 1 100 Description = TRENCHING, SCL SERVICE, CONDUIT Unit = LF Takeoff Quan: 1,805.000 Engr Quan: 1,805.000
471.01 | [5 empty] | TRENCHING, SCL SERVICE, CONDUIT | [24 empty] | Quan: |  |  | 1,805.00 LF | [8 empty] | Hrs/Shft: | [5 empty] | 10 |  |  | Cal: 610 |  | WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 1,805.00 LF | [7 empty] | 0.001 | [11 empty] | 2 | [13 empty] | 2
4TREN | [5 empty] | TRENCHING SUB | [13 empty] | 1 |  |  | 1,805.00 LF | [7 empty] | 27.75 | [11 empty] | 50089 | [13 empty] | 50089
50090.56 | [30 empty] | [ ] | [11 empty] | 50091 | [13 empty] | 50091
=====> Item Totals: | [10 empty] | 471 |  |  | - TRENCHING, SCL SERVICE, CONDUIT
50090.56 | [13 empty] | [ ] | [23 empty] | 50091 | [18 empty] | 50091
27.751 | [13 empty] | 1805 LF | [23 empty] | 27.75 | [18 empty] | 27.75
BID ITEM = 472 CLIENT# = 472 Land Item SCHEDULE: 1 100 Description = TRENCHING, SDOT, CONDUIT Unit = LF Takeoff Quan: 26,891.000 Engr Quan: 26,891.000
172.01 TRENCHING, SDOT, CONDUIT Quan: 26,891.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
4TREN TRENCHING SUB 1.00 26,891.00 LF 27.750 746,225 746,225
BID ITEM = 473 CLIENT# = 473 Land Item SCHEDULE: 1 100 Description = TRENCHING, SCL LIGHTING, CONDUIT Unit = LF Takeoff Quan: 10,485.000 Engr Quan: 10,485.000
473.01 TRENCHING, SCL LIGHTING, CONDUIT Quan: 10,485.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 10,485.00 LF | [7 empty] | 0.001 | [6 empty] | 10 | [18 empty] | 10
4TREN | [5 empty] | TRENCHING SUB | [13 empty] | 1 |  |  | 10,485.00 LF | [7 empty] | 27.75 | [6 empty] | 290959 | [18 empty] | 290959
290969.24 | [30 empty] | [ ] | [6 empty] | 290969 | [18 empty] | 290969
=====> Item Totals: | [10 empty] | 473 |  |  | - TRENCHING, SCL LIGHTING, CONDUIT
290969.24 | [13 empty] | [ ] | [23 empty] | 290969 | [18 empty] | 290969
27.751 | [13 empty] | 10485 LF | [23 empty] | 27.75 | [18 empty] | 27.75
BID ITEM = 474 CLIENT# = 474 Land Item SCHEDULE: 1 100 Description = TRENCHING, SDOT/SCL LIGHTING, CONDUIT Unit = LF Takeoff Quan: 1,150.000 Engr Quan: 1,150.000
474.01 | [5 empty] | TRENCHING, SDOT/SCL LIGHTING, CONDUIT | [24 empty] | Quan: |  |  | 1,150.00 LF | [8 empty] | Hrs/Shft: | [5 empty] | 10 |  |  | Cal: 610 |  | WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [9 empty] | 1 | [6 empty] | 1,150.00 LF | [7 empty] | 0.001 | [11 empty] | 1 | [13 empty] | 1
4TREN | [5 empty] | TRENCHING SUB | [9 empty] | 1 | [6 empty] | 1,150.00 LF | [7 empty] | 27.75 | [11 empty] | 31913 | [13 empty] | 31913
31913.65 | [30 empty] | [ ] | [11 empty] | 31914 | [13 empty] | 31914
=====> Item Totals: $31,913.65 | [10 empty] | 474 |  |  |  |  | - TRENCHING, SDOT/SCL LIGHTING, CONDUIT [ ] | [26 empty] | 31914 | [13 empty] | 31914
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 474 CLIENT# = 474 Land Item SCHEDULE: 1 100 Description = TRENCHING, SDOT/SCL LIGHTING, CONDUIT Unit = LF Takeoff Quan: 1,150.000 Engr Quan: 1,150.000 27.751 1150 LF 27.75 27.75
BID ITEM | [5 empty] | = |  | 475 | [5 empty] | CLIENT# = | [8 empty] | 475 | [5 empty] | Land Item SCHEDULE: 1 100
Description = | [5 empty] | TRENCHING, KCM, CONDUIT | [16 empty] | Unit = LF Takeoff Quan: 4,309.000 Engr Quan: 4,309.000
475.01 | [5 empty] | TRENCHING, KCM, CONDUIT | [16 empty] | Quan: 4,309.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
4TREN TRENCHING SUB 1.00 4,309.00 LF 27.750 119,575 119,575
BID ITEM = 476 CLIENT# = 476 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | CONDUIT RISER, 2 IN | [24 empty] | Unit = EA Takeoff Quan: 6.000 Engr Quan: 6.000
| 476.01 |  |  |  |  | CONDUIT RISER, 2 IN | [24 empty] | Quan: 6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 6.00 EA | [7 empty] | 1,200.000 7,200 7,200
BID ITEM = 477 CLIENT# = 477 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | CONDUIT RISER, 3 IN | [24 empty] | Unit = EA Takeoff Quan: 48.000 Engr Quan: 48.000
| 477.01 |  |  |  |  | CONDUIT RISER, 3 IN | [24 empty] | Quan: 48.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 48.00 EA | [7 empty] | 1,790.000 85,920 85,920
BID ITEM = 478 CLIENT# = 478 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 1 | [24 empty] | Unit = EA Takeoff Quan: 11.000 Engr Quan: 11.000
| 478.01 |  |  |  |  | HANDHOLE, TYPE 1 | [24 empty] | Quan: 11.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 11.00 EA | [7 empty] | 1,090.000 11,990 11,990
BID ITEM = 479 CLIENT# = 479 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 2 | [24 empty] | Unit = EA Takeoff Quan: 235.000 Engr Quan: 235.000
| 479.01 |  |  |  |  | HANDHOLE, TYPE 2 | [24 empty] | Quan: 235.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 235.00 EA | [7 empty] | 1,490.000 350,150 350,150
BID ITEM = 480 CLIENT# = 480 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 3 | [24 empty] | Unit = |  |  | EA Takeoff Quan: 177.000 Engr Quan: 177.000
| 480.01 |  |  |  |  | HANDHOLE, TYPE 3 | [24 empty] | Quan: |  |  | 177.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 177.00 EA 2,980.000 527,460 527,460
Activity Desc Resource | [19 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM = 481 CLIENT# = 481 Land Item SCHEDULE: 1 100
Description = | [5 empty] | HANDHOLE, TYPE 5 | [24 empty] | Unit = EA Takeoff Quan: 145.000 Engr Quan: 145.000
481.01 | [5 empty] | HANDHOLE, TYPE 5 | [24 empty] | Quan: 145.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 145.00 EA | [7 empty] | 3,030.000 439,350 439,350
BID ITEM = 482 CLIENT# = 482 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 6 | [24 empty] | Unit = EA Takeoff Quan: 11.000 Engr Quan: 11.000
| 482.01 |  |  |  |  | HANDHOLE, TYPE 6 | [24 empty] | Quan: 11.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 11.00 EA | [7 empty] | 4,630.000 50,930 50,930
BID ITEM = 483 CLIENT# = 483 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 2R | [24 empty] | Unit = EA Takeoff Quan: 30.000 Engr Quan: 30.000
| 483.01 |  |  |  |  | HANDHOLE, TYPE 2R | [24 empty] | Quan: 30.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 30.00 EA | [7 empty] | 1,640.000 49,200 49,200
BID ITEM = 484 CLIENT# = 484 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 3R | [24 empty] | Unit = EA Takeoff Quan: 16.000 Engr Quan: 16.000
| 484.01 |  |  |  |  | HANDHOLE, TYPE 3R | [24 empty] | Quan: 16.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 16.00 EA | [7 empty] | 3,150.000 50,400 50,400
BID ITEM = 485 CLIENT# = 485 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HANDHOLE, TYPE 5R | [24 empty] | Unit = EA Takeoff Quan: 16.000 Engr Quan: 16.000
| 485.01 |  |  |  |  | HANDHOLE, TYPE 5R | [24 empty] | Quan: 16.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 4ELEC |  |  |  |  | Electrical sub | [13 empty] | 1 |  |  | 16.00 EA | [7 empty] | 3,810.000 60,960 60,960
BID ITEM = 486 CLIENT# = 486 Land Item SCHEDULE: 1 100 Description = LID, HANDHOLE, TYPE 6 Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
4ELEC Electrical sub 1.00 5.00 EA 2,800.000 14,000 14,000
BID ITEM = 487 CLIENT# = 487 Land Item SCHEDULE: 1 100 Description = LID, HANDHOLE, TYPE 5 Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 487 CLIENT# = 487 Land Item SCHEDULE: 1 100 Description = LID, HANDHOLE, TYPE 5 Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
4ELEC Electrical sub 1.00 4.00 EA 2,150.000 8,600 8,600
BID ITEM = 488 CLIENT# = 488 Land Item SCHEDULE: 1 100 Description = CONDUIT ENCASEMENT SYSTEM Unit = LF Takeoff Quan: 458.000 Engr Quan: 458.000
4ELEC Electrical sub 1.00 458.00 LF 125.000 57,250 57,250
BID ITEM = 489 CLIENT# = 489 Land Item SCHEDULE: 1 100 Description = CONDUIT, RGS, 3 IN, AREAWAY Unit = LF Takeoff Quan: 20.000 Engr Quan: 20.000
4ELEC Electrical sub 1.00 20.00 LF 140.000 2,800 2,800
BID ITEM = 490 CLIENT# = 490 Land Item SCHEDULE: 1 100 Description = UTILITY VAULT 7' 2"X 4' 10" X 5' 2" Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 EA 13,000.000 13,000 13,000
BID ITEM = 491 CLIENT# = 491 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM SPRING AND 3RD AVENUE E Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1680
491.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 110.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 110.00 SF | [10 empty] | 13.850 1
,680
Hrs/Shft: 10.00
491.02 | [5 empty] | WHEEL GUID | [24 empty] | Quan: |  |  | 55.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 55.00 LF 109.260 6,625 6,625 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 6,625 7,741
7741.42 |  |  | 0.2909 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 16.931 ]
491.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 8.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1069 | [56 empty] | 1069
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
9329.36 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [7 empty] | [ 6932.29 ] | [8 empty] | 8261 |  |  |  |  | 1069 | [7 empty] | 9329
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 491 CLIENT# = 491 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | STATION PLATFORM SPRING AND 3RD AVENUE E | [23 empty] | Unit = LS
491.04 |  |  | SIDEWALKS | [23 empty] | Quan: 30.0
COM 2CR040 |  |  | Concrete 6 Man Crew 8.00 4000LB READY M@110.2 1.00 11.00 CY | [23 empty] | CH Pro 121.150
d:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1469 | [56 empty] | 1469
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
5599.65 | [5 empty] | 1.6000 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 115.538 ] | [8 empty] | 4130 |  |  |  |  | 1469 | [7 empty] | 5600
491.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
491.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500 | [10 empty] | 500 | [14 empty] | 500
491.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: |  |  | 122.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122 | [10 empty] | 2.000 269 269
=====> Item Totals: 491 - S $29,383.07 208.0000 MH/LS | [19 empty] | TATION PLATFORM SPRING AND 3RD AVENUE E 208.00 MH [ 14795.79 ] 17,638 11,245 500 29,383
29383.07 | [5 empty] | 1 LS | [24 empty] | 17,637.79 11,245.28 500.00 29,383.07
:
BID ITEM = 492 CLIENT# = 492 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM SPRING AND 4TH AVENUE E Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1924
492.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 126.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 126.00 SF | [10 empty] | 13.850 1
,924
Hrs/Shft: 10.00
492.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 64.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 64.00 LF 109.260 7,709 7,709 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,709 8,826
8825.56 |  |  | 0.2500 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 14.55 ]
492.03 |  |  | STATION FOUNDATION | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 12.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1603 | [56 empty] | 1603
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9863.63 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1603 | [7 empty] | 9864
492.04 | [5 empty] | SIDEWALKS | [24 empty] | Quan: |  |  | 45.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 11.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,469 1,469
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
Activity Desc Resource Pcs | [16 empty] | Quantity | [5 empty] | Unit |  |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  |  | Total
BID ITEM = 492 CLIENT# = 492 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM SPRING AND 4TH AVENUE E Unit = LS Takeoff Quan: 1.000 | [49 empty] | Engr Quan: |  |  |  |  | 1
$5,599.65 1.0666 MH/SY 48.00 MH [ 77.025 ] 4,130 1,469 | [54 empty] | 5600
492.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
Prod: 121.150
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
492.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
492.07 | [5 empty] | LEAN RAIL | [24 empty] | Quan: 6.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 2 |  | Eqp Pcs: |  | 0
1169 | [56 empty] | 1169
ZZZZ SITE FURNISHINGS CREW 8.00 CH Prod:
2LEAN | [5 empty] | LEAN RAIL@110.25% | [13 empty] | 1 |  |  | 6.00 LF | [7 empty] | 176.77
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [7 empty] | 52.91
2285.5 | [5 empty] | 2.6666 MH/LF | [16 empty] | 16.00 MH | [7 empty] | [ 155.203 ]
1116 | [52 empty] | 1116
1116 | [44 empty] | 1169 | [7 empty] | 2286
492.08 REBAR PURCHASE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 43 | [7 empty] | 1.5 | [8 empty] | 71 | [12 empty] | 71
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [8 empty] | 269 | [12 empty] | 269
340.12 | [30 empty] | [ ] | [8 empty] | 340 | [12 empty] | 340
=====> Item Totals: 492 - STATION PLATFORM SPRING AND 4TH AVENUE E 500 33,602 500.00 33,602.40
33602.4 | [5 empty] | 224.0000 MH/LS | [16 empty] | 224.00 MH | [7 empty] | [ 15727.01 ] | [6 empty] | 18754 | [6 empty] | 14348
33602.4 | [5 empty] | 1 LS | [31 empty] | 18753.96 | [6 empty] | 14348.44
BID ITEM = 493 CLIENT# = 493 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM SPRING AND 8TH AVENUE E Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1878
493.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 123.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 123.00 SF | [10 empty] | 13.850 1
,878
Hrs/Shft: 10.00
493.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 62.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 62.00 LF 109.260 7,468 7,468 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,468 8,585
8584.64 |  |  | 0.2580 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 15.02 ]
493.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 19.00 CY | [7 empty] | 24 |  | CH Pr 121.150
od:
24.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2538 | [56 empty] | 2538
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 120.00 MH | [5 empty] | 64.98 | [10 empty] | 10224 | [12 empty] | 10224
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 68.98 | [10 empty] | 2168 | [12 empty] | 2168
$14,929.01 144.0000 MH/LS 144.00 MH | [28 empty] | [ 10398.43 ] 12,391 2,538 14,929
493.04 | [5 empty] | SIDEWALKS | [24 empty] | Quan: |  |  | 26.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 8.10 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,082 1,082
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost | [5 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 493 CLIENT# = 493 Land Item STATION PLATFORM SPRING AND 8TH AVENUE E Unit = | [25 empty] | SCHEDULE: 1 LS Takeoff Quan: | [13 empty] | 100 |  |  | 1 |  | Engr Quan: |  |  |  | 1
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [10 empty] | 64.98 | [5 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 68.98 | [5 empty] | 723 | [10 empty] | 723
5212.3 | [5 empty] | 1.8461 MH/SY | [16 empty] | 48.00 MH | [10 empty] | [ 133.313 ] | [5 empty] | 4130 |  |  |  |  | 1082 | [5 empty] | 5212
493.05 FOUNDATION STEM WALL Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
Prod: 121.150
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
493.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
493.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2.000 269 269
=====> Item Totals: 493 - S $35,637.09 256.0000 MH/LS | [19 empty] | TATION PLATFORM SPRING AND 8TH AVENUE E 256.00 MH [ 18261.93 ] 21,768 13,369 500 35,637
35637.09 | [5 empty] | 1 LS | [24 empty] | 21,768.19 13,368.90 500.00 35,637.09
:
BID ITEM = 494 CLIENT# = 494 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 3RD AVENUE Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1527
494.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 100.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 100.00 SF | [10 empty] | 13.850 1
,527
Hrs/Shft: 10.00
494.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 56.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 56.00 LF 109.260 6,746 6,746 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 6,746 7,862
7861.88 |  |  | 0.2857 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 16.629 ]
494.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 6.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
801 | [56 empty] | 801
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
9062.23 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [7 empty] | [ 6932.29 ] | [8 empty] | 8261 |  |  |  |  | 801 | [7 empty] | 9062
494.04 SIDEWALKS Quan: 32.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 9.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1202 | [56 empty] | 1202
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [5 empty] | 64.98 | [10 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 68.98 | [10 empty] | 723 | [12 empty] | 723
5332.51 | [5 empty] | 1.5000 MH/SY | [16 empty] | 48.00 MH | [5 empty] | [ 108.317 ] | [10 empty] | 4130 |  |  |  |  | 1202 | [7 empty] | 5333
494.05 | [5 empty] | FOUNDATION STEM WALL | [24 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [16 empty] | 8 | [7 empty] | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [11 empty] | Equip Sub- Ment Contract |  |  | Total
BID ITEM Description = |  |  |  |  | = |  |  | 494 CLIENT# = 494 Land Item STATION PLATFORM MADISON AND 3RD AVENUE Unit = | [25 empty] | SCHEDULE: 1 100 LS Takeoff Quan: | [17 empty] | 1 |  | Engr Quan: |  |  | 1
2CR040 | [7 empty] | 4000LB READY M@110.2 1.00 2.20 CY | [25 empty] | 121.150 294 | [22 empty] | 294
CEJ |  |  |  |  | Cement Mason | [14 empty] | 5 |  |  | 40.00 MH | [10 empty] | 64.98 | [7 empty] | 3408 | [9 empty] | 3408
FOCO |  |  |  |  | Concrete Forman | [14 empty] | 1 |  |  | 8.00 MH | [10 empty] | 68.98 | [7 empty] | 723 | [9 empty] | 723
4424.25 |  |  |  |  | 48.0000 MH/LS | [17 empty] | 48.00 MH [ | [10 empty] | 3466.14 ] | [7 empty] | 4130 |  |  |  |  | 294 |  |  |  |  | 4424
494.06 |  |  |  |  | STATION CHANALIZATION | [17 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI |  |  |  |  | Striping sub | [14 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
494.07 |  |  |  |  | REBAR PURCHASE | [25 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 |  |  |  |  | #4 REBAR@110.25% | [14 empty] | 1 |  |  | 48.00 LF | [7 empty] | 1.5 | [10 empty] | 79 | [9 empty] | 79
2RB5 |  |  |  |  | #5 REBAR@110.25% | [14 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [9 empty] | 269
348.39 | [30 empty] | [ ] | [10 empty] | 348 | [9 empty] | 348
=====> Ite $29,056.22 |  |  |  |  | m Totals: 494 - S 208.0000 MH/LS | [14 empty] | TATION PLATFORM MADISON AND 3RD AVENUE 208.00 MH [ 14795.79 ] 17,638 10,918 500 29,056
29056.22 |  |  |  |  | 1 LS | [25 empty] | 17,637.79 10,918.43 500.00 29,056.22
:
BID ITEM = 495 CLIENT# = 495 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 5TH AVENUE Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1787
495.01 | [5 empty] | TRUNCATED DOME | [24 empty] | Quan: |  |  | 117.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 117.00 SF | [10 empty] | 13.850 1
,787
Hrs/Shft: 10.00
495.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 62.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 62.00 LF 109.260 7,468 7,468 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,468 8,585
8584.64 |  |  | 0.2580 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 15.02 ]
495.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 9.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1202 | [56 empty] | 1202
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9462.93 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1202 | [7 empty] | 9463
495.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 111.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 20.00 CY | [5 empty] | 16 |  | CH |  |  | Prod: 16.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 2,671 2,671
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
10932.18 | [5 empty] | 0.8648 MH/SY | [16 empty] | 96.00 MH | [7 empty] | [ 62.453 ] | [8 empty] | 8261 |  |  |  |  | 2671 | [7 empty] | 10932
495.05 FOUNDATION STEM WALL Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [8 empty] | 4130 |  |  |  |  | 134 | [7 empty] | 4264
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 495 CLIENT# = 495 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 5TH AVENUE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
495.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
495.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 186.00 LF | [7 empty] | 2.000 410 410
=====> Item Totals: 495 - STATION PLATFORM MADISON AND 5TH AVENUE
35940.4 | [5 empty] | 256.0000 MH/LS | [13 empty] | 256.00 MH | [10 empty] | [ 18261.94 ] 21,768 13,672 500 35,940
35940.4 | [5 empty] | 1 LS | [24 empty] | 21,768.21 13,672.19 500.00 35,940.40
BID ITEM = 496 CLIENT# = 496 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 8TH AVENUE Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 2519
496.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 165.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 165.00 SF | [10 empty] | 13.850 2
,519
Hrs/Shft: 10.00
496.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 65.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 65.00 LF 109.260 7,830 7,830 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,830 8,946
8946.01 |  |  | 0.2461 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 14.326 ]
496.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 10.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1336 | [56 empty] | 1336
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
9596.5 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [7 empty] | [ 6932.29 ] | [8 empty] | 8261 |  |  |  |  | 1336 | [7 empty] | 9597
496.04 STATION SIDEWALKS Quan: 32.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 29.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
3873 | [56 empty] | 3873
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
8003.87 | [5 empty] | 1.5000 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 108.317 ] | [8 empty] | 4130 |  |  |  |  | 3873 | [7 empty] | 8004
496.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
496.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
496.07 | [5 empty] | ISLAND NOSING | [24 empty] | Quan: 6.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
:
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 496 CLIENT# = 496 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 8TH AVENUE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 5.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
668 | [56 empty] | 668
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [5 empty] | 64.98 | [12 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 68.98 | [12 empty] | 723 | [10 empty] | 723
4798.24 | [5 empty] | 8.0000 MH/SY | [16 empty] | 48.00 MH | [5 empty] | [ 577.69 ] | [12 empty] | 4130 |  |  | 668 | [7 empty] | 4798
496.08 ZZZZ | [5 empty] | BARRIER RAIL SITE FURNISHINGS CREW | [13 empty] | 8 | [10 empty] | Quan: CH |  |  | 87.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
25886 | [56 empty] | 25886
2BARE BARRIER RAIL@110.25% 1.00 87.00 LF 269.880
LAG General Laborer 2.00 | [22 empty] | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [10 empty] | 1116
$27,002.38 0.1839 MH/LF | [22 empty] | 16.00 MH | [5 empty] | [ 10.704 ] | [12 empty] | 1,116 25,886 | [10 empty] | 27002
496.09 ZZZZ | [5 empty] | BARRIER RAIL W HANDRAIL SITE FURNISHINGS CREW | [16 empty] | 8 | [7 empty] | Quan: CH |  |  | 32.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
10394 | [56 empty] | 10394
2BAREH BARRIER RAIL W@110.2 1.00 32.00 LF 294.610
LAG General Laborer 2.00 | [22 empty] | 16.00 MH | [7 empty] | 52.91 | [6 empty] | 1116 | [14 empty] | 1116
$11,510.01 0.5000 MH/LF | [22 empty] | 16.00 MH | [7 empty] | [ 29.101 ] | [6 empty] | 1,116 10,394 | [14 empty] | 11510
496.1 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 614.00 LF | [7 empty] | 1.5 | [6 empty] | 1015 | [14 empty] | 1015
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [6 empty] | 269 | [14 empty] | 269
1284.41 | [30 empty] | [ ] | [6 empty] | 1284 | [14 empty] | 1284
=====> Item Totals: 496 - STATION PLATFORM MADISON AND 8TH AVENUE
78424.88 | [5 empty] | 288.0000 MH/LS | [13 empty] | 288.00 MH | [10 empty] | [ 20124.37 ] | [6 empty] | 24001 | [6 empty] | 53,924 500 78,425
78424.88 | [5 empty] | 1 LS | [31 empty] | 24000.53 | [6 empty] | 53,924.35 500.00 78,424.88
BID ITEM = 497 CLIENT# = 497 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND TERRY AVENU Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
497.01 TRUNKATED DOME Quan: 192.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2TRUNK |  |  | TRUNKATED DOME@11 | [10 empty] | 1 |  |  | 192.00 SF | [12 empty] | 13.85 | [6 empty] | 2932 | [17 empty] | 2932
497.02 |  |  | WHEEL GUIDE | [23 empty] | Quan: |  |  | 200.00 LF | [6 empty] | Hrs/Shft: 10.00 | [8 empty] | Cal: 510 | [5 empty] | WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 24.00 CH Prod: 2WHEEL STATION WHEEL @110. 1.00 200.00 LF 109.260 LAG General Laborer $27,440.33 0.2400 MH/LF
24.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 2 |  | Eqp Pcs: |  | 0
24092 | [56 empty] | 24092
2 | [22 empty] | 48.00 MH | [7 empty] | 52.91 | [8 empty] | 3349 | [12 empty] | 3349
[23 empty] | 48.00 MH | [7 empty] | [ 13.968 ] | [8 empty] | 3,349 24,092 | [12 empty] | 27440
497.03 STATION FOUNDATIONS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 24 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 19.00 CY
24.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2538 | [56 empty] | 2538
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 120.00 MH | [5 empty] | 64.98 | [10 empty] | 10224 | [12 empty] | 10224
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 68.98 | [10 empty] | 2168 | [12 empty] | 2168
$14,929.01 144.0000 MH/LS 144.00 MH | [28 empty] | [ 10398.43 ] 12,391 2,538 14,929
497.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 97.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 31.00 CY | [5 empty] | 16 |  | CH |  |  | Prod: 16.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 4,141 4,141
Activity Desc Quantity Unit Perm Constr Equip Sub- Resource Pcs Unit Cost Labor Material Matl/Exp Ment Contract Total
BID ITEM = 497 CLIENT# = 497 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND TERRY AVENU Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 CEJ Cement Mason 5.00 80.00 MH 64.980 6,816 6,816 FOCO Concrete Forman 1.00 16.00 MH 68.980 1,445 1,445 $12,401.42 0.9896 MH/SY 96.00 MH [ 71.467 ] 8,261 4,141 12,401
497.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 8.00 CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 1.00 CY 121.150 134 134 CEJ Cement Mason 5.00 40.00 MH 64.980 3,408 3,408 FOCO Concrete Forman 1.00 8.00 MH 68.980 723 723 $4,263.97 48.0000 MH/LS 48.00 MH [ 3466.14 ] 4,130 134 4,264
497.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 1.00 LS 500.000 500 500
497.07 ISLAND NOSING Quan: 30.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 8.00 CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 10.00 CY 121.150 1,336 1,336 CEJ Cement Mason 5.00 40.00 MH 64.980 3,408 3,408 FOCO Concrete Forman 1.00 8.00 MH 68.980 723 723 $5,466.08 1.6000 MH/SY 48.00 MH [ 115.538 ] 4,130 1,336 5,466
497.08 LEANING RAIL Quan: 6.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW 4.00 CH Prod: 4.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00 2LEAN LEAN RAIL@110.25% 1.00 6.00 LF 176.770 1,169 1,169 LAG General Laborer 1.00 4.00 MH 52.910 279 279 $1,448.37 0.6666 MH/LF 4.00 MH [ 38.8 ] 279 1,169 1,448
497.09 BARRIER RAIL Quan: 158.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZ SIGN CREW 16.00 CH Prod: 16.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00 2BARE BARRIER RAIL@110.25% 1.00 158.00 LF 269.880 47,012 47,012 LAG General Laborer 1.00 16.00 MH 52.910 1,116 1,116 $48,127.92 0.1012 MH/LF 16.00 MH [ 5.894 ] 1,116 47,012 48,128
497.10 BARRIER RAIL WITH HANDRAIL Quan: 56.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 8.00 CH Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2BAREH BARRIER RAIL W@110.2 1.00 56.00 LF 294.610 18,189 18,189 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 $19,305.39 0.2857 MH/LF 16.00 MH [ 16.629 ] 1,116 18,189 19,305
497.11 REBAR PURCHASE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 #4 REBAR@110.25% 1.00 1,350.00 LF 1.500 2,233 2,233 2RB5 #5 REBAR@110.25% 1.00 308.00 LF 2.000 679 679 $2,911.70 [ ] 2,912 2,912
=====> Item Totals: 497 - STATION PLATFORM MADISON AND TERRY AVENU $139,725.96 420.0000 MH/LS 420.00 MH [ 29151.89 ] 34,773 104,453 500 139,726 139,725.960 1 LS 34,772.72 104,453.24 500.00 139,725.96
Activity Desc Quantity Unit Perm Constr Equip Sub- Resource Pcs Unit Cost Labor Material Matl/Exp Ment Contract Total
BID ITEM = 498 CLIENT# = 498 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND BOYLSTON AV Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
498.01 TRUNCATED DOMES Quan: 332.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2TRUNK TRUNKATED DOME@11 1.00 332.00 SF 13.850 5,070 5,070
498.02 WHEEL GUIDE Quan: 425.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 32.00 CH Prod: 32.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 425.00 LF 109.260 51,195 51,195 LAG General Laborer 2.00 64.00 MH 52.910 4,465 4,465 $55,659.80 0.1505 MH/LF 64.00 MH [ 8.764 ] 4,465 51,195 55,660
498.03 STATION FOUNDATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 32.00 CH Prod: 32.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 29.00 CY 121.150 3,873 3,873 CEJ Cement Mason 5.00 160.00 MH 64.980 13,632 13,632 FOCO Concrete Forman 1.00 32.00 MH 68.980 2,890 2,890 $20,395.10 192.0000 MH/LS 192.00 MH [ 13864.58 ] 16,522 3,873 20,395
498.04 STATION SIDEWALKS Quan: 248.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 24.00 CH Prod: 24.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 71.36 CY 121.150 9,531 9,531 CEJ Cement Mason 5.00 120.00 MH 64.980 10,224 10,224 FOCO Concrete Forman 1.00 24.00 MH 68.980 2,168 2,168 $21,922.62 0.5806 MH/SY 144.00 MH [ 41.929 ] 12,391 9,531 21,923
498.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 4.00 CH Prod: 4.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 1.00 CY 121.150 134 134 CEJ Cement Mason 5.00 20.00 MH 64.980 1,704 1,704 FOCO Concrete Forman 1.00 4.00 MH 68.980 361 361 $2,198.77 24.0000 MH/LS 24.00 MH [ 1733.07 ] 2,065 134 2,199
498.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 1.00 LS 500.000 500 500
498.07 ISLAND NOSING Quan: 12.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM Concrete 6 Man Crew 8.00 CH Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 2CR040 4000LB READY M@110.2 1.00 4.00 CY 121.150 534 534 CEJ Cement Mason 5.00 40.00 MH 64.980 3,408 3,408 FOCO Concrete Forman 1.00 8.00 MH 68.980 723 723 $4,664.67 4.0000 MH/SY 48.00 MH [ 288.845 ] 4,130 534 4,665
498.08 BARRIER RAIL Quan: 342.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 24.00 CH Prod: 24.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2BARE BARRIER RAIL@110.25% 1.00 342.00 LF 269.880 101,760 101,760 LAG General Laborer 2.00 48.00 MH 52.910 3,349 3,349 $105,108.10 0.1403 MH/LF 48.00 MH [ 8.169 ] 3,349 101,760 105,108
498.09 BARRIER RAIL W HANDRAIL Quan: 91.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 8.00 CH Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2BAREH BARRIER RAIL W@110.2 1.00 91.00 LF 294.610 29,557 29,557
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 498 CLIENT# = 498 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND BOYLSTON AV Unit = LS Takeoff Quan: 1.000 | [52 empty] | Engr Quan: |  |  |  | 1
LAG General Laborer 2.00 | [22 empty] | 16.00 MH | [7 empty] | 52.91 | [8 empty] | 1116 | [12 empty] | 1116
$30,673.65 0.1758 MH/LS | [22 empty] | 16.00 MH | [7 empty] | [ 10.233 ] | [8 empty] | 1,116 29,557 | [12 empty] | 30674
498.1 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 2,360.00 LF | [7 empty] | 1.5 | [8 empty] | 3903 | [12 empty] | 3903
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 372.00 LF | [7 empty] | 2 | [8 empty] | 820 | [12 empty] | 820
4723.11 | [30 empty] | [ ] | [8 empty] | 4723 | [12 empty] | 4723
=====> Item Totals: 498 - STATION PLATFORM MADISON AND BOYLSTON AV $250,915.34 536.0000 MH/LS 536.00 MH [ 36911.95 ] 44,038 206,378 500 250,915 250,915.340 1 LS 44,037.78 206,377.56 500.00 250,915.34
BID ITEM = 499 CLIENT# = 499 Land Item SCHEDULE: 1 100
Description = | [5 empty] | STATION PLATFORM MADISON AND EAST UNION | [24 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
499.01 | [5 empty] | TRUNKATED DOME | [24 empty] | Quan: 184.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 184.00 SF | [10 empty] | 13.85 | [8 empty] | 2810 | [13 empty] | 2810
499.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 301.00 LF | [8 empty] | Hrs/Shft: 10.00 | [8 empty] | Cal: 510 |  | WC: WAAVG
ZZZZ SITE FURNISHINGS CREW 16.00 CH Prod: 2WHEEL STATION WHEEL @110. 1.00 301.00 LF 109.260 LAG General Laborer $38,490.53 0.1063 MH/LF
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 2 |  | Eqp Pcs: |  | 0
36258 | [56 empty] | 36258
2 | [22 empty] | 32.00 MH | [7 empty] | 52.91 | [8 empty] | 2232 | [12 empty] | 2232
[23 empty] | 32.00 MH | [7 empty] | [ 6.187 ] | [8 empty] | 2,232 36,258 | [12 empty] | 38491
499.03 STATION FOUNDATIONS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 32 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 20.00 CY
32.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2671 | [56 empty] | 2671
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 160.00 MH | [5 empty] | 64.98 | [10 empty] | 13632 | [12 empty] | 13632
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 68.98 | [10 empty] | 2890 | [12 empty] | 2890
19192.99 | [5 empty] | 192.0000 MH/LS | [16 empty] | 192.00 MH | [5 empty] | [ 13864.58 ] | [10 empty] | 16522 |  |  |  |  | 2671 | [7 empty] | 19193
499.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: 241.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 63.00 CY | [5 empty] | 24 |  | CH Prod: 24.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 8,415 8,415
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 120.00 MH | [7 empty] | 64.98 | [8 empty] | 10224 | [12 empty] | 10224
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 68.98 | [8 empty] | 2168 | [12 empty] | 2168
20806 | [5 empty] | 0.5975 MH/SY | [16 empty] | 144.00 MH | [7 empty] | [ 43.147 ] | [8 empty] | 12391 |  |  |  |  | 8415 | [7 empty] | 20806
499.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [8 empty] | 4130 |  |  |  |  | 134 | [7 empty] | 4264
499.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 1.00 LS 500.000 500 500
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 499 CLIENT# = 499 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | STATION PLATFORM MADISON AND EAST UNION | [23 empty] | Unit = LS
499.07 |  |  | ISLAND NOSING | [23 empty] | Quan: 12.0
COM 2CR040 |  |  | Concrete 6 Man Crew 6.00 4000LB READY M@110.2 1.00 1.50 CY | [23 empty] | CH Pro 121.150
d:
6.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
200 | [56 empty] | 200
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 30.00 MH | [5 empty] | 64.98 | [12 empty] | 2556 | [10 empty] | 2556
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 6.00 MH | [5 empty] | 68.98 | [12 empty] | 542 | [10 empty] | 542
3298.15 | [5 empty] | 3.0000 MH/SY | [16 empty] | 36.00 MH | [5 empty] | [ 216.634 ] | [12 empty] | 3098 |  |  | 200 | [7 empty] | 3298
499.08 ZZZZ | [5 empty] | LEANING RAIL SITE FURNISHINGS CREW | [13 empty] | 4 | [10 empty] | Quan: CH |  |  | 7.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG Prod: 4.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
1364 | [57 empty] | 1364
2LEAN | [5 empty] | LEAN RAIL@110.25% | [13 empty] | 1 |  |  | 7.00 LF | [7 empty] | 176.77
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 52.91
1922.3 | [5 empty] | 1.1428 MH/LF | [16 empty] | 8.00 MH | [7 empty] | [ 66.516 ]
558 | [52 empty] | 558
558 | [44 empty] | 1364 | [7 empty] | 1922
Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
499.09 | [5 empty] | BARRIER RAIL | [24 empty] | Quan: |  |  | 350.00 LS
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [18 empty] | 24 | [5 empty] | CH |  |  | Prod:
24.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 2 |  | Eqp Pcs: |  | 0
104140 | [56 empty] | 104140
2BARE BARRIER RAIL@110.25% 1.00 350.00 LF 269.880
LAG General Laborer 2.00 | [22 empty] | 48.00 MH | [5 empty] | 52.91 | [12 empty] | 3349 | [10 empty] | 3349
$107,488.45 0.1371 MH/LS | [22 empty] | 48.00 MH | [5 empty] | [ 7.982 ] | [12 empty] | 3,349 104,140 | [10 empty] | 107488
499.10 ZZZZ | [5 empty] | BARRIER RAIL W HANDRAIL SITE FURNISHINGS CREW | [16 empty] | 12 | [7 empty] | Quan: CH |  |  | 160.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG Prod: 12.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
51969 | [56 empty] | 51969
2BAREH BARRIER RAIL W@110.2 1.00 160.00 LF 294.610
LAG General Laborer 2.00 | [22 empty] | 24.00 MH | [7 empty] | 52.91 | [8 empty] | 1674 | [12 empty] | 1674
$53,643.44 0.1500 MH/LS | [22 empty] | 24.00 MH | [7 empty] | [ 8.73 ] | [8 empty] | 1,674 51,969 | [12 empty] | 53643
499.11 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 2,731.00 LF | [7 empty] | 1.5 | [8 empty] | 4516 | [12 empty] | 4516
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 244.00 LF | [7 empty] | 2 | [8 empty] | 538 | [12 empty] | 538
5054.41 | [30 empty] | [ ] | [8 empty] | 5054 | [12 empty] | 5054
=====> Item Totals: 499 - STATION PLATFORM MADISON AND EAST UNION $257,469.85 532.0000 MH/LS 532.00 MH [ 36847.27 ] 43,954 213,016 500 257,470 257,469.850 1 LS 43,954.20 213,015.65 500.00 257,469.85
BID ITEM = 500 CLIENT# = 500 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 17TH AVENUE Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1527
500.01 | [5 empty] | TRUNCATED DOME | [24 empty] | Quan: |  |  | 100.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 100.00 SF | [10 empty] | 13.850 1
,527
Hrs/Shft: 10.00
500.02 | [5 empty] | WHEEEL GUIDE | [24 empty] | Quan: |  |  | 54.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH | [58 empty] | Lab Pcs: | 2 | Eqp Pcs: | 0
2WHEEL STATION WHEEL @110. 1.00 54.00 LF 109.260 6,505 | [61 empty] | 6505
LAG General Laborer 2.00 16.00 MH 52.910 1,116 $7,620.96 0.2962 MH/LF 16.00 MH [ 17.245 ] 1,116 6,505 | [61 empty] | 1,116 7,621
500.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM |  |  | Concrete 6 Man Crew | [16 empty] | 16 | [6 empty] | CH |  |  | Prod: 16.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  | Unit Cost | [12 empty] | Perm Constr Labor Material Matl/Exp | [10 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 500 CLIENT# = 500 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 17TH AVENUE Unit = LS Takeoff Quan: 1.000 | [52 empty] | Engr Quan: |  |  |  | 1
2CR040 4000LB READY M@110.2 1.00 11.00 CY 121.150 1,469 | [56 empty] | 1469
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9730.07 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1469 | [7 empty] | 9730
500.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 104.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 15.00 CY | [5 empty] | 12 |  | CH |  |  | Prod: 12.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 2,004 2,004
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 60.00 MH | [7 empty] | 64.98 | [8 empty] | 5112 | [12 empty] | 5112
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 68.98 | [8 empty] | 1084 | [12 empty] | 1084
8199.13 | [5 empty] | 0.6923 MH/SY | [16 empty] | 72.00 MH | [7 empty] | [ 49.993 ] | [8 empty] | 6196 |  |  |  |  | 2004 | [7 empty] | 8199
500.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 4 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [10 empty] | 1704 | [6 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [10 empty] | 361 | [6 empty] | 361
2198.77 | [5 empty] | 24.0000 MH/LS | [16 empty] | 24.00 MH | [7 empty] | [ 1733.07 ] | [10 empty] | 2065 |  |  |  |  | 134 |  | 2199
500.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | : 10.00 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
500.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [10 empty] | 45 | [6 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [6 empty] | 269
313.66 | [30 empty] | [ ] | [10 empty] | 314 | [6 empty] | 314
=====> Item Totals: 500 - STATION PLATFORM MADISON AND 17TH AVENUE $30,089.55 208.0000 MH/LS 208.00 MH [ 14795.8 ] 17,638 11,952 500 30,090 30,089.550 1 LS 17,637.80 11,951.75 500.00 30,089.55
BID ITEM = 501 CLIENT# = 501 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 17TH AVENUE Unit = LS Takeoff Qua
n: 1.000 | [53 empty] | Engr Quan: |  |  | 1
ft: 10.00 Cal: 510 | [53 empty] | WC: WAAVG
1,512 ft: 10.00 Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1512
2TRUNK TRUNKATED DOME@11 1.00 99.00 SF 13.850
501.02 WHEEL GUIDE Quan: 54.00 LF Hrs/Sh
ZZZZ SITE FURNISHINGS CREW 8.00 CH Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 54.00 LF 109.260 6,505 6,505 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 6,505 7,621
7620.96 |  |  | 0.2962 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 17.245 ]
501.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 12.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1603 | [56 empty] | 1603
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
9863.63 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [7 empty] | [ 6932.29 ] | [8 empty] | 8261 |  |  |  |  | 1603 | [7 empty] | 9864
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 501 CLIENT# = 501 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 17TH AVENUE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
501.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 106.00 SY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [16 empty] | 12 | [7 empty] | CH |  |  | Prod: | [7 empty] | 12.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 15.00 CY | [10 empty] | 121.15 | [7 empty] | 2,004 2,004
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 60.00 MH 64.980 | [18 empty] | 5112 | [10 empty] | 5112
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 12.00 MH 68.980 | [18 empty] | 1084 | [10 empty] | 1084
8199.13 | [5 empty] | 0.6792 MH/SY | [16 empty] | 72.00 MH [ 49.049 ] | [18 empty] | 6196 |  |  | 2004 | [7 empty] | 8199
501.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 4 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [10 empty] | 1704 | [6 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [10 empty] | 361 | [6 empty] | 361
2198.77 | [5 empty] | 24.0000 MH/LS | [16 empty] | 24.00 MH | [7 empty] | [ 1733.07 ] | [10 empty] | 2065 |  |  |  |  | 134 |  | 2199
501.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | : 10.00 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
501.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [10 empty] | 45 | [6 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [6 empty] | 269
313.66 | [30 empty] | [ ] | [10 empty] | 314 | [6 empty] | 314
=====> Item Totals: 501 - STATION PLATFORM MADISON AND 17TH AVENUE $30,207.84 208.0000 MH/LS 208.00 MH [ 14795.8 ] 17,638 12,070 500 30,208 30,207.840 1 LS 17,637.80 12,070.04 500.00 30,207.84
BID ITEM = 502 CLIENT# = 502 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND EAST DENNY Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1832
502.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 120.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 120.00 SF | [10 empty] | 13.850 1
,832
Hrs/Shft: 10.00
502.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 56.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 56.00 LF 109.260 6,746 6,746 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 6,746 7,862
7861.88 |  |  | 0.2857 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 16.629 ]
502.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 16.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2137 | [56 empty] | 2137
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
10397.91 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 2137 | [7 empty] | 10398
502.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 60.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 10.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,336 1,336
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost | [5 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 502 CLIENT# = 502 Land Item STATION PLATFORM MADISON AND EAST DENNY Unit = | [25 empty] | SCHEDULE: 1 LS Takeoff Quan: | [13 empty] | 100 |  |  | 1 |  | Engr Quan: |  |  |  | 1
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [10 empty] | 64.98 | [5 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 68.98 | [5 empty] | 723 | [10 empty] | 723
5466.08 | [5 empty] | 0.8000 MH/SY | [16 empty] | 48.00 MH | [10 empty] | [ 57.769 ] | [5 empty] | 4130 |  |  |  |  | 1336 | [5 empty] | 5466
502.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 4 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [10 empty] | 1704 | [6 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [10 empty] | 361 | [6 empty] | 361
2198.77 | [5 empty] | 24.0000 MH/LS | [16 empty] | 24.00 MH | [7 empty] | [ 1733.07 ] | [10 empty] | 2065 |  |  |  |  | 134 |  | 2199
502.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | : 10.00 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
502.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [10 empty] | 45 | [6 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [6 empty] | 269
313.66 | [30 empty] | [ ] | [10 empty] | 314 | [6 empty] | 314
=====> Item Totals: 502 - STATION PLATFORM MADISON AND EAST DENNY $28,570.66 184.0000 MH/LS 184.00 MH [ 13062.72 ] 15,573 12,498 500 28,571 28,570.660 1 LS 15,572.59 12,498.07 500.00 28,570.66
BID ITEM = 503 CLIENT# = 503 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND EAST DENNY Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1848
503.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 121.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 121.00 SF | [10 empty] | 13.850 1
,848
Hrs/Shft: 10.00
503.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 64.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 64.00 LF 109.260 7,709 7,709 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,709 8,826
8825.56 |  |  | 0.2500 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 14.55 ]
503.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 8.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1069 | [56 empty] | 1069
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9329.36 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1069 | [7 empty] | 9329
503.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 67.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 14.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,870 1,870
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
6000.35 | [5 empty] | 0.7164 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 51.733 ] | [8 empty] | 4130 |  |  |  |  | 1870 | [7 empty] | 6000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 503 CLIENT# = 503 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | STATION PLATFORM MADISON AND EAST DENNY | [23 empty] | Unit = LS
503.05 |  |  | FOUNDATION STEM WALL | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4.00 4000LB READY M@110.2 1.00 1.00 CY | [23 empty] | CH Pro 121.150
d:
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [10 empty] | 1704 | [6 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [10 empty] | 361 | [6 empty] | 361
2198.77 | [5 empty] | 24.0000 MH/LS | [16 empty] | 24.00 MH | [7 empty] | [ 1733.07 ] | [10 empty] | 2065 |  |  |  |  | 134 |  | 2199
503.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
503.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2.000 269 269
=====> Item Totals: 503 - S $28,970.67 184.0000 MH/LS | [19 empty] | TATION PLATFORM MADISON AND EAST DENNY 184.00 MH [ 13062.72 ] 15,573 12,898 500 28,971
28970.67 | [5 empty] | 1 LS | [24 empty] | 15,572.59 12,898.08 500.00 28,970.67
:
BID ITEM = 504 CLIENT# = 504 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 23RD AVENUE Unit = LS Takeoff Qua
n: 1.000 | [53 empty] | Engr Quan: |  |  | 1
ft: 10.00 Cal: 510 | [53 empty] | WC: WAAVG
1,130 ft: 10.00 Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1130
2TRUNK TRUNKATED DOME@11 1.00 74.00 SF 13.850
504.02 WHEEEL GUIDE Quan: 65.00 LF Hrs/Sh
ZZZZ SITE FURNISHINGS CREW 8.00 CH Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 65.00 LF 109.260 7,830 7,830 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,830 8,946
8946.01 |  |  | 0.2461 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 14.326 ]
504.03 |  |  | STATION FOUNDATION | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 8.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1069 | [56 empty] | 1069
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9329.36 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1069 | [7 empty] | 9329
504.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 70.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 13.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,736 1,736
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [5 empty] | 64.98 | [12 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 68.98 | [12 empty] | 723 | [10 empty] | 723
5866.78 | [5 empty] | 0.6857 MH/SY | [16 empty] | 48.00 MH | [5 empty] | [ 49.516 ] | [12 empty] | 4130 |  |  | 1736 | [7 empty] | 5867
504.05 | [5 empty] | FOUNDATION STEM WALL | [24 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 134 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 504 CLIENT# = 504 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 23RD AVENUE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 $4,263.97 48.0000 MH/LS 48.00 MH [ 3466.14 ] 4,130 134 4,264
504.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
504.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [8 empty] | 45 | [12 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [8 empty] | 269 | [12 empty] | 269
313.66 | [30 empty] | [ ] | [8 empty] | 314 | [12 empty] | 314
=====> Item Totals: 504 - STATION PLATFORM MADISON AND 23RD AVENUE
30349.73 | [5 empty] | 208.0000 MH/LS | [13 empty] | 208.00 MH | [10 empty] | [ 14795.79 ] 17,638 12,212 500 30,350
30349.73 | [5 empty] | 1 LS | [24 empty] | 17,637.79 12,211.94 500.00 30,349.73
BID ITEM = 505 CLIENT# = 505 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 24TH AVENUE Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1787
505.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 117.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 117.00 SF | [10 empty] | 13.850 1
,787
: 10.00
505.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 71.00 LF Hrs/Shft
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod: 8.0000
CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer $1,116.17 0.2253 MH/LF
2 | [22 empty] | 16.00 MH | [7 empty] | 52.91 | [8 empty] | 1116 | [12 empty] | 1116
[23 empty] | 16.00 MH | [7 empty] | [ 13.116 ] | [8 empty] | 1116 | [12 empty] | 1116
505.03 STATION FOUNDATIONS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 16 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 14.00 CY
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1870 | [56 empty] | 1870
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
10130.77 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1870 | [7 empty] | 10131
505.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 92.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 17.00 CY | [5 empty] | 12 |  | CH |  |  | Prod: 12.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 2,271 2,271
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 60.00 MH | [7 empty] | 64.98 | [8 empty] | 5112 | [12 empty] | 5112
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 12.00 MH | [7 empty] | 68.98 | [8 empty] | 1084 | [12 empty] | 1084
8466.26 | [5 empty] | 0.7826 MH/SY | [16 empty] | 72.00 MH | [7 empty] | [ 56.513 ] | [8 empty] | 6196 |  |  |  |  | 2271 | [7 empty] | 8466
505.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [8 empty] | 4130 |  |  |  |  | 134 | [7 empty] | 4264
505.06 STATION CHANALIZATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4STRI Striping sub 1.00 1.00 LS 500.000 500 500
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 505 CLIENT# = 505 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND 24TH AVENUE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
505.07 | [5 empty] | REBAR PURCHASE | [13 empty] | Quan: | [13 empty] | 1.00 LS | [8 empty] | Hrs/Shft: | [5 empty] | 10 |  |  | Cal: 510 |  | WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [11 empty] | 45 | [5 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [11 empty] | 269 | [5 empty] | 269
313.66 | [30 empty] | [ ] | [11 empty] | 314 | [5 empty] | 314
=====> Item Totals: 505 - STATION PLATFORM MADISON AND 24TH AVENUE $26,577.38 232.0000 MH/LS 232.00 MH [ 16528.87 ] 19,703 6,374 500 26,577 26,577.380 1 LS 19,703.00 6,374.38 500.00 26,577.38
BID ITEM = 506 CLIENT# = 506 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND MLK WAY Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1787
506.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 117.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 117.00 SF | [10 empty] | 13.850 1
,787
Hrs/Shft: 10.00
506.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 65.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 65.00 LF 109.260 7,830 7,830 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 1,116 7,830 8,946
8946.01 |  |  | 0.2461 MH/LF | [13 empty] | 16.00 MH | [9 empty] | [ 14.326 ]
506.03 |  |  | STATION FOUNDATIONS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [13 empty] | 9.00 CY | [7 empty] | 16 |  | CH Pr 121.150
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1202 | [56 empty] | 1202
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9462.93 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1202 | [7 empty] | 9463
506.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 73.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 12.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,603 1,603
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
5733.21 | [5 empty] | 0.6575 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 47.481 ] | [8 empty] | 4130 |  |  |  |  | 1603 | [7 empty] | 5733
506.05 FOUNDATION STEM WALLS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 4 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 20.00 MH | [7 empty] | 64.98 | [10 empty] | 1704 | [6 empty] | 1704
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 68.98 | [10 empty] | 361 | [6 empty] | 361
2198.77 | [5 empty] | 24.0000 MH/LS | [16 empty] | 24.00 MH | [7 empty] | [ 1733.07 ] | [10 empty] | 2065 |  |  |  |  | 134 |  | 2199
506.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | : 10.00 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
506.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [10 empty] | 45 | [6 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [6 empty] | 269
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 506 CLIENT# = 506 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM MADISON AND MLK WAY Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 $313.66 [ ] 314 314
=====> Item Totals: 506 - STATION PLATFORM MADISON AND MLK WAY $28,941.13 184.0000 MH/LS 184.00 MH [ 13062.72 ] 15,573 12,869 500 28,941 28,941.130 1 LS 15,572.59 12,868.54 500.00 28,941.13
BID ITEM = 507 CLIENT# = 507 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | STATION PLATFORM EAST UNION AND 12TH AVE | [23 empty] | Unit = LS
507.01 |  |  | STATION FOUNDATION | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 8.00 4000LB READY M@110.2 1.00 3.00 CY | [23 empty] | CH Pro 121.150
d:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
401 | [56 empty] | 401
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [5 empty] | 64.98 | [12 empty] | 3408 | [10 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 68.98 | [12 empty] | 723 | [10 empty] | 723
4531.1 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [5 empty] | [ 3466.14 ] | [12 empty] | 4130 |  |  | 401 | [7 empty] | 4531
507.02 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 82.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 9.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,202 1,202
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
5332.51 | [5 empty] | 0.5853 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 42.27 ] | [8 empty] | 4130 |  |  |  |  | 1202 | [7 empty] | 5333
Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
507.03 ZZZZ | [5 empty] | BARRIER RAIL SITE FURNISHINGS CREW | [16 empty] | 8 | [7 empty] | Quan: CH |  |  | 44.00 LF Prod:
2BARE | [5 empty] | BARRIER RAIL@110.25% 1.00 | [16 empty] | 44.00 LF | [10 empty] | 269.88
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 16.00 MH | [10 empty] | 52.910 1
14208.05 | [5 empty] | 0.3636 MH/LF | [16 empty] | 16.00 MH | [10 empty] | [ 21.164 ] 1
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 2 |  | Eqp Pcs: |  | 0
13092 | [56 empty] | 13092
,116 | [52 empty] | 1116
,116 | [44 empty] | 13092 | [7 empty] | 14208
=====> Item $24,071.66 | [6 empty] | Totals: 507 - ST 112.0000 MH/LS | [14 empty] | ATION PLATFORM EA 112.00 MH | [8 empty] | ST UNION AND 12TH AVE [ 7863.5 ] 9,377 | [13 empty] | 14695 | [7 empty] | 24072
24071.66 | [6 empty] | 1 LS | [23 empty] | 9376.97 | [13 empty] | 14694.69 | [7 empty] | 24071.66
BID ITEM = 508 CLIENT# = 508 Land Item SCHEDULE: 1 100 Description = STATION PLATFORM EAST MADISON STREET AND Unit = LS Takeoff Quan:
1 | [53 empty] | Engr Quan: |  |  | 1
Cal: 510 | [53 empty] | WC: WAAVG
Cal: 510 | [53 empty] | WC: WAAVG |  |  | 1649
508.01 | [5 empty] | TRUNCATED DOMES | [24 empty] | Quan: |  |  | 108.00 SF Hrs/Shft
2TRUNK | [5 empty] | TRUNKATED DOME@11 | [13 empty] | 1 |  |  | 108.00 SF | [10 empty] | 13.850 1
,649
Hrs/Shft: 10.00
508.02 | [5 empty] | WHEEL GUIDE | [24 empty] | Quan: |  |  | 57.00 LF
ZZZZ | [5 empty] | SITE FURNISHINGS CREW | [22 empty] | 8 |  | CH |  |  | Prod:
8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00 2WHEEL STATION WHEEL @110. 1.00 57.00 LF 109.260 6,866 6,866 LAG General Laborer 2.00 16.00 MH 52.910 1,116 1,116 $7,982.34 0.2807 MH/LF 16.00 MH [ 16.337 ] 1,116 6,866 7,982
Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
508.03 COM | [5 empty] | STATION FOUNDATION Concrete 6 Man Crew | [22 empty] | 16 |  | Quan: CH |  |  | 1.00 LS Prod:
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 6.00 CY | [10 empty] | 121.15
16.0000 CH Lab Pcs: | [52 empty] | 6 |  | Eqp Pcs: |  | 0
801 | [56 empty] | 801
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [10 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 508 CLIENT# = 508 Land Item STATION PLATFORM EAST MADISON STREET AND Unit = | [25 empty] | SCHEDULE: 1 LS Takeoff Quan: | [12 empty] | 100 |  |  |  | 1 |  | Engr Quan: |  |  |  | 1
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [10 empty] | 64.98 | [7 empty] | 6816 | [8 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [10 empty] | 68.98 | [7 empty] | 1445 | [8 empty] | 1445
9062.23 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH [ | [10 empty] | 6932.29 ] | [7 empty] | 8261 |  |  |  |  | 801 |  |  |  | 9062
508.04 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 42.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 10.00 CY | [5 empty] | 8 |  | CH |  |  | Prod: 8.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,336 1,336
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 3408 | [12 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 723 | [12 empty] | 723
5466.08 | [5 empty] | 1.1428 MH/SY | [16 empty] | 48.00 MH | [7 empty] | [ 82.527 ] | [8 empty] | 4130 |  |  |  |  | 1336 | [7 empty] | 5466
508.05 FOUNDATION STEM WALL Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 8 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 1.00 CY
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
Prod: 121.150
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
508.06 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | 10 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
508.07 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2.000 269 269
=====> Item Totals: 508 - S $29,192.75 208.0000 MH/LS | [19 empty] | TATION PLATFORM EAST MADISON STREET AND 208.00 MH [ 14795.79 ] 17,638 11,055 500 29,193
29192.75 | [5 empty] | 1 LS | [24 empty] | 17,637.79 11,054.96 500.00 29,192.75
:
BID ITEM = 509 CLIENT# = 509 Land Item SCHEDULE: 1 100
Description = |  |  | STATION PLATFORM MADISON AND 1ST AVE NB | [23 empty] | Unit = |  |  | LS Takeoff Quan: 1.000 Engr Quan: 1.000
509.01 |  |  | WHEEL GUIDE | [23 empty] | Quan: |  |  | 61.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ |  |  | SITE FURNISHINGS CREW 8.00 | [23 empty] | CH |  |  | Prod: 8.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 | [16 empty] | 16.00 MH | [9 empty] | 52.91 | [7 empty] | 1116 | [14 empty] | 1116
$1,116.17 0.2622 MH/LF | [16 empty] | 16.00 MH | [9 empty] | [ 15.266 ] | [7 empty] | 1116 | [14 empty] | 1116
509.02 STATION FOUNDATION Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Prod: 121.150
COM | [5 empty] | Concrete 6 Man Crew | [22 empty] | 16 |  | CH
2CR040 | [5 empty] | 4000LB READY M@110.2 1.00 | [16 empty] | 10.00 CY
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1336 | [56 empty] | 1336
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [5 empty] | 64.98 | [12 empty] | 6816 | [10 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 68.98 | [12 empty] | 1445 | [10 empty] | 1445
9596.5 | [5 empty] | 96.0000 MH/LS | [16 empty] | 96.00 MH | [5 empty] | [ 6932.29 ] | [12 empty] | 8261 |  |  | 1336 | [7 empty] | 9597
509.03 | [5 empty] | STATION SIDEWALKS | [24 empty] | Quan: |  |  | 112.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 1.00 | [16 empty] | 13.00 CY | [5 empty] | 16 |  | CH |  |  | Prod: 16.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.150 1,736 1,736
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [8 empty] | 6816 | [12 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [8 empty] | 1445 | [12 empty] | 1445
9997.2 | [5 empty] | 0.8571 MH/SY | [16 empty] | 96.00 MH | [7 empty] | [ 61.895 ] | [8 empty] | 8261 |  |  |  |  | 1736 | [7 empty] | 9997
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 509 CLIENT# = 509 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | STATION PLATFORM MADISON AND 1ST AVE NB | [23 empty] | Unit = LS
509.04 |  |  | FOUNDATION STEM WALLS | [23 empty] | Quan: 1.0
COM 2CR040 |  |  | Concrete 6 Man Crew 8.00 4000LB READY M@110.2 1.00 1.00 CY | [23 empty] | CH Pro 121.150
d:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
134 | [56 empty] | 134
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [10 empty] | 3408 | [6 empty] | 3408
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [10 empty] | 723 | [6 empty] | 723
4263.97 | [5 empty] | 48.0000 MH/LS | [16 empty] | 48.00 MH | [7 empty] | [ 3466.14 ] | [10 empty] | 4130 |  |  |  |  | 134 |  | 4264
509.05 | [5 empty] | STATION CHANALIZATION | [16 empty] | Quan: | [10 empty] | 1.00 LS | [7 empty] | Hrs/Shft |  |  |  |  | : 10.00 |  |  |  |  | Cal: 510 |  | WC: WAAVG
4STRI | [5 empty] | Striping sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 500.000 500 500
509.06 | [5 empty] | REBAR PURCHASE | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2RB4 | [5 empty] | #4 REBAR@110.25% | [13 empty] | 1 |  |  | 27.00 LF | [7 empty] | 1.5 | [10 empty] | 45 | [6 empty] | 45
2RB5 | [5 empty] | #5 REBAR@110.25% | [13 empty] | 1 |  |  | 122.00 LF | [7 empty] | 2 | [10 empty] | 269 | [6 empty] | 269
313.66 | [30 empty] | [ ] | [10 empty] | 314 | [6 empty] | 314
=====> Item Totals: 509 - STATION PLATFORM MADISON AND 1ST AVE NB $25,787.50 256.0000 MH/LS 256.00 MH [ 18261.94 ] 21,768 3,519 500 25,788 25,787.500 1 LS 21,768.21 3,519.29 500.00 25,787.50
BID ITEM = 510 CLIENT# = 510 Land Item SCHEDULE: 1 100 Description = EXTRA LAMINATED TEMPERED GLASS PANELS Unit = EA Takeoff Quan: 20.000 Engr Quan: 20.000
510.01 EXTRA LAMINATED TEMPERED GLASS PANEL Quan: 20.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4GLAS GLASS INSTALLER 1.00 20.00 EA 325.000 6,500 6,500
BID ITEM = 511 CLIENT# = 511 Land Item SCHEDULE: 1 100 Description = FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
511.01 FURNISH AND INSTALL RAPIDRIDE SHELTER, Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZZ | [5 empty] | (Mod) SHELTER CREW | [13 empty] | 30 | [10 empty] | CH | Prod: | [8 empty] | 30.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 3 |  | Eqp Pcs: |  | 0
2SHEL208 | [5 empty] | SHELTER TYPE 2@110.2 | [13 empty] | 1 |  |  | 3.00 EA | [5 empty] | 36100 | [11 empty] | 119401 | [15 empty] | 119401
3BOOM | [5 empty] | BOOM TRUCK | [13 empty] | 1 |  |  | 30.00 HR | [5 empty] | 250 | [19 empty] | 7500 | [7 empty] | 7500
4GLAS | [5 empty] | GLASS INSTALLER | [13 empty] | 1 |  |  | 3.00 EA | [5 empty] | 5409 | [23 empty] | 16227 |  |  |  | 16227
LAG General Laborer 3.00 90.00 MH | [28 empty] | 52.91 | [11 empty] | 6278 | [15 empty] | 6278
$149,406.18 30.0000 MH/EA 90.00 MH | [28 empty] | [ 1746.03 ] | [11 empty] | 6278 |  |  |  | 119401 |  |  |  | 7500 |  |  |  | 16227 |  |  |  | 149406
=====> Item Totals: 511 - FURNISH AND INSTALL RAPIDRIDE SHELTER, R
149406.18 | [5 empty] | 30.0000 MH/EA | [13 empty] | 90.00 MH | [8 empty] | [ 1746.03 ] 6,278 | [15 empty] | 119401 |  |  |  | 7,500 16,227 149,406
49802.06 | [5 empty] | 3 EA | [22 empty] | 2092.81 | [15 empty] | 39800.25 |  |  |  | 2,500.00 5,409.00 49,802.06
BID ITEM = 512 CLIENT# = 512 Land Item SCHEDULE: 1 100 Description = FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  |  | Unit Cost | [7 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = |  |  |  |  | = |  |  | 512 CLIENT# = 512 Land Item SCHEDULE: 1 100 FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 5.000 | [44 empty] | Engr Quan: |  |  |  | 5
ZZZZZ | [7 empty] | (Mod) SHELTER CREW 50.00 CH | [23 empty] | Prod: 50.0000 CH Lab Pcs: | [20 empty] | 3.00 Eqp Pcs: |  |  |  | 0
2SHEL206 |  |  |  |  | SHELTER TYPE 2@110.2 | [13 empty] | 1 |  |  |  | 5.00 EA | [8 empty] | 34625 | [7 empty] | 190870 | [16 empty] | 190870
3BOOM |  |  |  |  | BOOM TRUCK | [13 empty] | 1 |  |  |  | 50.00 HR | [8 empty] | 250 | [16 empty] | 12500 | [7 empty] | 12500
4GLAS |  |  |  |  | GLASS INSTALLER | [13 empty] | 1 |  |  |  | 5.00 EA | [8 empty] | 5409 | [20 empty] | 27045 |  |  |  | 27045
LAG General Laborer 3.00 150.00 MH | [31 empty] | 52.91 | [7 empty] | 10464 | [16 empty] | 10464
$240,879.36 30.0000 MH/EA 150.00 MH | [31 empty] | [ 1746.03 ] | [7 empty] | 10464 |  |  |  |  | 190870 |  |  |  | 12500 |  |  |  | 27045 |  |  |  | 240879
=====> Ite $240,879.36 |  |  |  |  | m Totals: 512 - 30.0000 MH/EA | [13 empty] | FURNISH AND INSTALL RAPID 150.00 MH | [12 empty] | RIDE SHELTER, R [ 1746.03 ] 10,464 | [12 empty] | 190870 |  |  |  | 12,500 27,045 240,879
48175.872 |  |  |  |  | 5 EA | [26 empty] | 2092.81 | [12 empty] | 38174.06 |  |  |  | 2,500.00 5,409.00 48,175.87
BID ITEM = 513 CLIENT# = 513 Land Item SCHEDULE: 1 100 Description = FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
513.01 FURNISH AND INSTALL RAPIDRIDE SHELTER, Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZZ |  |  |  |  | (Mod) SHELTER CREW | [13 empty] | 80 | [11 empty] | CH | Prod: | [7 empty] | 80.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 3 |  | Eqp Pcs: |  | 0
2SHEL206LP |  |  |  |  | SHELTER TYPE 2@110.2 | [13 empty] | 1 |  |  |  | 8.00 EA | [5 empty] | 33805 | [10 empty] | 298160 | [16 empty] | 298160
3BOOM |  |  |  |  | BOOM TRUCK | [13 empty] | 1 |  |  |  | 80.00 HR | [5 empty] | 250 | [19 empty] | 20000 | [7 empty] | 20000
4GLAS |  |  |  |  | GLASS INSTALLER | [13 empty] | 1 |  |  |  | 8.00 EA | [5 empty] | 5409 | [23 empty] | 43272 |  |  |  | 43272
LAG General Laborer 3.00 240.00 MH | [28 empty] | 52.91 | [10 empty] | 16742 | [16 empty] | 16742
$378,174.57 30.0000 MH/EA 240.00 MH | [28 empty] | [ 1746.03 ] | [10 empty] | 16742 |  |  |  |  | 298160 |  |  |  | 20000 |  |  |  | 43272 |  |  |  | 378175
=====> Item Totals: 513 - FURNISH AND INSTALL RAPIDRIDE SHELTER, R
378174.57 |  |  |  |  | 30.0000 MH/EA | [13 empty] | 240.00 MH | [9 empty] | [ 1746.03 ] 16,742 | [15 empty] | 298160 |  |  |  | 20,000 43,272 378,175
47271.821 |  |  |  |  | 8 EA | [23 empty] | 2092.81 | [15 empty] | 37270.01 |  |  |  | 2,500.00 5,409.00 47,271.82
BID ITEM = 514 CLIENT# = 514 Land Item SCHEDULE: 1 100 Description = FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
514.01 FURNISH AND INSTALL RAPIDRIDE SHELTER, Quan: 8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZZ |  |  |  |  | (Mod) SHELTER CREW | [13 empty] | 80 | [11 empty] | CH | Prod: | [7 empty] | 80.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 3 |  | Eqp Pcs: |  | 0
2SHEL126 |  |  |  |  | SHELTER TYPE 1@110.2 | [13 empty] | 1 |  |  |  | 8.00 EA | [5 empty] | 20780 | [10 empty] | 183280 | [16 empty] | 183280
3BOOM |  |  |  |  | BOOM TRUCK | [13 empty] | 1 |  |  |  | 80.00 HR | [5 empty] | 250 | [19 empty] | 20000 | [7 empty] | 20000
4GLAS |  |  |  |  | GLASS INSTALLER | [13 empty] | 1 |  |  |  | 8.00 EA | [5 empty] | 5409 | [23 empty] | 43272 |  |  |  | 43272
LAG General Laborer 3.00 240.00 MH | [28 empty] | 52.91 | [10 empty] | 16742 | [16 empty] | 16742
$263,294.07 30.0000 MH/EA 240.00 MH | [28 empty] | [ 1746.03 ] | [10 empty] | 16742 |  |  |  |  | 183280 |  |  |  | 20000 |  |  |  | 43272 |  |  |  | 263294
=====> Item Totals: 514 - FURNISH AND INSTALL RAPIDRIDE SHELTER, R
263294.07 |  |  |  |  | 30.0000 MH/EA | [13 empty] | 240.00 MH | [9 empty] | [ 1746.03 ] 16,742 | [15 empty] | 183280 |  |  |  | 20,000 43,272 263,294
32911.759 |  |  |  |  | 8 EA | [23 empty] | 2092.81 | [15 empty] | 22909.95 |  |  |  | 2,500.00 5,409.00 32,911.76
BID ITEM = 515 CLIENT# = 515 Land Item SCHEDULE: 1 100
| Description = |  |  |  | INSTALL OWNER FURNISHED, METRO ROUTE SIG | [25 empty] | Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000
| 515.01 ZZZ |  |  |  | INSTALL OWNER FURNISHED, METRO ROUTE SIGN CREW 11.00 | [25 empty] | Quan: 22.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG CH Prod: 11.0000 CH Lab Pcs: 1.00 Eqp Pcs: 0.00
| LAG |  |  |  | General Laborer 1.00 11.00 MH | [25 empty] | 52.910 767 767
| $767.36 0.5000 MH/EA 11.00 MH | [29 empty] | [ 29.1 ] | [8 empty] | 767 | [12 empty] | 767
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 515 CLIENT# = 515 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURNISHED, METRO ROUTE SIG Unit = EA Takeoff Quan: 22.000 Engr Quan: 22.000 =====> Item Totals: 515 - INSTALL OWNER FURNISHED, METRO ROUTE SIG $767.36 0.5000 MH/EA 11.00 MH [ 29.1 ] 767 767 34.880 22 EA 34.88 34.88
BID ITEM = 516 CLIENT# = 516 Land Item SCHEDULE: 1 100
Description = |  |  | INSTALL OWNER FURNISHED, TRASH RECEPTACL | [23 empty] | Unit = |  |  | EA Takeoff Quan: 19.000 Engr Quan: 19.000
516.01 |  |  | INSTALL OWNER FURNISHED, TRASH RECEPT | [23 empty] | Quan: |  |  | 19.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ |  |  | SITE FURNISHINGS CREW 15.00 | [23 empty] | CH |  |  | Prod: 15.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 30.00 MH | [26 empty] | 52.91 | [5 empty] | 2093 | [16 empty] | 2093
$2,092.81 1.5789 MH/EA 30.00 MH | [26 empty] | [ 91.896 ] | [5 empty] | 2093 | [16 empty] | 2093
=====> Item Totals: 516 - INSTALL OWNER FURNISHED, TRASH R $2,092.81 1.5789 MH/EA 30.00 MH [ 91.896 ] | [32 empty] | ECEPTACL 2,093 | [16 empty] | 2093
110.148 19 EA | [32 empty] | 110.15 | [16 empty] | 110.15
BID ITEM = 517 CLIENT# = 517 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURNISHED, TICKET VENDING Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
517.01 INSTALL OWNER FURNISHED, TICKET VENDIN Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 3.00 EA 1,600.000 4,800 4,800
BID ITEM = 518 CLIENT# = 518 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURNISHED, TECH PYLON WITH Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
518.01 INSTALL OWNER FURNISHED, TECH PYLON WI Quan: 21.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 21.00 EA 4,750.000 99,750 99,750
BID ITEM = 519 CLIENT# = 519 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURNISHED, BENCH Unit = EA Takeoff Quan: 25.000 Engr Quan: 25.000
519.01 |  | INSTALL OWNER FURNISHED, BENCH | [24 empty] | Quan: |  |  | 25.00 EA | [5 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZ |  | SITE FURNISHINGS CREW 20.00 | [24 empty] | CH |  |  | Prod: | [5 empty] | 20.0000 CH Lab Pcs: 2.00 Eqp Pcs: 0.00
LAG General Laborer 2.00 40.00 MH |  | 52.91 | [33 empty] | 2790 | [13 empty] | 2790
$2,790.41 1.6000 MH/EA 40.00 MH |  | [ 93.122 ] | [33 empty] | 2790 | [13 empty] | 2790
=====> Item Totals: 519 - INSTALL OWNER FURNISHED, BENCH $2,790.41 1.6000 MH/EA 40.00 MH [ 93.122 ] 2,790 2,790 111.616 25 EA 111.62 111.62
BID ITEM = 520 CLIENT# = 520 Land Item SCHEDULE: 1 100 Description = INSTALL OWNER FURNISHED, BLADE Unit = EA Takeoff Quan: 41.000 Engr Quan: 41.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 520 CLIENT# = 520 INSTALL OWNER FURNISHED, BLADE | [20 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 41.000 Engr Quan: 41.000
520.01 | [5 empty] | INSTALL OWNER FURNISHED, BLADE | [20 empty] | Quan: 41.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZZ SHELTER CREW 41.00 CH Prod: 41.0000 CH Lab Pcs: | [52 empty] | 3 |  | Eqp Pcs: |  | 2
8TRBOOM | [5 empty] | BOOM TRUCK | [13 empty] | 1 |  |  | 41.00 HR | [7 empty] | 45 | [21 empty] | 1845 |  | 1845
8TRML | [5 empty] | MANLIFT | [13 empty] | 1 |  |  | 41.00 HR | [7 empty] | 25 | [21 empty] | 1025 |  | 1025
LAG | [5 empty] | General Laborer | [13 empty] | 3 |  |  | 123.00 MH | [7 empty] | 52.91 | [8 empty] | 8581 | [14 empty] | 8581
$11,450.51 3.0000 MH/EA 123.00 MH | [30 empty] | [ 174.603 ] | [8 empty] | 8581 | [12 empty] | 2870 |  | 11451
=====> Item Totals: 520 - INSTALL OWNER FURNISHED, BLADE $11,450.51 3.0000 MH/EA 123.00 MH [ 174.603 ] | [39 empty] | 8581 | [12 empty] | 2870 |  | 11451
279.281 41 EA | [39 empty] | 209.28 | [12 empty] | 70 |  | 279.28
BID ITEM = 521 CLIENT# = 521 Land Item SCHEDULE: 1 100 Description = FURNISH AND INSTALL RAPIDRIDE SHELTER, R Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
521.01 FURNISH AND INSTALL RAPIDRIDE SHELTER, Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZZZZZ | [5 empty] | (Mod) SHELTER CREW | [13 empty] | 8 | [10 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 3 |  | Eqp Pcs: |  | 0
2SHEL125 | [5 empty] | SHELTER TYPE 1@110.2 | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 19880 | [11 empty] | 21918 | [15 empty] | 21918
3BOOM | [5 empty] | BOOM TRUCK | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 250 | [19 empty] | 2000 | [7 empty] | 2000
4GLAS | [5 empty] | GLASS INSTALLER | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 5409 | [23 empty] | 5409 |  |  |  | 5409
LAG General Laborer 3.00 24.00 MH | [28 empty] | 52.91 | [11 empty] | 1674 | [15 empty] | 1674
$31,000.94 24.0000 MH/EA 24.00 MH | [28 empty] | [ 1396.82 ] | [11 empty] | 1674 |  |  |  | 21918 |  |  |  | 2000 |  |  |  | 5409 |  |  |  | 31001
=====> Item Totals: 521 - FURNISH AND INSTALL RAPIDRIDE SHELTER, R
31000.94 | [5 empty] | 24.0000 MH/EA | [13 empty] | 24.00 MH | [8 empty] | [ 1396.82 ] 1,674 | [15 empty] | 21918 |  |  |  | 2,000 5,409 31,001
31000.94 | [5 empty] | 1 EA | [22 empty] | 1674.24 | [15 empty] | 21917.7 |  |  |  | 2,000.00 5,409.00 31,000.94
BID ITEM = 522 CLIENT# = 522 Land Item SCHEDULE: 1 100
Description = | [5 empty] | KCM POWER PEDESTAL | [13 empty] | Unit = EA Takeoff Quan: 15.000 Engr Quan: 15.000
522.01 | [5 empty] | KCM POWER PEDESTAL | [13 empty] | Quan: 15.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 15.00 EA | [7 empty] | 5750 | [21 empty] | 86250 |  |  |  | 86250
BID ITEM = 523 CLIENT# = 523 Land Item SCHEDULE: 1 100 Description = KCM POWER PEDESTAL WITH STEP-DOWN TRANSF Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
523.01 KCM POWER PEDESTAL WITH STEP-DOWN TR Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 3.00 EA 5,630.000 16,890 16,890
BID ITEM = 524 CLIENT# = 524 Land Item SCHEDULE: 1 100
Description = | [5 empty] | FOUNDATION, KCM POWER PEDESTAL | [24 empty] | Unit = |  |  | EA Takeoff Quan: 15.000 Engr Quan: 15.000
524.01 | [5 empty] | FOUNDATION, KCM POWER PEDESTAL | [24 empty] | Quan: |  |  | 15.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 15.00 EA | [7 empty] | 4110 | [21 empty] | 61650 |  |  |  | 61650
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 525 CLIENT# = 525 Land Item SCHEDULE: 1 100 Description = FOUNDATION, KCM POWER PEDESTAL WITH STEP Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
525.01 FOUNDATION, KCM POWER PEDESTAL WITH S Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 3.00 EA 4,110.000 12,330 12,330
BID ITEM = 526 CLIENT# = 526 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, SPRING ST & 3RD AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
526.01 KCM STATION WIRING, SPRING ST & 3RD AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,800.000 3,800 3,800
BID ITEM = 527 CLIENT# = 527 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, SPRING ST & 4TH AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
527.01 KCM STATION WIRING, SPRING ST & 4TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,900.000 1,900 1,900
BID ITEM = 528 CLIENT# = 528 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, SPRING ST & 8TH AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
528.01 KCM STATION WIRING, SPRING ST & 8TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,300.000 1,300 1,300
BID ITEM = 529 CLIENT# = 529 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON ST & 3RD AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
529.01 KCM STATION WIRING, MADISON ST & 3RD AV Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,800.000 1,800 1,800
BID ITEM = 530 CLIENT# = 530 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 5TH AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
530.01 KCM STATION WIRING, MADISON & 5TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,400.000 1,400 1,400
BID ITEM | [5 empty] | = |  | 531 |  |  |  |  | CLIENT# = 531 | [15 empty] | Land Item SCHEDULE: 1 | [18 empty] | 100
Description = | [7 empty] | KCM STATION |  |  |  |  | WIRING, MADISON & 8TH AVE | [15 empty] | Unit = LS Takeoff Quan: | [21 empty] | 1 |  | Engr Quan: |  |  |  | 1
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 531 CLIENT# = 531 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 8TH AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
531.01 KCM STATION WIRING, MADISON & 8TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,300.000 1,300 1,300
BID ITEM = 532 CLIENT# = 532 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & TERRY AVE Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
532.01 KCM STATION WIRING, MADISON & TERRY AV Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 3,400.000 3,400 3,400
BID ITEM = 533 CLIENT# = 533 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & BOYLSTON A Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
533.01 KCM STATION WIRING, MADISON & BOYLSTO Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 6,900.000 6,900 6,900
BID ITEM = 534 CLIENT# = 534 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & E UNION ST Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
534.01 KCM STATION WIRING, MADISON & E UNION S Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 7,100.000 7,100 7,100
BID ITEM = 535 CLIENT# = 535 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 17TH AVE W Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
535.01 KCM STATION WIRING, MADISON & 17TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 4,900.000 4,900 4,900
BID ITEM = 536 CLIENT# = 536 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 17TH AVE E Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
536.01 KCM STATION WIRING, MADISON & 17TH AVE Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,600.000 1,600 1,600
BID ITEM | [5 empty] | = |  | 537 |  |  |  |  | CLIENT# = 537 Land Item SCHEDULE: 1 | [34 empty] | 100
Description = | [7 empty] | KCM STATION |  |  |  |  | WIRING, MADISON & E DENNY WA Unit = LS Takeoff Quan: | [37 empty] | 1 |  | Engr Quan: |  |  |  | 1
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 537 CLIENT# = 537 Lan KCM STATION WIRING, MADISON & E DENNY WA | [24 empty] | d Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
537.01 | [5 empty] | KCM STATION WIRING, MADISON & E DENNY | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 2,200.000 2,200 2,200
BID ITEM = 538 CLIENT# = 538 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & E DENNY WA Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 3,100.000 3,100 3,100
BID ITEM = 539 CLIENT# = 539 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 23RD AVE W Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 1,600.000 1,600 1,600
BID ITEM = 540 CLIENT# = 540 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 24TH AVE E Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 2,600.000 2,600 2,600
BID ITEM = 541 CLIENT# = 541 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & MLK BLVD W Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
541.01 KCM STATION WIRING, MADISON & MLK BLVD Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC Electrical sub 1.00 1.00 LS 1,900.000 1,900 1,900
BID ITEM = 542 CLIENT# = 542 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, MADISON & 27TH AVE E Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
4ELEC Electrical sub 1.00 1.00 LS 3,100.000 3,100 3,100
BID ITEM = 543 CLIENT# = 543 Land Item SCHEDULE: 1 100 Description = KCM STATION WIRING, 1ST AVE NB Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 543 CLIENT# = 543 KCM STATION WIRING, 1ST AVE NB | [20 empty] | Land Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
543.01 | [5 empty] | KCM STATION WIRING, 1ST AVE NB | [20 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 1800 | [8 empty] | 1800 | [16 empty] | 1800
BID ITEM = 544 CLIENT# = 544 Land Item SCHEDULE: 1 100 Description = YELLOW DETECTABLE GUIDANCE STRIP Unit = LF Takeoff Quan: 134.000 Engr Quan: 134.000
4STRI Striping sub 1.00 134.00 LF 25.000 3,350 3,350
BID ITEM = 545 CLIENT# = 545 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ADJUST EXISTING SCL VAULT ACCESS | [22 empty] | Unit = EA Takeoff Quan: 15.000 Engr Quan: 15.000
545.01 | [5 empty] | ADJUST EXISTING SCL VAULT ACCESS | [22 empty] | Quan: 15.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 15 |  | CH | Prod: | [8 empty] | 15.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 15.00 HR | [5 empty] | 51.051 | [19 empty] | 766 | [5 empty] | 766
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 15.00 HR | [5 empty] | 52.3 | [19 empty] | 784 | [5 empty] | 784
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 15.00 MH | [5 empty] | 77.06 | [11 empty] | 1510 | [13 empty] | 1510
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 30.00 MH | [5 empty] | 52.91 | [11 empty] | 2093 | [13 empty] | 2093
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 15.00 MH | [5 empty] | 74.56 | [11 empty] | 1462 | [13 empty] | 1462
$6,614.52 4.0000 MH/EA 60.00 MH | [28 empty] | [ 283.184 ] | [11 empty] | 5064 | [7 empty] | 1550 | [5 empty] | 6615
=====> Item Totals: 545 - ADJUST EXISTING SCL VAULT ACCESS $6,614.52 4.0000 MH/EA 440.968 15 EA
60.00 MH | [30 empty] | [ 283.184 ] | [8 empty] | 5064 | [12 empty] | 1550 |  |  |  | 6615
[40 empty] | 337.62 | [12 empty] | 103.35 |  |  |  | 440.97
BID ITEM = 546 CLIENT# = 546 Land Item SCHEDULE: 1 100 Description = ARTWORK FOUNDATION Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
COM Concrete 6 Man Crew 24.00 CH Prod: 24.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR040 4000LB READY M@110.2 1.00 8.00 CY | [30 empty] | 121.15 | [6 empty] | 1069 | [14 empty] | 1069
2REBARART ART FOUNDATION@110 1.00 1.00 LS | [30 empty] | 2500 | [6 empty] | 2756 | [14 empty] | 2756
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 120.00 MH | [7 empty] | 64.98 | [6 empty] | 10224 | [6 empty] | 10224
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 24.00 MH | [7 empty] | 68.98 | [6 empty] | 2168 | [6 empty] | 2168
$16,216.01 144.0000 MH/LS 144.00 MH [ 10398.43 ] | [37 empty] | 12391 | [6 empty] | 3825 | [7 empty] | 16216
=====> Item Totals: 546 - ARTWORK FOUNDATION $16,216.01 144.0000 MH/LS 144.00 MH [ 10398.43 ] | [37 empty] | 12391 | [6 empty] | 3825 | [7 empty] | 16216
16,216.010 1 LS 12,391.22 3,824.79 16,216.01
BID ITEM = 547 CLIENT# = 547 Land Item SCHEDULE: 1 100 Description = PONY BAR RAMP Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 547 CLIENT# = 547 Land Item SCHEDULE: 1 100 Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | PONY BAR RAMP | [23 empty] | Unit = LS
547.01 |  |  | PONY BAR RAMP | [23 empty] | Quan: 1.0
COM 2PONYRAMP |  |  | Concrete 6 Man Crew PONY BAR RAMP@110.2 1.00 | [13 empty] | 1.00 LS | [7 empty] | 16 |  | CH Pr 5,000.000
od:
16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
5513 | [56 empty] | 5513
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 80.00 MH | [7 empty] | 64.98 | [6 empty] | 6816 | [6 empty] | 6816
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 68.98 | [6 empty] | 1445 | [6 empty] | 1445
$13,773.32 96.0000 MH/LS 96.00 MH [ 6932.29 ] | [37 empty] | 8261 | [6 empty] | 5513 | [7 empty] | 13773
=====> Item Totals: 547 - PONY BAR RAMP $13,773.32 96.0000 MH/LS 96.00 MH [ 6932.29 ] | [37 empty] | 8261 | [6 empty] | 5513 | [7 empty] | 13773
13,773.320 1 LS 8,260.82 5,512.50 13,773.32
BID ITEM = 548 CLIENT# = 548 Land Item SCHEDULE: 1 100
Description = |  |  | MOBILIZATION-SCHEDULE 2 | [23 empty] | Unit = |  |  | LS Takeoff Quan: 1.000 Engr Quan: 1.000
548.01 |  |  | MOBILIZATION-SCHEDULE 2 | [23 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
There are no cost resources for this activity.
=====> Item Totals: 548 - MOBILIZATION-SCHEDULE 2 $0.00 [ ] 0.000 1 LS
BID ITEM = 549 CLIENT# = 549 Land Item SCHEDULE: 1 100 Description = SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN Unit = SF Takeoff Quan: 50,405.000 Engr Quan: 50,405.000
549.01 SAFETY SYSTEMS IN TRENCH EXCAVATION, M Quan: 50,405.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3SHORING shoring water line 1.00 1.00 LS 100,000.000
100000 | [8 empty] | 100000
TION, MIN 100,000 | [8 empty] | 100000
1.98 | [8 empty] | 1.98
=====> Item Totals: 549 - SAFETY SYSTEMS IN TRENCH EXCAVA $100,000.00 [ ] 1.984 50405 SF
BID ITEM = 550 CLIENT# = 550 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [24 empty] | Unit = TN Takeoff Quan: 4,520.000 Engr Quan: 4,520.000
550.01 | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [24 empty] | Quan: 4,520.00 TN Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [12 empty] | 1 |  |  |  | 4,520.00 TON | [7 empty] | 25.75 | [6 empty] | 116390 | [14 empty] | 116390
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [12 empty] | 1 |  |  |  | 3,616.00 TCY | [7 empty] | 24.5 | [17 empty] | 88592 |  |  |  | 88592
204982 | [30 empty] | [ ] | [6 empty] | 116390 | [10 empty] | 88592 |  |  |  | 204982
=====> Item Totals: $204,982.00 | [10 empty] | 550 |  |  | - |  |  |  |  | MINERAL AGGREGATE, TYPE 17 | [16 empty] | [ ] |  | 116390 | [10 empty] | 88592 |  |  |  | 204982
45.35 | [13 empty] | 4520 TN | [23 empty] | 25.75 | [10 empty] | 19.6 |  |  |  | 45.35
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  | Unit Cost | [12 empty] | Perm Constr Labor Material Matl/Exp | [10 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 551 CLIENT# = 551 Description = MAINTENANCE HOLE, TYPE 204A | [26 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
551.01 | [5 empty] | MAINTENANCE HOLE, TYPE 204A | [20 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 5.3 | [7 empty] | CH | Prod: | [9 empty] | 5.3000 CH | [6 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSMH204A | [5 empty] | TYPE 204A MAINTENAN | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 1796 | [15 empty] | 1796 | [9 empty] | 1796
2CPSZ230 | [5 empty] | TYPE 230 CASTING SEW | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 785 | [15 empty] | 785 | [9 empty] | 785
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 5.00 TCY | [5 empty] | 29 | [19 empty] | 145 | [5 empty] | 145
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 5.30 HR | [5 empty] | 68.251 | [23 empty] | 362 |  | 362
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 5.30 HR | [5 empty] | 78 | [23 empty] | 413 |  | 413
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 5.30 HR | [5 empty] | 81.5 | [23 empty] | 432 |  | 432
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 5.30 MH | [5 empty] | 77.06 | [12 empty] | 533 | [12 empty] | 533
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 10.60 MH | [5 empty] | 53.88 | [12 empty] | 753 | [12 empty] | 753
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 5.30 MH | [5 empty] | 74.56 | [12 empty] | 516 | [12 empty] | 516
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 5.30 MH | [5 empty] | 74.56 | [12 empty] | 516 | [12 empty] | 516
$6,252.04 26.5000 MH/EA 26.50 MH | [28 empty] | [ 1946.86 ] | [12 empty] | 2319 |  |  | 2581 |  |  |  | 145 |  |  |  | 1207 |  | 6252
551.02 | [5 empty] | CHANAL MH | [24 empty] | Quan: |  |  | 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM 2CR040 | [5 empty] | Concrete 6 Man Crew 4000LB READY M@110.2 | [13 empty] | 1 |  |  | 3.00 CY | [5 empty] | 3 |  | CH |  |  | Prod: 3.0000 CH Lab Pcs: 6.00 Eqp Pcs: 0.00 121.500 402 402
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 15.00 MH | [7 empty] | 64.98 | [8 empty] | 1278 | [12 empty] | 1278
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 68.98 | [8 empty] | 271 | [12 empty] | 271
$1,950.76 18.0000 MH/EA 18.00 MH [ 1299.8 ]
1549 | 402 | [16 empty] | 1951
3868 | 2983 |  |  | 145 |  |  |  |  | 1207 | [8 empty] | 8203
=====> Item Totals: 551 - MAINTENANCE HOLE, TYPE 204A $8,202.80 44.5000 MH/EA 44.50 MH [ 3246.66 ] 8,202.800 1 EA 3,867.89 2,982.86 145.00 1,207.05 8,202.80
BID ITEM = 552 CLIENT# = 552 Land Item SCHEDULE: 1 100 Description = EXTRA DEPTH, TYPE 204A MAINTENANCE HOLE Unit = VF Takeoff Quan: 3.000 Engr Quan: 3.000
552.01 EXTRA DEPTH, TYPE 204A MAINTENANCE HOL Quan: 3.00 VF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 3.00 CH Prod: 3.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CPSED204 EXTRA DEPTH MH 204 1.00 3.00 LF 1.000 3 | [56 empty] | 3
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 68.251 | [17 empty] | 205 | [5 empty] | 205
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 78 | [17 empty] | 234 | [5 empty] | 234
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 3.00 HR | [7 empty] | 81.5 | [17 empty] | 244 | [5 empty] | 244
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 77.06 | [8 empty] | 302 | [14 empty] | 302
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 6.00 MH | [7 empty] | 53.88 | [8 empty] | 426 | [14 empty] | 426
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [14 empty] | 292
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 3.00 MH | [7 empty] | 74.56 | [8 empty] | 292 | [14 empty] | 292
$1,998.88 5.0000 MH/VF | [22 empty] | 15.00 MH | [7 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 3 |  |  |  | 683 | [5 empty] | 1999
=====> Item Totals: 552 - EXTRA DEPTH, TYPE 204A MAINTENANCE HOLE
1998.88 | [5 empty] | 5.0000 MH/VF | [13 empty] | 15.00 MH | [10 empty] | [ 367.337 ] | [8 empty] | 1313 |  |  |  |  | 3 |  |  |  | 683 | [5 empty] | 1999
666.293 | [5 empty] | 3 VF | [33 empty] | 437.55 |  |  |  |  | 1 |  |  |  | 227.74 | [5 empty] | 666.29
BID ITEM = 553 CLIENT# = 553 Land Item SCHEDULE: 1 100
Description = |  |  | TEMPORARY WATER MAINS AND SERVICES | [23 empty] | Unit = |  |  | LS Takeoff Quan: 1.000 Engr Quan: 1.000
553.01 |  |  | STAGE 2 TEMP WATER MAIN | [23 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 553 CLIENT# = 553 Land Item SCHEDULE: 1 100 Description = TEMPORARY WATER MAINS AND SERVICES Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 UNS Underground Utilities 4 Man 74.00 CH Prod: 74.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 74.00 HR | [5 empty] | 51.051 | [23 empty] | 3778 |  |  |  | 3778
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 74.00 HR | [5 empty] | 52.3 | [23 empty] | 3870 |  |  |  | 3870
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 74.00 MH | [5 empty] | 77.06 | [11 empty] | 7448 | [15 empty] | 7448
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 74.00 MH | [5 empty] | 53.88 | [11 empty] | 5254 | [15 empty] | 5254
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 74.00 MH | [5 empty] | 74.56 | [11 empty] | 7211 | [15 empty] | 7211
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 74.00 MH | [5 empty] | 74.56 | [11 empty] | 7211 | [15 empty] | 7211
$34,772.54 296.0000 MH/LS | [22 empty] | 296.00 MH | [5 empty] | [ 22796.87 ] | [11 empty] | 27125 | [11 empty] | 7648 |  |  |  | 34773
553.02 | [5 empty] | STAGE 3 TEMP WATER MAIN | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 60.00 CH Prod: 60.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 60.00 HR | [5 empty] | 51.051 | [23 empty] | 3063 |  |  |  | 3063
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 60.00 HR | [5 empty] | 52.3 | [23 empty] | 3138 |  |  |  | 3138
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 77.06 | [11 empty] | 6039 | [15 empty] | 6039
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 53.88 | [11 empty] | 4260 | [15 empty] | 4260
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 74.56 | [11 empty] | 5847 | [15 empty] | 5847
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 74.56 | [11 empty] | 5847 | [15 empty] | 5847
$28,193.96 240.0000 MH/LS | [22 empty] | 240.00 MH | [5 empty] | [ 18483.96 ] | [11 empty] | 21993 | [11 empty] | 6201 |  |  |  | 28194
553.03 | [5 empty] | STAGE 4 TEMP WATER MAIN | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 32.00 CH Prod: 32.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 51.051 | [23 empty] | 1634 |  |  |  | 1634
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 52.3 | [23 empty] | 1674 |  |  |  | 1674
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 77.06 | [11 empty] | 3221 | [15 empty] | 3221
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 53.88 | [11 empty] | 2272 | [15 empty] | 2272
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [11 empty] | 3118 | [15 empty] | 3118
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [11 empty] | 3118 | [15 empty] | 3118
$15,036.77 128.0000 MH/LS | [22 empty] | 128.00 MH | [5 empty] | [ 9858.11 ] | [11 empty] | 11730 | [11 empty] | 3307 |  |  |  | 15037
553.04 | [5 empty] | STAGE 5 TEMP WATER MAIN | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 60.00 CH Prod: 60.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 60.00 HR | [5 empty] | 51.051 | [23 empty] | 3063 |  |  |  | 3063
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 60.00 HR | [5 empty] | 52.3 | [23 empty] | 3138 |  |  |  | 3138
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 77.06 | [11 empty] | 6039 | [15 empty] | 6039
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 53.88 | [11 empty] | 4260 | [15 empty] | 4260
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 74.56 | [11 empty] | 5847 | [15 empty] | 5847
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 60.00 MH | [5 empty] | 74.56 | [11 empty] | 5847 | [15 empty] | 5847
$28,193.96 240.0000 MH/LS | [22 empty] | 240.00 MH | [5 empty] | [ 18483.96 ] | [11 empty] | 21993 | [11 empty] | 6201 |  |  |  | 28194
553.05 | [5 empty] | STAGE 6 TEMP WATER MAIN | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 40.00 CH Prod: 40.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 51.051 | [23 empty] | 2042 |  |  |  | 2042
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 52.3 | [23 empty] | 2092 |  |  |  | 2092
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 77.06 | [11 empty] | 4026 | [15 empty] | 4026
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 53.88 | [11 empty] | 2840 | [15 empty] | 2840
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [11 empty] | 3898 | [15 empty] | 3898
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [11 empty] | 3898 | [15 empty] | 3898
$18,795.98 160.0000 MH/LS | [22 empty] | 160.00 MH | [5 empty] | [ 12322.64 ] | [11 empty] | 14662 | [11 empty] | 4134 |  |  |  | 18796
553.06 | [5 empty] | STAGE 9 TEMP WATER MAIN | [24 empty] | Quan: |  |  | 1.00 LS | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 56 | [7 empty] | CH |  |  | Prod: | [6 empty] | 56.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 56.00 HR | [5 empty] | 51.051 | [23 empty] | 2859 |  |  |  | 2859
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 56.00 HR | [5 empty] | 52.3 | [23 empty] | 2929 |  |  |  | 2929
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 56.00 MH | [5 empty] | 77.06 | [11 empty] | 5636 | [15 empty] | 5636
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 553 CLIENT# = 553 Land Item SCHEDULE: 1 100 Description = TEMPORARY WATER MAINS AND SERVICES Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 56.00 MH | [7 empty] | 53.88 | [8 empty] | 3976 | [12 empty] | 3976
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 56.00 MH | [7 empty] | 74.56 | [8 empty] | 5457 | [12 empty] | 5457
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 56.00 MH | [7 empty] | 74.56 | [8 empty] | 5457 | [12 empty] | 5457
$26,314.35 224.0000 MH/LS | [22 empty] | 224.00 MH | [7 empty] | [ 17251.71 ] | [8 empty] | 20527 | [12 empty] | 5788 |  |  |  | 26314
553.07 TEMPORARY WATERMAIN MATERIALS Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2BI553PIPE | [5 empty] | BID ITEM 553 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 45000 | [8 empty] | 45000 | [8 empty] | 45000
3FUSIONMACHI FUSHION MACHINE | [19 empty] | 1 |  |  | 1.00 LS | [7 empty] | 5000 | [17 empty] | 5000 |  |  |  | 5000
3TEMPWATMIS MISS TEMP WATER PAR | [19 empty] | 1 |  |  | 1.00 LS | [7 empty] | 10000 | [17 empty] | 10000 |  |  |  | 10000
60000 | [30 empty] | [ ] | [8 empty] | 45000 | [8 empty] | 15000 |  |  |  | 60000
=====> Item Totals: 553 - TEMPORARY WATER MAINS AND SERVICES | [41 empty] | 15,000 33,279 211,308 15,000.00 33,278.99 211,307.56
211307.56 | [5 empty] | 1,288.0000 MH/LS | [16 empty] | 1,288.00 MH | [7 empty] | [ 99197.25 ] 118,029 | [13 empty] | 45000
211307.56 | [5 empty] | 1 LS | [24 empty] | 118028.57 | [13 empty] | 45000
BID ITEM | [5 empty] | = |  | 554 |  | CLIENT# = | [12 empty] | 554 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [7 empty] | 1 100
Description = | [5 empty] | PIPE, WM, D.I., CL 52, 12 IN, RJ, INCL. | [22 empty] | Unit = |  |  |  |  | LF Takeoff Quan: 3,964.000 Engr Quan: 3,964.000
554.01 | [5 empty] | PIPE, WM, D.I., CL 52, 12 IN, RJ, INCL. | [22 empty] | Quan: |  |  |  |  | 3,964.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 481 | [7 empty] | CH |  |  | Prod: | [7 empty] | 481.0000 CH | [6 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI554PIPE | [5 empty] | BID ITEM 554 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 328379.28 | [15 empty] | 328379 | [9 empty] | 328379
2JB12IN | [5 empty] | JOINT BONDING 12 IN PI | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 29930 | [15 empty] | 29930 | [9 empty] | 29930
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 481.00 HR | [5 empty] | 68.251 | [19 empty] | 32829 | [5 empty] | 32829
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 481.00 HR | [5 empty] | 78 | [19 empty] | 37518 | [5 empty] | 37518
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 481.00 HR | [5 empty] | 81.5 | [19 empty] | 39201 | [5 empty] | 39201
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 481.00 MH | [5 empty] | 77.06 | [10 empty] | 48411 | [14 empty] | 48411
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 962.00 MH | [5 empty] | 53.88 | [10 empty] | 68303 | [14 empty] | 68303
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 481.00 MH | [5 empty] | 74.56 | [10 empty] | 46873 | [14 empty] | 46873
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 481.00 MH | [5 empty] | 74.56 | [10 empty] | 46873 | [14 empty] | 46873
678318.7 | [5 empty] | 0.6067 MH/ LF | [16 empty] | 2,405.00 MH [ 44.573 ] 210,461 358,309 109,548 678,319
554.02 | [5 empty] | FLUSHING AND TESTING | [16 empty] | Quan: 9.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 144 | [7 empty] | CH | Prod: | [7 empty] | 144.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3TESTMAT | [5 empty] | TESTING MATERIAL | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 5000 | [17 empty] | 5000 | [5 empty] | 5000
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 144.00 HR | [7 empty] | 68.251 | [21 empty] | 9828 |  | 9828
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 144.00 HR | [7 empty] | 78 | [21 empty] | 11232 |  | 11232
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 144.00 HR | [7 empty] | 81.5 | [21 empty] | 11736 |  | 11736
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 144.00 MH | [7 empty] | 77.06 | [8 empty] | 14493 | [14 empty] | 14493
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 288.00 MH | [7 empty] | 53.88 | [8 empty] | 20448 | [14 empty] | 20448
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 144.00 MH | [7 empty] | 74.56 | [8 empty] | 14033 | [14 empty] | 14033
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 144.00 MH | [7 empty] | 74.56 | [8 empty] | 14033 | [14 empty] | 14033
$100,803.23 80.0000 MH/EA 720.00 MH | [30 empty] | [ 5877.342 ] | [8 empty] | 63007 | [8 empty] | 5000 |  |  |  | 32796 |  | 100803
=====> Item Totals: 554 - PIPE, WM, D.I., CL 52, 12 IN, RJ, INCL.
$779,121.93 0.7883 MH/ LF 3,125.00 MH | [30 empty] | [ 57.917 ] | [8 empty] | 273468 |  |  |  |  | 358309 |  |  |  | 5000 |  |  |  | 142344 |  | 779122
196.549 3964 LF | [39 empty] | 68.99 |  |  |  |  | 90.39 |  |  |  | 1.26 |  |  |  | 35.91 |  | 196.55
BID ITEM = 555 CLIENT# = 555 Land Item SCHEDULE: 1 100 Description = PIPE, WM, D.I., CL 52, 16 IN, RJ, INCL. Unit = LF Takeoff Quan: 1,000.000 Engr Quan: 1,000.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 555 CLIENT# = 555 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, WM, D.I., CL 52, 16 IN, RJ, INCL. | [22 empty] | Unit = |  |  |  |  | LF Takeoff Quan: 1,000.000 Engr Quan: 1,000.000
555.01 | [5 empty] | PIPE, WM, D.I., CL 52, 16 IN, RJ, INCL. | [22 empty] | Quan: |  |  |  |  | 1,000.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 140 |  | CH |  |  | Prod: | [5 empty] | 140.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI555PIPE | [5 empty] | BID ITEM 555 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 123334.65 | [15 empty] | 123335 | [9 empty] | 123335
2JB16IN | [5 empty] | JOINT BONDING 16 INC | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 10000 | [15 empty] | 10000 | [9 empty] | 10000
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 140.00 HR | [5 empty] | 68.251 | [19 empty] | 9555 | [5 empty] | 9555
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 140.00 HR | [5 empty] | 78 | [19 empty] | 10920 | [5 empty] | 10920
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 140.00 HR | [5 empty] | 81.5 | [19 empty] | 11410 | [5 empty] | 11410
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 140.00 MH | [5 empty] | 77.06 | [10 empty] | 14091 | [14 empty] | 14091
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 280.00 MH | [5 empty] | 53.88 | [10 empty] | 19880 | [14 empty] | 19880
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 140.00 MH | [5 empty] | 74.56 | [10 empty] | 13643 | [14 empty] | 13643
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 140.00 MH | [5 empty] | 74.56 | [10 empty] | 13643 | [14 empty] | 13643
226476.68 | [5 empty] | 0.7000 MH/ LF | [16 empty] | 700.00 MH [ 51.427 ] 61,257 133,335 31,885 226,477
555.02 | [5 empty] | FLUSHING AND TESTING | [16 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 16 | [7 empty] | CH | Prod: | [7 empty] | 16.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 68.251 | [17 empty] | 1092 | [5 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 78 | [17 empty] | 1248 | [5 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 81.5 | [17 empty] | 1304 | [5 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 77.06 | [8 empty] | 1610 | [14 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [7 empty] | 53.88 | [8 empty] | 2272 | [14 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [14 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [14 empty] | 1559
$10,644.79 80.0000 MH/EA 80.00 MH | [30 empty] | [ 5877.36 ] | [8 empty] | 7001 | [8 empty] | 3644 | [5 empty] | 10645
=====> Item Totals: 555 - PIPE, WM, D.I., CL 52, 16 IN, RJ, INCL.
$237,121.47 0.7800 MH/ LF 780.00 MH | [30 empty] | [ 57.304 ] | [8 empty] | 68258 |  |  |  |  | 133335 |  |  |  | 35529 | [5 empty] | 237121
237.121 1000 LF | [39 empty] | 68.26 |  |  |  |  | 133.33 |  |  |  | 35.53 | [5 empty] | 237.12
BID ITEM = 556 CLIENT# = 556 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, WM, D.I., CL 52, 20 IN, RJ, INCL. | [22 empty] | Unit = LF Takeoff Quan: 319.000 Engr Quan: 319.000
556.01 | [5 empty] | PIPE, WM, D.I., CL 52, 20 IN, RJ, INCL. | [22 empty] | Quan: 319.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 48 |  | CH | Prod: | [7 empty] | 48.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI556PIPE | [5 empty] | BID ITEM 556 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 77793.58 | [15 empty] | 77794 | [9 empty] | 77794
2JB20IN | [5 empty] | JOINT BONDING 20 IN PI | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 1216 | [15 empty] | 1216 | [9 empty] | 1216
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 48.00 HR | [5 empty] | 68.251 | [19 empty] | 3276 | [5 empty] | 3276
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 48.00 HR | [5 empty] | 78 | [19 empty] | 3744 | [5 empty] | 3744
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 48.00 HR | [5 empty] | 81.5 | [19 empty] | 3912 | [5 empty] | 3912
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 48.00 MH | [5 empty] | 77.06 | [10 empty] | 4831 | [14 empty] | 4831
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 96.00 MH | [5 empty] | 53.88 | [10 empty] | 6816 | [14 empty] | 6816
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 48.00 MH | [5 empty] | 74.56 | [10 empty] | 4678 | [14 empty] | 4678
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 48.00 MH | [5 empty] | 74.56 | [10 empty] | 4678 | [14 empty] | 4678
$110,943.99 0.7523 MH/ LF 240.00 MH | [28 empty] | [ 55.273 ] | [10 empty] | 21002 |  |  |  |  | 79010 |  |  |  | 10932 | [5 empty] | 110944
556.02 | [5 empty] | FLUSHING AND TESTING 20 IN | [24 empty] | Quan: |  |  | 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 16 | [7 empty] | CH |  |  | Prod: 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 68.251 | [15 empty] | 1092 | [9 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 78 | [15 empty] | 1248 | [9 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 81.5 | [15 empty] | 1304 | [9 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 77.06 | [10 empty] | 1610 | [14 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [5 empty] | 53.88 | [10 empty] | 2272 | [14 empty] | 2272
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 556 CLIENT# = 556 Land Item SCHEDULE: 1 100 Description = PIPE, WM, D.I., CL 52, 20 IN, RJ, INCL. Unit = LF Takeoff Quan: 319.000 Engr Quan: 319.000
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [12 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [12 empty] | 1559
$10,644.79 80.0000 MH/EA 80.00 MH | [30 empty] | [ 5877.36 ] | [8 empty] | 7001 | [12 empty] | 3644 |  |  |  | 10645
=====> Item Totals: 556 - PIPE, WM, D.I., CL 52, 20 IN, RJ, INCL. $121,588.78 1.0031 MH/ LF 381.156 319 LF
320.00 MH | [30 empty] | [ 73.697 ] | [8 empty] | 28003 |  |  |  |  | 79010 | [7 empty] | 14576 |  |  |  | 121589
[40 empty] | 87.78 |  |  |  |  | 247.68 | [7 empty] | 45.69 |  |  |  | 381.16
BID ITEM = 557 CLIENT# = 557 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, WATER MAIN, CL B, 8 IN PIPE | [24 empty] | Unit = |  |  | LF Takeoff Quan: 318.000 Engr Quan: 318.000
557.01 | [5 empty] | BEDDING, WATER MAIN, CL B, 8 IN PIPE | [24 empty] | Quan: |  |  | 318.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [11 empty] | 1 |  |  |  |  | 233.00 TON | [7 empty] | 29.75 | [6 empty] | 6932 | [14 empty] | 6932
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [11 empty] | 1 |  |  |  |  | 170.00 TCY | [7 empty] | 24.5 | [17 empty] | 4165 |  |  |  | 4165
11096.75 | [30 empty] | [ ] | [6 empty] | 6932 | [10 empty] | 4165 |  |  |  | 11097
=====> Item Totals: | [10 empty] | 557 | [6 empty] | - BEDDING, WATER MAIN, CL B, 8 IN PIPE
11096.75 | [17 empty] | [ ] | [19 empty] | 6932 | [10 empty] | 4165 |  |  |  | 11097
34.895 | [13 empty] | 318 LF | [23 empty] | 21.8 | [10 empty] | 13.1 |  |  |  | 34.9
BID ITEM = 558 CLIENT# = 558 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, WATER MAIN, CL B, 12 IN PIPE | [24 empty] | Unit = |  |  | LF Takeoff Quan: 5,128.000 Engr Quan: 5,128.000
558.01 | [5 empty] | BEDDING, WATER MAIN, CL B, 12 IN PIPE | [24 empty] | Quan: |  |  | 5,128.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 3,621.00 TON | [7 empty] | 29.75 | [8 empty] | 107725 | [12 empty] | 107725
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 2,735.00 TCY | [7 empty] | 24.5 | [17 empty] | 67008 |  |  |  | 67008
174732.25 | [30 empty] | [ ] | [8 empty] | 107725 | [8 empty] | 67008 |  |  |  | 174732
=====> Item Totals: 558 - BEDDING, WATER MAIN, CL B, 12 IN PIPE
174732.25 | [19 empty] | [ ] | [19 empty] | 107725 | [8 empty] | 67008 |  |  |  | 174732
34.074 | [5 empty] | 5128 LF | [33 empty] | 21.01 | [8 empty] | 13.07 |  |  |  | 34.07
BID ITEM = 559 CLIENT# = 559 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, WATERMAIN, CL B, 16 IN PIPE | [24 empty] | Unit = |  |  | LF Takeoff Quan: 1,000.000 Engr Quan: 1,000.000
559.01 | [5 empty] | BEDDING, WATERMAIN, CL B, 16 IN PIPE | [24 empty] | Quan: |  |  | 1,000.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 668.00 TON | [7 empty] | 29.75 | [8 empty] | 19873 | [12 empty] | 19873
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 532.00 TCY | [7 empty] | 24.5 | [17 empty] | 13034 |  |  |  | 13034
32907 | [30 empty] | [ ] | [8 empty] | 19873 | [8 empty] | 13034 |  |  |  | 32907
=====> Item Totals: 559 - BEDDING, WATERMAIN, CL B, 16 IN PIPE
32907 | [19 empty] | [ ] | [19 empty] | 19873 | [8 empty] | 13034 |  |  |  | 32907
32.907 | [5 empty] | 1000 LF | [33 empty] | 19.87 | [8 empty] | 13.03 |  |  |  | 32.91
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  | Unit Cost | [9 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM Description = | [5 empty] | = 560 CLIENT# = 560 L BEDDING, WATERMAIN, CL B, 20 IN PIPE | [23 empty] | and Item SCHEDULE: 1 100 Unit = LF Takeoff Quan: 319.000 Engr Quan: 319.000
560.01 | [5 empty] | BEDDING, WATERMAIN, CL B, 20 IN PIPE | [23 empty] | Quan: 319.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 324.00 TON | [6 empty] | 29.75 | [9 empty] | 9639 | [12 empty] | 9639
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 259.00 TCY | [6 empty] | 24.5 | [18 empty] | 6346 |  |  |  | 6346
15984.5 | [29 empty] | [ ] | [9 empty] | 9639 | [8 empty] | 6346 |  |  |  | 15985
=====> Item Totals: 560 - BEDDING, WATERMAIN, CL B, 20 IN PIPE
15984.5 | [19 empty] | [ ] | [19 empty] | 9639 | [8 empty] | 6346 |  |  |  | 15985
50.108 | [5 empty] | 319 LF | [33 empty] | 30.22 | [8 empty] | 19.89 |  |  |  | 50.11
BID ITEM = 561 CLIENT# = 561 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BLOCKING, CEMENT CONCRETE | [22 empty] | Unit = CY Takeoff Quan: 63.000 Engr Quan: 63.000
561.01 | [5 empty] | BLOCKING, CEMENT CONCRETE | [22 empty] | Quan: 63.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 50 |  | CH | Prod: | [7 empty] | 50.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2CR040 | [5 empty] | 4000LB READY MIX | [13 empty] | 1.25 |  |  | 78.75 CY | [5 empty] | 121.15 | [15 empty] | 9541 | [9 empty] | 9541
2TBBOLT | [5 empty] | THRUST BLOCK BOLTS | [13 empty] | 1 |  |  | 4.00 EA | [5 empty] | 800 | [15 empty] | 3200 | [9 empty] | 3200
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 50.00 HR | [5 empty] | 68.251 | [19 empty] | 3413 | [5 empty] | 3413
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 50.00 HR | [5 empty] | 78 | [19 empty] | 3900 | [5 empty] | 3900
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 50.00 HR | [5 empty] | 81.5 | [19 empty] | 4075 | [5 empty] | 4075
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 50.00 MH | [5 empty] | 77.06 | [10 empty] | 5032 | [14 empty] | 5032
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 100.00 MH | [5 empty] | 53.88 | [10 empty] | 7100 | [14 empty] | 7100
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 50.00 MH | [5 empty] | 74.56 | [10 empty] | 4873 | [14 empty] | 4873
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 50.00 MH | [5 empty] | 74.56 | [10 empty] | 4873 | [14 empty] | 4873
$46,005.57 3.9682 MH/CY 250.00 MH | [28 empty] | [ 291.535 ] | [10 empty] | 21877 |  |  |  |  | 12741 |  |  |  | 11388 | [5 empty] | 46006
=====> Item Totals: 561 - BLOCKING, CEMENT CONCRETE $46,005.57 3.9682 MH/CY 250.00 MH [ 291.535 ] | [37 empty] | 21877 | [6 empty] | 12741 |  |  |  | 11388 | [5 empty] | 46006
730.247 63 CY | [37 empty] | 347.26 | [6 empty] | 202.23 |  |  |  | 180.75 | [5 empty] | 730.25
BID ITEM = 562 CLIENT# = 562 Land Item SCHEDULE: 1 100
Description = | [5 empty] | STATION, ELECTROLYSIS TEST | [24 empty] | Unit = EA Takeoff Quan: 31.000 Engr Quan: 31.000
562.01 | [5 empty] | STATION, ELECTROLYSIS TEST | [24 empty] | Quan: 31.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 62 |  | CH Prod: 62.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2STELTEST | [5 empty] | STATION ELECTROLOSI 1.00 | [18 empty] | 31.00 EA | [5 empty] | 1,483.620 45,992 45,992
3CERTTEST | [5 empty] | CERTIFIED TESTER | [13 empty] | 1 |  |  |  |  | 31.00 EA |  |  |  | 2414 | [15 empty] | 74834 | [11 empty] | 74834
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 62.00 HR |  |  |  | 68.251 | [23 empty] | 4232 |  |  |  | 4232
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 62.00 HR |  |  |  | 78 | [23 empty] | 4836 |  |  |  | 4836
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 62.00 HR |  |  |  | 81.5 | [23 empty] | 5053 |  |  |  | 5053
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 62.00 MH |  |  |  | 77.06 | [8 empty] | 6240 | [18 empty] | 6240
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 124.00 MH |  |  |  | 53.88 | [8 empty] | 8804 | [18 empty] | 8804
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 62.00 MH |  |  |  | 74.56 | [8 empty] | 6042 | [18 empty] | 6042
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 62.00 MH |  |  |  | 74.56 | [8 empty] | 6042 | [18 empty] | 6042
$162,074.82 10.0000 MH/EA 310.00 MH | [28 empty] | [ 734.668 ] | [8 empty] | 27128 | [6 empty] | 45992 |  |  |  | 74834 |  |  |  | 14121 |  |  |  | 162075
=====> Item Totals: 562 - STATION, ELECTROLYSIS TEST $162,074.82 10.0000 MH/EA 310.00 MH [ 734.668 ] 27,128 | [44 empty] | 45992 |  |  |  | 74834 |  |  |  | 14121 |  |  |  | 162075
5,228.220 31 EA 875.10 1,483.62 | [48 empty] | 2414 |  |  |  | 455.5 |  |  |  | 5228.22
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract Total
BID ITEM = 563 CLIENT# = 563 Land Item SCHEDULE: 1 100 Description = SACRIFICIAL ANODE BONDED TO PIPE Unit = EA Takeoff Quan: 244.000 Engr Quan: 244.000
563.01 | [5 empty] | SACRIFICIAL ANODE BONDED TO PIPE | [24 empty] | Quan: |  |  | 244.00 EA | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 30 | [7 empty] | CH |  |  | Prod: | [6 empty] | 30.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2ANOD | [5 empty] | ANODES | [13 empty] | 1 |  |  | 244.00 EA 253.000 61,732 61,732
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 30.00 HR 68.251 | [21 empty] | 2048 | [11 empty] | 2048
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 30.00 HR 78.000 | [21 empty] | 2340 | [11 empty] | 2340
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 30.00 HR 81.500 | [21 empty] | 2445 | [11 empty] | 2445
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 30.00 MH 77.060 | [17 empty] | 3019 | [15 empty] | 3019
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 60.00 MH 53.880 | [17 empty] | 4260 | [15 empty] | 4260
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 30.00 MH 74.560 | [17 empty] | 2924 | [15 empty] | 2924
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 30.00 MH 74.560 | [17 empty] | 2924 | [15 empty] | 2924
$81,691.00 0.6147 MH/EA 150.00 MH | [22 empty] | [ 45.164 ] | [16 empty] | 13126 |  |  |  |  | 61732 | [7 empty] | 6833 |  |  |  | 81691
=====> Item Totals: 563 - SACRIFICIAL ANODE BONDED TO PIPE
$81,691.00 0.6147 MH/EA 150.00 MH | [22 empty] | [ 45.164 ] | [16 empty] | 13126 |  |  |  |  | 61732 | [7 empty] | 6833 |  |  |  | 81691
334.799 244 EA | [39 empty] | 53.8 |  |  |  |  | 253 | [7 empty] | 28 |  |  |  | 334.8
BID ITEM = 564 CLIENT# = 564 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SUPPORT SPU WITH JOINT CLAMP EXISTING PI | [22 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
264.01 | [5 empty] | JOINT CLAMP 1ST AND MADISON | [22 empty] | Quan: 1.00 LS Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 8 |  | CH |  |  | Prod: | [6 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 10.00 TON | [5 empty] | 29.75 | [15 empty] | 298 | [11 empty] | 298
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  | 20.00 TON | [5 empty] | 25.75 | [15 empty] | 515 | [11 empty] | 515
3VAC | [5 empty] | VACTOR TRUCKS | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 4000 | [19 empty] | 4000 | [7 empty] | 4000
4SAWC | [5 empty] | Sawcutting | [13 empty] | 1 |  |  | 832.00 INFT | [5 empty] | 0.58 | [25 empty] | 483 |  | 483
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 51.051 | [23 empty] | 408 |  |  |  | 408
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 52.3 | [23 empty] | 418 |  |  |  | 418
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [11 empty] | 1092 | [15 empty] | 1092
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 52.91 | [11 empty] | 1510 | [15 empty] | 1510
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [11 empty] | 1057 | [15 empty] | 1057
9780.64 | [5 empty] | 32.0000 MH/LS | [18 empty] | 32.00 MH [ 3089.28 ] 3,659 813 4,000 827 483 9,781
264.02 | [5 empty] | JOINT CLAMP SPRING AND 8TH | [18 empty] | Quan: 1.00 LS Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 8 | [5 empty] | CH | Prod: | [8 empty] | 8.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  |  |  | 10.00 TON | [5 empty] | 29.75 | [13 empty] | 298 | [9 empty] | 298
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  |  |  | 10.00 TON | [5 empty] | 25.75 | [13 empty] | 258 | [9 empty] | 258
3VAC | [5 empty] | VACTOR TRUCKS | [13 empty] | 1 |  |  |  |  | 1.00 LS | [5 empty] | 4000 | [17 empty] | 4000 | [5 empty] | 4000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 8.00 HR | [5 empty] | 51.051 | [21 empty] | 408 |  | 408
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 8.00 HR | [5 empty] | 52.3 | [21 empty] | 418 |  | 418
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 8.00 MH | [5 empty] | 77.06 | [9 empty] | 1092 | [13 empty] | 1092
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 16.00 MH | [5 empty] | 52.91 | [9 empty] | 1510 | [13 empty] | 1510
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 8.00 MH | [5 empty] | 74.56 | [9 empty] | 1057 | [13 empty] | 1057
$9,040.58 32.0000 MH/LS | [24 empty] | 32.00 MH | [5 empty] | [ 3089.28 ] | [9 empty] | 3659 |  |  |  | 555 |  |  |  | 4000 |  |  |  | 827 |  | 9041
264.03 | [5 empty] | JOINT CLAMP MADISON AND 5TH | [24 empty] | Quan: |  |  | 1.00 LS | [6 empty] | Hrs/Shft: 8.00 Cal: S08 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 8 |  | CH |  |  | Prod: | [6 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  |  |  | 10.00 TON |  |  |  | 29.75 | [11 empty] | 298 | [13 empty] | 298
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  |  |  | 10.00 TON |  |  |  | 25.75 | [11 empty] | 258 | [13 empty] | 258
3VAC | [5 empty] | VACTOR TRUCKS | [13 empty] | 1 |  |  |  |  | 1.00 LS |  |  |  | 4000 | [19 empty] | 4000 | [5 empty] | 4000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 8.00 HR |  |  |  | 51.051 | [23 empty] | 408 |  | 408
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 8.00 HR |  |  |  | 52.3 | [23 empty] | 418 |  | 418
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 564 CLIENT# = 564 Land Item SCHEDULE: 1 100 Description = SUPPORT SPU WITH JOINT CLAMP EXISTING PI Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 77.06 | [8 empty] | 1092 | [12 empty] | 1092
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [7 empty] | 52.91 | [8 empty] | 1510 | [12 empty] | 1510
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [8 empty] | 1057 | [12 empty] | 1057
$9,040.58 32.0000 MH/LS 32.00 MH [ 3089.28 ] | [37 empty] | 3,659 555 | [10 empty] | 4000 |  |  |  | 827 |  |  |  | 9041
[38 empty] | STING PI 10,976 1,923 | [10 empty] | 12000 |  |  |  | 2480 |  | 483 |  | 27862
=====> Item Totals: 564 - SUPPORT SPU WITH JOINT CLAMP EXI $27,861.80 96.0000 MH/LS 96.00 MH [ 9267.84 ]
27,861.800 1 LS 10,976.34 1,922.50 12,000.00 2,480.40 482.56 27,861.80
BID ITEM = 565 CLIENT# = 565 Land Item SCHEDULE: 1 100 Description = SUPPORT SPU WITH CUT, CAP, AND CONNECT Unit = EA Takeoff Quan: 44.000 Engr Quan: 44.000
565.01 SUPPORT SPU WITH CUT, CAP, AND CONNECT Quan: 44.00 EA Hrs/Shft: 12.00 Cal: 512 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 352 | [10 empty] | CH | Prod: | [7 empty] | 352.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 195.00 TON | [7 empty] | 29.75 | [13 empty] | 5801 | [9 empty] | 5801
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  | 443.00 TON | [7 empty] | 25.75 | [13 empty] | 11407 | [9 empty] | 11407
2BI565PIPE | [5 empty] | BID ITEM 565 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 25000 | [13 empty] | 27563 | [9 empty] | 27563
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 450.00 TCY | [7 empty] | 24.5 | [17 empty] | 11025 | [5 empty] | 11025
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 352.00 HR | [7 empty] | 51.051 | [21 empty] | 17970 |  | 17970
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 352.00 HR | [7 empty] | 52.3 | [21 empty] | 18410 |  | 18410
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 352.00 MH | [7 empty] | 77.06 | [8 empty] | 40159 | [14 empty] | 40159
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 352.00 MH | [7 empty] | 53.88 | [8 empty] | 28300 | [14 empty] | 28300
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 352.00 MH | [7 empty] | 74.56 | [8 empty] | 38880 | [14 empty] | 38880
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 352.00 MH | [7 empty] | 74.56 | [8 empty] | 38880 | [14 empty] | 38880
238393.59 | [5 empty] | 32.0000 MH/EA | [13 empty] | 1,408.00 MH | [10 empty] | [ 2800.6 ] | [8 empty] | 146218 |  |  |  |  | 44771 |  |  |  | 11025 |  |  |  | 36380 |  | 238394
=====> Item Totals: 565 - SUPPORT SPU WITH CUT, CAP, AND CONNECT $238,393.59 32.0000 MH/EA 1,408.00 MH [ 2800.6 ] 146,218 44,771 11,025 36,380 238,394 5,418.036 44 EA 3,323.14 1,017.52 250.57 826.81 5,418.04
BID ITEM = 566 CLIENT# = 566 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, WM, D.I. CL 53 MIN, 8 IN, RJ, POLY | [22 empty] | Unit = LF Takeoff Quan: 318.000 Engr Quan: 318.000
566.01 | [5 empty] | PIPE, WM, D.I. CL 53 MIN, 8 IN, RJ, POLY | [22 empty] | Quan: 318.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 32 |  | CH Prod: 32.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI566PIPE | [5 empty] | BID ITEM 566 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 19,022.220 19,022 19,022
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 68.251 | [15 empty] | 2184 | [11 empty] | 2184
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 78 | [15 empty] | 2496 | [11 empty] | 2496
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 81.5 | [15 empty] | 2608 | [11 empty] | 2608
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 77.06 | [8 empty] | 3412 | [18 empty] | 3412
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 64.00 MH | [5 empty] | 53.88 | [8 empty] | 4811 | [18 empty] | 4811
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [8 empty] | 3303 | [18 empty] | 3303
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [8 empty] | 3303 | [18 empty] | 3303
$41,140.54 0.5031 MH/LF 160.00 MH [ 39.206 ] 14,830 | [44 empty] | 19022 | [7 empty] | 7288 |  |  |  | 41141
=====> Item Totals: 566 - PIPE, WM, D.I. CL 5 $41,140.54 0.5031 MH/LF 160.00 MH | [28 empty] | 3 MIN, 8 IN, RJ, POLY [ 39.206 ] | [8 empty] | 14830 | [6 empty] | 19022 | [7 empty] | 7288 |  |  |  | 41141
129.373 318 LF | [37 empty] | 46.64 | [6 empty] | 59.82 | [7 empty] | 22.92 |  |  |  | 129.37
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 567 CLIENT# = 567 Land Item SCHEDULE: 1 100
Description = |  |  | PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL | [23 empty] | Unit = |  |  | LF Takeoff Quan: 1,164.000 Engr Quan: 1,164.000
567.01 |  |  | PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL | [23 empty] | Quan: |  |  | 1,164.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 127 |  | CH | Prod: | [8 empty] | 127.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI567PIPE | [5 empty] | BID ITEM 567 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [8 empty] | 94606 | [8 empty] | 94606 | [15 empty] | 94606
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 127.00 HR | [5 empty] | 68.251 | [19 empty] | 8668 | [5 empty] | 8668
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 127.00 HR | [5 empty] | 78 | [19 empty] | 9906 | [5 empty] | 9906
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 127.00 HR | [5 empty] | 81.5 | [19 empty] | 10350 | [5 empty] | 10350
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 127.00 MH | [5 empty] | 77.06 | [11 empty] | 13541 | [13 empty] | 13541
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 254.00 MH | [5 empty] | 53.88 | [11 empty] | 19096 | [13 empty] | 19096
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 127.00 MH | [5 empty] | 74.56 | [11 empty] | 13111 | [13 empty] | 13111
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 127.00 MH | [5 empty] | 74.56 | [11 empty] | 13111 | [13 empty] | 13111
$182,388.13 0.5455 MH/LF 635.00 MH [ 42.509 ] 58,858 94,606 28,924 182,388
=====> Item Totals: 567 - PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL $182,388.13 0.5455 MH/LF 156.691 1164 LF
635.00 MH | [30 empty] | [ 42.509 ] | [8 empty] | 58858 |  |  |  |  | 94606 | [7 empty] | 28924 |  |  |  | 182388
[40 empty] | 50.57 |  |  |  |  | 81.28 | [7 empty] | 24.85 |  |  |  | 156.69
BID ITEM = 568 CLIENT# = 568 Land Item SCHEDULE: 1 100 Description = DAILY BLOCK, CEMENT CONCRETE, PRECAST Unit = EA Takeoff Quan: 7.000 Engr Quan: 7.000
568.01 DAILY BLOCK, CEMENT CONCRETE, PRECAST Quan: 7.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 16 | [10 empty] | CH | Prod: | [8 empty] | 16.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2AGS02 | [5 empty] | SEATTLE TYPE 2 | [13 empty] | 1 |  |  | 70.00 TON | [7 empty] | 29.75 | [13 empty] | 2083 | [9 empty] | 2083
2CPSDAILY | [5 empty] | DAILY BLOCK | [13 empty] | 1 |  |  | 7.00 EA | [7 empty] | 750 | [13 empty] | 5250 | [9 empty] | 5250
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 68.251 | [17 empty] | 1092 | [5 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 78 | [17 empty] | 1248 | [5 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 81.5 | [17 empty] | 1304 | [5 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 77.06 | [9 empty] | 1706 | [13 empty] | 1706
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [7 empty] | 53.88 | [9 empty] | 2406 | [13 empty] | 2406
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [9 empty] | 1652 | [13 empty] | 1652
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [9 empty] | 1652 | [13 empty] | 1652
$18,391.65 11.4285 MH/EA 80.00 MH | [30 empty] | [ 890.533 ] | [9 empty] | 7415 |  |  |  | 7333 |  |  |  | 3644 | [5 empty] | 18392
=====> Item Totals: 568 - DAILY BLOCK, CEMENT CONCRETE, PRECAST $18,391.65 11.4285 MH/EA 80.00 MH [ 890.533 ] 7,415 7,333 3,644 18,392 2,627.379 7 EA 1,059.31 1,047.50 520.57 2,627.38
BID ITEM = 569 CLIENT# = 569 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 4 IN Unit = EA Takeoff Quan: 8.000 Engr Quan: 8.000
569.01 | [5 empty] | VALVE, GATE, 4 IN | [24 empty] | Quan: |  |  | 8.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 8 | [7 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI569PIPE | [5 empty] | BID ITEM 569 PIPE 1.00 | [16 empty] | 1.00 LS | [10 empty] | 9165.04 | [7 empty] | 9,165 9,165
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 8.00 HR 68.251 | [29 empty] | 546 |  |  |  | 546
8EX200 | [5 empty] | 200 Excavator 1.00 | [16 empty] | 8.00 HR 78.000 | [29 empty] | 624 |  |  |  | 624
8LO950 | [5 empty] | 950 Loader 1.00 | [16 empty] | 8.00 HR 81.500 | [29 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 8.00 MH 77.060 | [18 empty] | 805 | [14 empty] | 805
LAP | [5 empty] | Labor Underground Water 2.00 | [16 empty] | 16.00 MH 53.880 | [18 empty] | 1136 | [14 empty] | 1136
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 8.00 MH 74.560 | [18 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader 1.00 | [16 empty] | 8.00 MH 74.560 | [18 empty] | 780 | [14 empty] | 780
| Activity Desc Resource | [18 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 569 CLIENT# = 569 Land Item SCHEDULE: 1 100
| Description = VALVE, GATE, 4 IN Unit = | [32 empty] | EA | [5 empty] | Takeoff Quan: | [8 empty] | 8 |  |  |  | Engr Quan: |  |  |  | 8
$14,487.44 5.0000 MH/EA 40.00 MH [ 367.335 ] | [37 empty] | 3500 | [6 empty] | 9165 | [7 empty] | 1822 |  |  |  | 14487
=====> Item Totals: $14,487.44 | [9 empty] | 569 5.0000 MH/EA | [6 empty] | - VALVE, GATE, 4 IN 40.00 MH | [13 empty] | [ 367.335 ] | [6 empty] | 3500 | [6 empty] | 9165 | [7 empty] | 1822 |  |  |  | 14487
1,810.930 8 EA 437.55 1,145.63 227.75 | [56 empty] | 1810.93
BID ITEM = 570 CLIENT# = 570 Land Item SCHEDULE: 1 100
Description = | [5 empty] | VALVE, GATE, 6 IN | [13 empty] | Unit = EA Takeoff Quan: 31.000 Engr Quan: 31.000
570.01 | [5 empty] | VALVE, GATE, 6 IN | [13 empty] | Quan: 31.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 31 |  | CH Prod: 31.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI570PIPE | [5 empty] | BID ITEM 570 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 45,642.230 45,642 45,642
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 31.00 HR | [5 empty] | 68.251 | [15 empty] | 2116 | [11 empty] | 2116
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 31.00 HR | [5 empty] | 78 | [15 empty] | 2418 | [11 empty] | 2418
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 31.00 HR | [5 empty] | 81.5 | [15 empty] | 2526 | [11 empty] | 2526
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 31.00 MH | [5 empty] | 77.06 | [8 empty] | 3120 | [18 empty] | 3120
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 62.00 MH | [5 empty] | 53.88 | [8 empty] | 4402 | [18 empty] | 4402
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 31.00 MH | [5 empty] | 74.56 | [8 empty] | 3021 | [18 empty] | 3021
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 31.00 MH | [5 empty] | 74.56 | [8 empty] | 3021 | [18 empty] | 3021
$66,266.52 5.0000 MH/EA 155.00 MH | [28 empty] | [ 367.335 ] | [8 empty] | 13564 | [6 empty] | 45642 | [7 empty] | 7060 |  |  |  | 66267
=====> Item Totals: | [9 empty] | 570 | [6 empty] | - VALVE, GATE, 6 IN
66266.52 | [9 empty] | 5.0000 MH/EA | [6 empty] | 155.00 MH | [11 empty] | [ 367.335 ] | [8 empty] | 13564 | [6 empty] | 45642 | [7 empty] | 7060 |  |  |  | 66267
2137.63 | [5 empty] | 31 EA | [10 empty] | 437.55 1,472.33 | [35 empty] | 227.75 |  |  |  | 2137.63
BID ITEM = 571 CLIENT# = 571 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 8 IN Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
UNM Unerground Utilities 6 Man 5.00 CH Prod: 5.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI571PIPE BID ITEM 571 PIPE 1.00 1.00 LS 14,639.780 14,640 | [56 empty] | 14640
8EX135A | [5 empty] | 135 Excavator W/Attach | [11 empty] | 1 |  |  |  |  | 5.00 HR | [7 empty] | 68.251 | [17 empty] | 341 | [5 empty] | 341
8EX200 | [5 empty] | 200 Excavator | [11 empty] | 1 |  |  |  |  | 5.00 HR | [7 empty] | 78 | [17 empty] | 390 | [5 empty] | 390
8LO950 | [5 empty] | 950 Loader | [11 empty] | 1 |  |  |  |  | 5.00 HR | [7 empty] | 81.5 | [17 empty] | 407 | [5 empty] | 407
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 |  |  |  |  | 5.00 MH | [7 empty] | 77.06 | [6 empty] | 503 | [16 empty] | 503
LAP | [5 empty] | Labor Underground Water | [11 empty] | 2 |  |  |  |  | 10.00 MH | [7 empty] | 53.88 | [6 empty] | 710 | [16 empty] | 710
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 5.00 MH | [7 empty] | 74.56 | [6 empty] | 487 | [16 empty] | 487
OPL | [5 empty] | Operator - Loader | [11 empty] | 1 |  |  |  |  | 5.00 MH | [7 empty] | 74.56 | [6 empty] | 487 | [16 empty] | 487
$17,966.27 5.0000 MH/EA 25.00 MH | [30 empty] | [ 367.334 ] | [6 empty] | 2188 | [6 empty] | 14640 |  |  |  | 1139 | [5 empty] | 17966
=====> Item Totals: $17,966.27 | [9 empty] | 571 5.0000 MH/EA | [7 empty] | - VALVE, GATE, 8 IN 25.00 MH | [12 empty] | [ 367.334 ] | [6 empty] | 2188 | [6 empty] | 14640 |  |  |  | 1139 | [5 empty] | 17966
3,593.254 5 EA 437.55 2,927.96 227.75 3,593.25
BID ITEM = 572 CLIENT# = 572 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | VALVE, GATE, 12 IN | [24 empty] | Unit = |  |  | EA Takeoff Quan: 26.000 Engr Quan: 26.000
| 572.01 |  |  |  |  | VALVE, GATE, 12 IN | [24 empty] | Quan: |  |  | 26.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 572 CLIENT# = 572 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 12 IN Unit = EA Takeoff Quan: 26.000 Engr Quan: 26.000
UNM 2BI572PIPE | [5 empty] | Unerground Utilities 6 Man BID ITEM 572 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 26 |  | CH Prod: 26.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 127,497.880 127,498 127,498
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 26.00 HR | [5 empty] | 68.251 | [15 empty] | 1775 | [11 empty] | 1775
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 26.00 HR | [5 empty] | 78 | [15 empty] | 2028 | [11 empty] | 2028
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 26.00 HR | [5 empty] | 81.5 | [15 empty] | 2119 | [11 empty] | 2119
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 26.00 MH | [5 empty] | 77.06 | [8 empty] | 2617 | [18 empty] | 2617
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 52.00 MH | [5 empty] | 53.88 | [8 empty] | 3692 | [18 empty] | 3692
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 26.00 MH | [5 empty] | 74.56 | [8 empty] | 2534 | [18 empty] | 2534
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 26.00 MH | [5 empty] | 74.56 | [8 empty] | 2534 | [18 empty] | 2534
$144,795.68 5.0000 MH/EA 130.00 MH | [28 empty] | [ 367.335 ] | [8 empty] | 11376 | [6 empty] | 127498 | [7 empty] | 5922 |  |  |  | 144796
=====> Item Totals: $144,795.68 | [9 empty] | 572 5.0000 MH/EA | [6 empty] | - VALVE, GATE, 12 IN 130.00 MH | [11 empty] | [ 367.335 ] | [8 empty] | 11376 | [6 empty] | 127498 | [7 empty] | 5922 |  |  |  | 144796
5,569.065 26 EA | [37 empty] | 437.55 | [6 empty] | 4903.76 | [7 empty] | 227.75 |  |  |  | 5569.06
BID ITEM = 573 CLIENT# = 573 Land Item SCHEDULE: 1 100 Description = VALVE, BUTTERFLY, 16 IN Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
UNM Unerground Utilities 6 Man 6.00 CH Prod: 6.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI573PIPE BID ITEM 573 PIPE 1.00 3.00 EA 16,257.300 48,772 | [56 empty] | 48772
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 68.251 | [17 empty] | 409 | [5 empty] | 409
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 78 | [17 empty] | 468 | [5 empty] | 468
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 81.5 | [17 empty] | 489 | [5 empty] | 489
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 77.06 | [8 empty] | 604 | [14 empty] | 604
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 12.00 MH | [7 empty] | 53.88 | [8 empty] | 852 | [14 empty] | 852
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 74.56 | [8 empty] | 585 | [14 empty] | 585
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 74.56 | [8 empty] | 585 | [14 empty] | 585
$52,763.69 10.0000 MH/EA 30.00 MH | [30 empty] | [ 734.673 ] | [8 empty] | 2625 |  |  |  |  | 48772 |  |  |  | 1366 | [5 empty] | 52764
=====> Item Totals: 573 - VALVE, BUTTERFLY, 16 IN
52763.69 | [5 empty] | 10.0000 MH/EA | [13 empty] | 30.00 MH | [10 empty] | [ 734.673 ] | [8 empty] | 2625 |  |  |  |  | 48772 |  |  |  | 1366 | [5 empty] | 52764
17587.897 | [5 empty] | 3 EA | [33 empty] | 875.1 |  |  |  |  | 16257.3 |  |  |  | 455.5 | [5 empty] | 17587.9
BID ITEM = 574 CLIENT# = 574 Land Item SCHEDULE: 1 100 Description = VALVE, BUTTERFLY, 20 IN Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI574PIPE BID ITEM 574 PIPE 1.00 1.00 LS 17,642.840 17,643 | [56 empty] | 17643
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [6 empty] | 403 | [16 empty] | 403
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 53.88 | [6 empty] | 568 | [16 empty] | 568
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
$20,304.03 10.0000 MH/EA 20.00 MH [ 734.66 ] | [37 empty] | 1750 | [6 empty] | 17643 |  |  |  | 911 | [5 empty] | 20304
=====> Item Totals: 574 - VALVE, BUTTERFLY, 20 IN $20,304.03 10.0000 MH/EA 20.00 MH [ 734.66 ] | [37 empty] | 1750 | [6 empty] | 17643 |  |  |  | 911 | [5 empty] | 20304
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 574 CLIENT# = 574 Land Item SCHEDULE: 1 100 Description = VALVE, BUTTERFLY, 20 IN Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000 10,152.015 2 EA 875.10 8,821.42 455.50 10,152.02
BID ITEM = 575 CLIENT# = 575 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | VALVE BOX, CAST IRON | [24 empty] | Unit = EA Takeoff Quan: 70.000 Engr Quan: 70.000
| 575.01 |  |  |  |  | VALVE BOX, CAST IRON | [24 empty] | Quan: 70.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| 2BI575PIPE BID ITEM 575 PIPE 1.00 1.00 LS 20,813.000 | [36 empty] | 20813 | [14 empty] | 20813
| =====> Item Totals: 575 - VALVE BOX, CAST IRON $20,813.00 [ ] | [36 empty] | 20813 | [14 empty] | 20813
| 297.329 70 EA | [36 empty] | 297.33 | [14 empty] | 297.33
BID ITEM = 576 CLIENT# = 576 Land Item SCHEDULE: 1 100
Description = | [5 empty] | VALVE CHAMBER, PRECAST, 8'X10' | [22 empty] | Unit = |  |  |  |  | EA Takeoff Quan: 5.000 Engr Quan: 5.000
576.01 | [5 empty] | VALVE CHAMBER, PRECAST, 8'X10' | [22 empty] | Quan: |  |  |  |  | 5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | (Mod) Unerground Utilities 6 Man 100.00 | [24 empty] | CH |  |  | Prod: | [5 empty] | 100.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 4
2BI576PIPE | [5 empty] | BID ITEM 576 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 193007 | [15 empty] | 212790 | [9 empty] | 212790
2VCHAMBER | [5 empty] | VALVE CHAMBER | [13 empty] | 1 |  |  | 5.00 EA | [5 empty] | 15908 | [15 empty] | 79540 | [9 empty] | 79540
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 100.00 HR | [5 empty] | 68.251 | [19 empty] | 6825 | [5 empty] | 6825
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 100.00 HR | [5 empty] | 78 | [19 empty] | 7800 | [5 empty] | 7800
8EX400 | [5 empty] | 400 Excavator | [13 empty] | 1 |  |  | 100.00 HR | [5 empty] | 175.7 | [19 empty] | 17570 | [5 empty] | 17570
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 100.00 HR | [5 empty] | 81.5 | [19 empty] | 8150 | [5 empty] | 8150
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 100.00 MH | [5 empty] | 77.06 | [10 empty] | 10065 | [14 empty] | 10065
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 200.00 MH | [5 empty] | 53.88 | [10 empty] | 14200 | [14 empty] | 14200
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 200.00 MH | [5 empty] | 74.56 | [10 empty] | 19490 | [14 empty] | 19490
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 100.00 MH | [5 empty] | 74.56 | [10 empty] | 9745 | [14 empty] | 9745
$386,175.24 120.0000 MH/EA 600.00 MH | [28 empty] | [ 8987 ] | [10 empty] | 53500 |  |  |  |  | 292330 |  |  |  | 40345 | [5 empty] | 386175
=====> Item Totals: 576 - VALVE CHAMBER, PRECAST, 8'X10'
386175.24 | [5 empty] | 120.0000 MH/EA | [13 empty] | 600.00 MH | [8 empty] | [ 8987 ] | [8 empty] | 53500 | [6 empty] | 292330 |  |  |  | 40345 | [5 empty] | 386175
77235.048 | [5 empty] | 5 EA | [31 empty] | 10699.98 | [6 empty] | 58466.04 |  |  |  | 8069.02 | [5 empty] | 77235.05
BID ITEM = 577 CLIENT# = 577 Land Item SCHEDULE: 1 100
Description = | [5 empty] | HYDRANT, 6 IN CONN, TYPE 310 | [18 empty] | Unit = EA Takeoff Quan: 15.000 Engr Quan: 15.000
577.01 | [5 empty] | HYDRANT, 6 IN CONN, TYPE 310 | [18 empty] | Quan: 15.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 60 |  | CH Prod: 60.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI577PIPE | [5 empty] | BID ITEM 577 PIPE | [13 empty] | 1 |  |  |  |  | 1.00 LS | [5 empty] | 55,896.600 55,897 55,897
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 60.00 HR |  |  |  | 68.251 | [15 empty] | 4095 | [11 empty] | 4095
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 60.00 HR |  |  |  | 78 | [15 empty] | 4680 | [11 empty] | 4680
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 60.00 HR |  |  |  | 81.5 | [15 empty] | 4890 | [11 empty] | 4890
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 60.00 MH |  |  |  | 77.06 | [10 empty] | 6039 | [16 empty] | 6039
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 120.00 MH |  |  |  | 53.88 | [10 empty] | 8520 | [16 empty] | 8520
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 60.00 MH |  |  |  | 74.56 | [10 empty] | 5847 | [16 empty] | 5847
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 60.00 MH |  |  |  | 74.56 | [10 empty] | 5847 | [16 empty] | 5847
$95,814.62 20.0000 MH/EA 300.00 MH | [28 empty] | [ 1469.336 ] | [10 empty] | 26253 |  |  |  |  | 55897 | [7 empty] | 13665 |  |  |  | 95815
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 577 CLIENT# = 577 Land Item SCHEDULE: 1 100 Description = HYDRANT, 6 IN CONN, TYPE 310 Unit = EA Takeoff Quan: 15.000 Engr Quan: 15.000 =====> Item Totals: 577 - HYDRANT, 6 IN CONN, TYPE 310 $95,814.62 20.0000 MH/EA 6,387.641 15 EA
300.00 MH | [30 empty] | [ 1469.336 ] | [7 empty] | 26,253 55,897 | [13 empty] | 13665 |  |  |  | 95815
[39 empty] | 1,750.20 3,726.44 | [13 empty] | 911 |  |  |  | 6387.64
BID ITEM = 578 CLIENT# = 578 Land Item SCHEDULE: 1 100 Description = HYDRANT, 6 IN CONN, TYPE 311 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI578PIPE BID ITEM 578 PIPE 1.00 1.00 LS 3,999.300 3,999 | [56 empty] | 3999
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [8 empty] | 403 | [14 empty] | 403
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 53.88 | [8 empty] | 568 | [14 empty] | 568
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
$6,660.49 20.0000 MH/EA 20.00 MH | [30 empty] | [ 1469.32 ] | [8 empty] | 1750 |  |  |  |  | 3999 |  |  |  | 911 | [5 empty] | 6660
=====> Item Totals: 578 - HYDRANT, 6 IN CONN, TYPE 311 $6,660.49 20.0000 MH/EA 20.00 MH [ 1469.32 ] 1,750 3,999 911 6,660 6,660.490 1 EA 1,750.19 3,999.30 911.00 6,660.49
BID ITEM = 579 CLIENT# = 579 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SUPPORT SPU WITH SERVICE TRANSFER OR REN | [24 empty] | Unit = EA Takeoff Quan: 43.000 Engr Quan: 43.000
579..02 | [5 empty] | BACKFILL 3/4 TO 2 INCH SERVICE | [24 empty] | Quan: 43.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 57 | [10 empty] | CH | Prod: | [8 empty] | 57.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 57.00 HR | [5 empty] | 51.051 | [19 empty] | 2910 | [5 empty] | 2910
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 57.00 HR | [5 empty] | 52.3 | [19 empty] | 2981 | [5 empty] | 2981
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 57.00 MH | [5 empty] | 77.06 | [11 empty] | 5737 | [13 empty] | 5737
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 57.00 MH | [5 empty] | 53.88 | [11 empty] | 4047 | [13 empty] | 4047
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 57.00 MH | [5 empty] | 74.56 | [11 empty] | 5555 | [13 empty] | 5555
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 57.00 MH | [5 empty] | 74.56 | [11 empty] | 5555 | [13 empty] | 5555
$26,784.25 5.3023 MH/EA 228.00 MH | [28 empty] | [ 408.367 ] | [11 empty] | 20893 | [7 empty] | 5891 | [5 empty] | 26784
579.01 | [5 empty] | TRENCH 3/4 TO 2 INCH SERVICE | [18 empty] | Quan: 43.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [18 empty] | 57.00 CH Prod: 57.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 57.00 HR |  |  |  | 51.051 | [23 empty] | 2910 |  |  |  | 2910
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 57.00 HR |  |  |  | 52.3 | [23 empty] | 2981 |  |  |  | 2981
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 57.00 MH |  |  |  | 77.06 | [8 empty] | 5737 | [18 empty] | 5737
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  |  |  | 57.00 MH |  |  |  | 53.88 | [8 empty] | 4047 | [18 empty] | 4047
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  |  |  | 57.00 MH |  |  |  | 74.56 | [8 empty] | 5555 | [18 empty] | 5555
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 57.00 MH |  |  |  | 74.56 | [8 empty] | 5555 | [18 empty] | 5555
$26,784.25 5.3023 MH/EA 228.00 MH | [28 empty] | [ 408.367 ] | [8 empty] | 20893 | [14 empty] | 5891 |  |  |  | 26784
=====> Item Totals: 579 - SUPPORT SPU WITH SERVICE TRANSFE $53,568.50 10.6046 MH/EA 456.00 MH [ 816.733 ] | [37 empty] | R OR REN 41,787 | [14 empty] | 11782 |  |  |  | 53569
1,245.779 43 EA | [37 empty] | 971.78 | [14 empty] | 274 |  |  |  | 1245.78
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 580 CLIENT# = 580 Lan SUPPORT SPU WITH SERVICE TRANSFER OR REN | [24 empty] | d Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 18.000 Engr Quan: 18.000
580.01 | [5 empty] | TRENCH SERVICE 4 TO 8 INCH | [24 empty] | Quan: 18.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [22 empty] | 40 |  | CH Prod: 40.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
2BI580PIPE | [5 empty] | BID ITEM 580 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 20,548.940 22,655 22,655
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 51.051 | [23 empty] | 2042 |  |  |  | 2042
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 40.00 HR | [5 empty] | 52.3 | [23 empty] | 2092 |  |  |  | 2092
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 77.06 | [10 empty] | 4026 | [16 empty] | 4026
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 53.88 | [10 empty] | 2840 | [16 empty] | 2840
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [10 empty] | 3898 | [16 empty] | 3898
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 74.56 | [10 empty] | 3898 | [16 empty] | 3898
$41,451.19 8.8888 MH/EA 160.00 MH | [28 empty] | [ 684.591 ] | [10 empty] | 14662 |  |  |  |  | 22655 | [7 empty] | 4134 |  |  |  | 41451
580.02 | [5 empty] | BACKFILL SERVICE 4 TO 8 IN | [16 empty] | Quan: 18.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [16 empty] | 30.00 CH Prod: 30.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 30.00 HR | [5 empty] | 51.051 | [15 empty] | 1532 | [11 empty] | 1532
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 30.00 HR | [5 empty] | 52.3 | [15 empty] | 1569 | [11 empty] | 1569
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 30.00 MH | [5 empty] | 77.06 | [10 empty] | 3019 | [16 empty] | 3019
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 30.00 MH | [5 empty] | 53.88 | [10 empty] | 2130 | [16 empty] | 2130
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 30.00 MH | [5 empty] | 74.56 | [10 empty] | 2924 | [16 empty] | 2924
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 30.00 MH | [5 empty] | 74.56 | [10 empty] | 2924 | [16 empty] | 2924
$14,096.98 6.6666 MH/EA 120.00 MH | [28 empty] | [ 513.443 ] | [10 empty] | 10996 |  |  |  |  | 3101 | [11 empty] | 14097
=====> Item Totals: 580 - SUPPORT SPU WITH SERVICE TRANSFER OR REN $55,548.17 15.5555 MH/EA 280.00 MH [ 1198.034 ] 25,658 22,655 7,235 55,548 3,086.009 18 EA 1,425.47 1,258.62 401.92 3,086.01
BID ITEM = 581 CLIENT# = 581 Land Item SCHEDULE: 1 100 Description = SUPPORT SPU WITH NEW WATER SERVICE, 4 IN Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
581.01 SUPPORT SPU WITH NEW WATER SERVICE, 4 I Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS Underground Utilities 4 Man 2.00 CH Prod: 2.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2BI581PIPE BID ITEM 581 P@110.25 1.00 1.00 EA 5,487.800 6,050 | [56 empty] | 6050
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 51.051 | [17 empty] | 102 | [5 empty] | 102
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 52.3 | [17 empty] | 105 | [5 empty] | 105
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 77.06 | [8 empty] | 201 | [14 empty] | 201
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 53.88 | [8 empty] | 142 | [14 empty] | 142
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [8 empty] | 195 | [14 empty] | 195
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [8 empty] | 195 | [14 empty] | 195
$6,990.09 8.0000 MH/EA 8.00 MH | [30 empty] | [ 616.13 ] | [8 empty] | 733 |  |  |  |  | 6050 |  |  |  | 207 | [5 empty] | 6990
=====> Item Totals: 581 - SUPPORT SPU WITH NEW WATER SERVICE, 4 IN $6,990.09 8.0000 MH/EA 8.00 MH [ 616.13 ] 733 6,050 207 6,990 6,990.090 1 EA 733.10 6,050.30 206.69 6,990.09
BID ITEM = 582 CLIENT# = 582 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | SUPPORT SPU WITH WATER SERVICE RETIREMEN | [24 empty] | Unit = |  |  | EA Takeoff Quan: 2.000 Engr Quan: 2.000
| 582.01 |  |  |  |  | SUPPORT SPU WITH WATER SERVICE RETIRE | [24 empty] | Quan: |  |  | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS Underground Utilities 4 Man 4.00 CH Prod: 4.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [5 empty] | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 582 CLIENT# = 582 Land Item SCHEDULE: 1 SUPPORT SPU WITH WATER SERVICE RETIREMEN Unit = EA Takeoff Quan: | [39 empty] | 100 |  |  | 2 |  | Engr Quan: |  |  |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1 |  |  |  | 4.00 HR | [9 empty] | 51.051 | [14 empty] | 204 | [8 empty] | 204
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1 |  |  |  | 4.00 HR | [9 empty] | 52.3 | [14 empty] | 209 | [8 empty] | 209
FOCI | [5 empty] | Civil Forman | [12 empty] | 1 |  |  |  | 4.00 MH | [9 empty] | 77.06 | [6 empty] | 403 | [16 empty] | 403
LAP | [5 empty] | Labor Underground Water | [12 empty] | 1 |  |  |  | 4.00 MH | [9 empty] | 53.88 | [6 empty] | 284 | [16 empty] | 284
OPB | [5 empty] | Operator - Backhoe | [12 empty] | 1 |  |  |  | 4.00 MH | [9 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1 |  |  |  | 4.00 MH | [9 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
$1,879.59 8.0000 MH/EA 16.00 MH | [32 empty] | [ 616.125 ] | [6 empty] | 1466 | [7 empty] | 413 | [8 empty] | 1880
=====> Item Totals: 582 - SUPPORT SPU WITH WATER SERVICE RETIREMEN
1879.59 | [5 empty] | 8.0000 MH/EA | [12 empty] | 16.00 MH | [13 empty] | [ 616.125 ] | [6 empty] | 1466 | [7 empty] | 413 | [8 empty] | 1880
939.795 | [5 empty] | 2 EA | [33 empty] | 733.1 | [7 empty] | 206.7 | [8 empty] | 939.8
BID ITEM = 583 CLIENT# = 583 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 4 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 26.000 Engr Quan: 26.000
583.01 | [5 empty] | BEDDING, CL B, 4 IN PIPE | [16 empty] | Quan: 26.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [10 empty] | 1 | [5 empty] | 13.00 TON | [7 empty] | 29.75 | [6 empty] | 387 | [14 empty] | 387
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [10 empty] | 1 | [5 empty] | 10.00 TCY | [7 empty] | 24.5 | [17 empty] | 245 |  |  |  | 245
631.75 | [30 empty] | [ ] | [6 empty] | 387 | [10 empty] | 245 |  |  |  | 632
=====> $631.75 |  |  |  | Item Totals: | [6 empty] | 583 | [5 empty] | - |  | BEDDING, CL B, 4 IN PIPE | [11 empty] | [ ] | [6 empty] | 387 | [10 empty] | 245 |  |  |  | 632
24.298 | [13 empty] | 26 LF | [23 empty] | 14.88 | [10 empty] | 9.42 |  |  |  | 24.3
BID ITEM = 584 CLIENT# = 584 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 6 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 55.000 Engr Quan: 55.000
584.01 | [5 empty] | BEDDING, CL B, 6 IN PIPE | [16 empty] | Quan: 55.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [10 empty] | 1 | [5 empty] | 27.00 TON | [7 empty] | 29.75 | [6 empty] | 803 | [14 empty] | 803
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [10 empty] | 1 | [5 empty] | 19.00 TCY | [7 empty] | 24.5 | [17 empty] | 466 |  |  |  | 466
1268.75 | [30 empty] | [ ] | [6 empty] | 803 | [10 empty] | 466 |  |  |  | 1269
=====> Item Totals: $1,268.75 | [10 empty] | 584 | [5 empty] | - |  | BEDDING, CL B, 6 IN PIPE | [11 empty] | [ ] | [6 empty] | 803 | [10 empty] | 466 |  |  |  | 1269
23.068 | [13 empty] | 55 LF | [23 empty] | 14.6 | [10 empty] | 8.46 |  |  |  | 23.07
BID ITEM = 585 CLIENT# = 585 Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, CL B, 8 IN PIPE | [16 empty] | Unit = LF Takeoff Quan: 12.000 Engr Quan: 12.000
585.01 | [5 empty] | BEDDING, CL B, 8 IN PIPE | [16 empty] | Quan: 12.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [10 empty] | 1 | [5 empty] | 9.00 TON | [7 empty] | 29.75 | [6 empty] | 268 | [14 empty] | 268
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [10 empty] | 1 | [5 empty] | 6.00 TCY | [7 empty] | 24.5 | [17 empty] | 147 |  |  |  | 147
414.75 | [30 empty] | [ ] | [6 empty] | 268 | [10 empty] | 147 |  |  |  | 415
=====> $414.75 |  |  |  | Item Totals: | [6 empty] | 585 | [5 empty] | - |  | BEDDING, CL B, 8 IN PIPE | [11 empty] | [ ] | [6 empty] | 268 | [10 empty] | 147 |  |  |  | 415
34.563 | [13 empty] | 12 LF | [23 empty] | 22.31 | [10 empty] | 12.25 |  |  |  | 34.56
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 586 CLIENT# = 586 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, SS or SSS, PVC D3034 SDR 35, 4 IN | [24 empty] | Unit = LF Takeoff Quan: 26.000 Engr Quan: 26.000
586.01 UNM | [5 empty] | PIPE, SS or SSS, PVC D3034 SDR 35, 4 IN Unerground Utilities 6 Man | [22 empty] | 16 |  | Quan: 26.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG CH Prod: 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI586PIPE | [5 empty] | BID ITEM 586 PIPE 1.00 1.00 LS | [24 empty] | 122.000 122 122
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 68.251 | [15 empty] | 1092 | [11 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 78 | [15 empty] | 1248 | [11 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 81.5 | [15 empty] | 1304 | [11 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 77.06 | [10 empty] | 1610 | [16 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [5 empty] | 53.88 | [10 empty] | 2272 | [16 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [10 empty] | 1559 | [16 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [10 empty] | 1559 | [16 empty] | 1559
$10,766.79 3.0769 MH/LF 80.00 MH [ 226.052 ] 7,001 | [44 empty] | 122 | [7 empty] | 3644 |  |  |  | 10767
=====> Item Totals: 586 - PIPE, SS or SSS, PVC D3034 SDR 35, 4 IN
$10,766.79 3.0769 MH/LF 80.00 MH | [28 empty] | [ 226.052 ] | [10 empty] | 7001 |  |  |  |  | 122 | [7 empty] | 3644 |  |  |  | 10767
414.107 26 LF | [39 empty] | 269.26 |  |  |  |  | 4.69 | [7 empty] | 140.15 |  |  |  | 414.11
BID ITEM = 587 CLIENT# = 587 Land Item SCHEDULE: 1 100
Description = | [5 empty] | PIPE, SS or SSS, PVC D3034 SDR 35, 6 IN | [24 empty] | Unit = LF Takeoff Quan: 55.000 Engr Quan: 55.000
587.01 UNM | [5 empty] | PIPE, SS or SSS, PVC D3034 SDR 35, 6 IN Unerground Utilities 6 Man | [22 empty] | 16 |  | Quan: 55.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG CH Prod: 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI587PIPE | [5 empty] | BID ITEM 587 PIPE 1.00 1.00 LS | [24 empty] | 362.000 362 362
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 68.251 | [15 empty] | 1092 | [11 empty] | 1092
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 78 | [15 empty] | 1248 | [11 empty] | 1248
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 81.5 | [15 empty] | 1304 | [11 empty] | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 77.06 | [8 empty] | 1610 | [18 empty] | 1610
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 32.00 MH | [5 empty] | 53.88 | [8 empty] | 2272 | [18 empty] | 2272
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [8 empty] | 1559 | [18 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [8 empty] | 1559 | [18 empty] | 1559
$11,006.79 1.4545 MH/LF 80.00 MH [ 106.861 ] 7,001 | [44 empty] | 362 | [7 empty] | 3644 |  |  |  | 11007
=====> Item Totals: 587 - PIPE, SS or SSS, PVC D3034 SDR 35, 6 IN $11,006.79 1.4545 MH/LF 80.00 MH [ 106.861 ] | [37 empty] | 7001 | [6 empty] | 362 | [7 empty] | 3644 |  |  |  | 11007
200.123 55 LF | [37 empty] | 127.29 | [6 empty] | 6.58 | [7 empty] | 66.25 |  |  |  | 200.12
BID ITEM = 588 CLIENT# = 588 Land Item SCHEDULE: 1 100 Description = PIPE, SD, D.I., CL 50, 8 IN Unit = LF Takeoff Quan: 12.000 Engr Quan: 12.000
UNM Unerground Utilities 6 Man 6.00 CH Prod: 6.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI588PIPE BID ITEM 588 PIPE 1.00 1.00 LS 285.480 285 | [56 empty] | 285
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 68.251 | [17 empty] | 409 | [5 empty] | 409
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 78 | [17 empty] | 468 | [5 empty] | 468
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 6.00 HR | [7 empty] | 81.5 | [17 empty] | 489 | [5 empty] | 489
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 77.06 | [8 empty] | 604 | [14 empty] | 604
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 12.00 MH | [7 empty] | 53.88 | [8 empty] | 852 | [14 empty] | 852
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 74.56 | [8 empty] | 585 | [14 empty] | 585
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 6.00 MH | [7 empty] | 74.56 | [8 empty] | 585 | [14 empty] | 585
$4,277.27 2.5000 MH/LF | [22 empty] | 30.00 MH | [7 empty] | [ 183.668 ] | [8 empty] | 2625 |  |  |  |  | 285 |  |  |  | 1366 | [5 empty] | 4277
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 588 CLIENT# = 588 Land Item SCHEDULE: 1 100 Description = PIPE, SD, D.I., CL 50, 8 IN Unit = LF Takeoff Quan: 12.000 Engr Quan: 12.000 =====> Item Totals: 588 - PIPE, SD, D.I., CL 50, 8 IN $4,277.27 2.5000 MH/LF 356.439 12 LF
30.00 MH | [30 empty] | [ 183.668 ] | [8 empty] | 2625 |  |  |  |  | 285 | [7 empty] | 1366 |  |  |  | 4277
[40 empty] | 218.78 |  |  |  |  | 23.79 | [7 empty] | 113.87 |  |  |  | 356.44
BID ITEM = 589 CLIENT# = 589 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SEWER CLEANOUT, 4 IN | [13 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
589.01 | [5 empty] | SEWER CLEANOUT, 4 IN | [24 empty] | Quan: |  |  | 2.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 2 | [10 empty] | CH |  |  | Prod: | [7 empty] | 2.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI589PIPE | [5 empty] | BID ITEM 589 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 136.340 136 136
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 2.00 HR | [5 empty] | 68.251 | [15 empty] | 136 | [11 empty] | 136
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 2.00 HR | [5 empty] | 78 | [15 empty] | 156 | [11 empty] | 156
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 2.00 HR | [5 empty] | 81.5 | [15 empty] | 163 | [11 empty] | 163
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 2.00 MH | [5 empty] | 77.06 | [12 empty] | 201 | [14 empty] | 201
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 4.00 MH | [5 empty] | 53.88 | [12 empty] | 284 | [14 empty] | 284
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 2.00 MH | [5 empty] | 74.56 | [12 empty] | 195 | [14 empty] | 195
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 2.00 MH | [5 empty] | 74.56 | [12 empty] | 195 | [14 empty] | 195
$1,466.92 5.0000 MH/EA 10.00 MH | [28 empty] | [ 367.33 ] | [12 empty] | 875 |  |  | 136 | [7 empty] | 455 |  |  |  | 1467
=====> Item Totals: 589 - SEWER CLEANOUT, 4 IN
1466.92 | [5 empty] | 5.0000 MH/EA | [13 empty] | 10.00 MH | [8 empty] | [ 367.33 ] | [10 empty] | 875 |  |  |  |  | 136 | [7 empty] | 455 |  |  |  | 1467
733.46 | [5 empty] | 2 EA | [33 empty] | 437.55 |  |  |  |  | 68.17 | [7 empty] | 227.75 |  |  |  | 733.46
BID ITEM = 590 CLIENT# = 590 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SEWER CLEANOUT, 8 IN | [13 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
590.01 | [5 empty] | SEWER CLEANOUT, 8 IN | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 1 | [10 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI590PIPE | [5 empty] | BID ITEM 590 PIPE | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 686.450 686 686
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 1.00 HR | [5 empty] | 68.251 | [15 empty] | 68 | [11 empty] | 68
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 1.00 HR | [5 empty] | 78 | [15 empty] | 78 | [11 empty] | 78
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 1.00 HR | [5 empty] | 81.5 | [15 empty] | 81 | [11 empty] | 81
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 1.00 MH | [5 empty] | 77.06 | [12 empty] | 101 | [14 empty] | 101
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 2.00 MH | [5 empty] | 53.88 | [12 empty] | 142 | [14 empty] | 142
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 1.00 MH | [5 empty] | 74.56 | [12 empty] | 97 | [14 empty] | 97
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 1.00 MH | [5 empty] | 74.56 | [12 empty] | 97 | [14 empty] | 97
$1,351.74 5.0000 MH/EA 5.00 MH | [28 empty] | [ 367.35 ] | [12 empty] | 438 |  |  | 686 | [7 empty] | 228 |  |  |  | 1352
=====> Item Totals: 590 - SEWER CLEANOUT, 8 IN
1351.74 | [5 empty] | 5.0000 MH/EA | [13 empty] | 5.00 MH | [8 empty] | [ 367.35 ] | [10 empty] | 438 |  |  |  |  | 686 | [7 empty] | 228 |  |  |  | 1352
1351.74 | [5 empty] | 1 EA | [33 empty] | 437.56 |  |  |  |  | 686.45 | [7 empty] | 227.73 |  |  |  | 1351.74
BID ITEM = 591 CLIENT# = 591 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CONDUIT RISER, 4 IN | [13 empty] | Unit = | [13 empty] | EA Takeoff Quan: 2.000 Engr Quan: 2.000
591.01 | [5 empty] | CONDUIT RISER, 4 IN | [13 empty] | Quan: | [13 empty] | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 2.00 EA | [7 empty] | 2,800.000 5,600 5,600
Activity Desc Resource | [17 empty] | Pcs |  |  |  |  | Quantity |  |  |  | Unit |  |  | Unit Cost | [9 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 592 CLIE HANDHOLE, TYPE 5 | [11 empty] | NT# = 5 |  |  |  |  | 92 L | [6 empty] | and Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
592.01 | [5 empty] | HANDHOLE, TYPE 5 | [23 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [11 empty] | 1 |  |  |  |  | 1.00 EA | [6 empty] | 3,200.000 3,200 3,200
BID ITEM = 593 CLIENT# = 593 Land Item SCHEDULE: 1 100
Description = | [5 empty] | METRO COMFORT STATION-BREAK ROOM | [24 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
593.01 | [5 empty] | METRO COMFORT STATION-BREAK ROOM | [24 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4COMSUB | [5 empty] | COMFORT STATION SU | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 200000 | [8 empty] | 200000 | [16 empty] | 200000
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 69700 | [8 empty] | 69700 | [16 empty] | 69700
4GLAS | [5 empty] | GLASS INSTALLER | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 19500 | [8 empty] | 19500 | [16 empty] | 19500
4HVAC | [5 empty] | HAVAC SUB | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 10000 | [8 empty] | 10000 | [16 empty] | 10000
4PLUM | [5 empty] | PLUMING SUB | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 10000 | [8 empty] | 10000 | [16 empty] | 10000
309200 | [30 empty] | [ ] | [8 empty] | 309200 | [16 empty] | 309200
593.02 | [5 empty] | EXCAVATATE FOUNDATION | [16 empty] | Quan: 20.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [16 empty] | 16.00 CH Prod: 16.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 51.051 | [21 empty] | 817 |  | 817
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 52.3 | [21 empty] | 837 |  | 837
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 77.06 | [8 empty] | 1610 | [14 empty] | 1610
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 32.00 MH | [7 empty] | 52.91 | [8 empty] | 2232 | [14 empty] | 2232
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [14 empty] | 1559
$7,055.49 3.2000 MH/CY 64.00 MH | [30 empty] | [ 226.548 ] | [8 empty] | 5402 | [12 empty] | 1654 |  | 7055
593.03 FOUNDATION Quan: 15.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COM | [5 empty] | Concrete 6 Man Crew | [13 empty] | 40 | [10 empty] | CH |  |  | Prod: | [6 empty] | 40.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
2CR040 | [5 empty] | 4000LB READY M@110.2 | [13 empty] | 1 |  |  | 15.00 CY | [5 empty] | 121.5 | [15 empty] | 2009 |  |  |  | 2009
2RBCOM | [5 empty] | REBAR COMFOR S@110. | [13 empty] | 1 |  |  | 1.00 LS | [5 empty] | 2500 | [15 empty] | 2756 |  |  |  | 2756
2SLABIN | [5 empty] | SLAB INSALATIO@110.2 | [13 empty] | 1 |  |  | 200.00 SF | [5 empty] | 10 | [15 empty] | 2205 |  |  |  | 2205
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 200.00 MH | [5 empty] | 64.98 | [11 empty] | 17039 | [7 empty] | 17039
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 40.00 MH | [5 empty] | 68.98 | [11 empty] | 3613 | [7 empty] | 3613
$27,622.58 16.0000 MH/CY 240.00 MH [ 1155.381 ]
20,652 6,971 | [17 empty] | 27623
OM 26,054 6,971 | [8 empty] | 1654 |  |  | 309200 | [5 empty] | 343878
=====> Item T $343,878.07 | [7 empty] | otals: 593 - M 304.0000 MH/LS | [12 empty] | ETRO COMFORT STAT 304.00 MH | [9 empty] | ION-BREAK RO [ 21861.67 ]
343878.07 | [7 empty] | 1 LS
26,053.91 6,970.56 1,653.60 309,200.00 343,878.07
BID ITEM = 594 CLIENT# = 594 Land Item SCHEDULE: 1 100 Description = CONCRETE ENCASED DUCT BANK (9-5" RGS) Unit = LF Takeoff Quan: 46.000 Engr Quan: 46.000
594.01 | [5 empty] | EXCAVATE CONRETE ENCED DUCT BANK | [24 empty] | Quan: |  |  | 46.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [17 empty] | 16 | [6 empty] | CH |  |  | Prod: | [7 empty] | 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02V | [5 empty] | VACTOR TRUCK DISPO | [13 empty] | 1 |  |  |  | 3.00 EA 500.000 | [24 empty] | 1500 | [7 empty] | 1500
3VAC | [5 empty] | VACTOR TRUCKS | [13 empty] | 1 |  |  |  | 16.00 HR 275.000 | [24 empty] | 4400 | [7 empty] | 4400
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  | 16.00 HR 52.300 | [28 empty] | 837 |  |  |  | 837
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 16.00 HR 68.251 | [28 empty] | 1092 |  |  |  | 1092
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  | 16.00 HR 81.500 | [28 empty] | 1304 |  |  |  | 1304
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 16.00 MH 77.060 | [17 empty] | 1610 | [14 empty] | 1610
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 594 CLIENT# = 594 Land Item SCHEDULE: 1 100 Description = CONCRETE ENCASED DUCT BANK (9-5" RGS) Unit = LF Takeoff Quan: 46.000 Engr Quan: 46.000
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 32.00 MH | [7 empty] | 52.91 | [8 empty] | 2232 | [8 empty] | 2232
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [8 empty] | 1559
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 1559 | [8 empty] | 1559
$16,093.89 1.7391 MH/LF | [22 empty] | 80.00 MH | [7 empty] | [ 127.026 ] | [8 empty] | 6961 | [8 empty] | 5900 |  |  |  | 3233 |  |  |  | 16094
594.02 CONCRETE ENCASED DUCT BANK (9-5" RGS) Quan: | [33 empty] | 46.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC DUCTBANK CREW 8.00 CH | [33 empty] | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 46.00 LF | [10 empty] | 1770 | [20 empty] | 81420 |  | 81420
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [10 empty] | 52.3 | [10 empty] | 418 | [11 empty] | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [10 empty] | 68.251 | [10 empty] | 546 | [11 empty] | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [10 empty] | 81.5 | [10 empty] | 652 | [11 empty] | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 77.06 | [7 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [10 empty] | 52.91 | [7 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 74.56 | [7 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [10 empty] | 74.56 | [7 empty] | 780 | [14 empty] | 780
$86,516.95 0.8695 MH/LF | [22 empty] | 40.00 MH | [10 empty] | [ 63.513 ] | [7 empty] | 3481 |  |  | 1616 | [9 empty] | 81420 |  | 86517
594.03 | [5 empty] | BACFILL CON ENCASED DUCT BANK | [24 empty] | Quan: |  |  | 46.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [22 empty] | 8 |  | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CRLSFTB | [5 empty] | LOW STRENGHT FTB | [13 empty] | 1 |  |  | 28.00 CY | [5 empty] | 107.150 3,000 3,000
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 52.3 | [15 empty] | 418 | [9 empty] | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [15 empty] | 546 | [9 empty] | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [15 empty] | 652 | [9 empty] | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [12 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [12 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
$8,097.15 0.8695 MH/LF | [22 empty] | 40.00 MH | [5 empty] | [ 63.513 ] | [12 empty] | 3481 |  |  | 3000 |  |  |  | 1616 | [5 empty] | 8097
=====> Item Totals: 594 - CONCRETE ENCASED DUCT BANK (9-5" RGS)
$110,707.99 3.4782 MH/LF 160.00 MH | [28 empty] | [ 254.053 ] | [10 empty] | 13922 |  |  |  |  | 3000 |  |  |  | 5900 |  |  |  | 6466 |  | 81420 |  | 110708
2,406.695 46 LF | [39 empty] | 302.66 |  |  |  |  | 65.22 |  |  |  | 128.26 |  |  |  | 140.56 |  | 1770 |  | 2406.7
BID ITEM = 595 CLIENT# = 595 Land Item SCHEDULE: 1 100 Description = HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS Unit = LF Takeoff Quan: 48.000 Engr Quan: 48.000
595.01 | [5 empty] | EXCAVATE DUCT BANK | [24 empty] | Quan: |  |  | 48.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW 8.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02D | [5 empty] | Dirt Trucking and Dump 1.00 | [16 empty] | 133.00 TCY | [5 empty] | 24.5 | [19 empty] | 3259 | [5 empty] | 3259
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 8.00 HR | [5 empty] | 52.3 | [23 empty] | 418 |  | 418
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 8.00 HR | [5 empty] | 68.251 | [23 empty] | 546 |  | 546
8LO950 | [5 empty] | 950 Loader 1.00 | [16 empty] | 8.00 HR | [5 empty] | 81.5 | [23 empty] | 652 |  | 652
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [12 empty] | 805
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [12 empty] | 1116
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
OPL | [5 empty] | Operator - Loader 1.00 | [16 empty] | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
$8,355.45 0.8333 MH/LF | [22 empty] | 40.00 MH | [5 empty] | [ 60.867 ] | [12 empty] | 3481 | [6 empty] | 3259 |  |  |  | 1616 |  | 8355
595.02 HSFTB ENCASED DUCT BANK (4-5" FIBERGLAS Quan: | [33 empty] | 48.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC DUCTBANK CREW 8.00 CH | [33 empty] | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
4ELEC | [5 empty] | Electrical sub 1.00 | [16 empty] | 48.00 LF | [5 empty] | 610 | [25 empty] | 29280 |  | 29280
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 8.00 HR | [5 empty] | 52.3 | [12 empty] | 418 | [14 empty] | 418
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 595 CLIENT# = 595 Land Item SCHEDULE: 1 100 Description = HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS Unit = LF Takeoff Quan: 48.000 Engr Quan: 48.000
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [15 empty] | 546 | [9 empty] | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [15 empty] | 652 | [9 empty] | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [12 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [12 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
$34,376.95 0.8333 MH/LF | [22 empty] | 40.00 MH | [5 empty] | [ 60.867 ] | [12 empty] | 3481 |  |  | 1616 | [9 empty] | 29280 |  | 34377
595.03 | [5 empty] | BACFILL DUCT BANK | [24 empty] | Quan: |  |  | 48.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [13 empty] | 8 | [10 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CRLSFTB | [5 empty] | LOW STRENGHT FTB | [13 empty] | 1 |  |  | 88.00 CY | [5 empty] | 107.150 9,429 9,429
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 52.3 | [15 empty] | 418 | [9 empty] | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 68.251 | [15 empty] | 546 | [9 empty] | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 81.5 | [15 empty] | 652 | [9 empty] | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [12 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [12 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [12 empty] | 780
$14,526.15 0.8333 MH/LF | [22 empty] | 40.00 MH | [5 empty] | [ 60.867 ] | [12 empty] | 3481 |  |  | 9429 |  |  |  | 1616 | [5 empty] | 14526
=====> Item Totals: 595 - HSFTB ENCASED DUCT BANK (4-5" FIBE $57,258.55 2.5000 MH/LF 120.00 MH [ 182.601 ] | [37 empty] | RGLASS 10,442 | [6 empty] | 9429 |  |  |  | 3259 |  |  |  | 4849 |  | 29280 |  | 57259
1,192.886 48 LF | [37 empty] | 217.53 | [6 empty] | 196.44 |  |  |  | 67.89 |  |  |  | 101.03 |  | 610 |  | 1192.89
BID ITEM = 596 CLIENT# = 596 Land Item SCHEDULE: 1 100 Description = HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS Unit = LF Takeoff Quan: 74.000 Engr Quan: 74.000
596.01 | [5 empty] | EXCAVATE DUCT BANK | [24 empty] | Quan: |  |  | 74.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW 16.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 16.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02D | [5 empty] | Dirt Trucking and Dump 1.00 | [16 empty] | 189.00 TCY | [7 empty] | 24.5 | [17 empty] | 4631 | [5 empty] | 4631
3VAC | [5 empty] | VACTOR TRUCKS 1.00 | [16 empty] | 8.00 HR | [7 empty] | 275 | [17 empty] | 2200 | [5 empty] | 2200
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 16.00 HR | [7 empty] | 52.3 | [21 empty] | 837 |  | 837
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 16.00 HR | [7 empty] | 68.251 | [21 empty] | 1092 |  | 1092
8LO950 | [5 empty] | 950 Loader 1.00 | [16 empty] | 16.00 HR | [7 empty] | 81.5 | [21 empty] | 1304 |  | 1304
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 16.00 MH | [7 empty] | 77.06 | [10 empty] | 1610 | [12 empty] | 1610
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 32.00 MH | [7 empty] | 52.91 | [10 empty] | 2232 | [12 empty] | 2232
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 16.00 MH | [7 empty] | 74.56 | [10 empty] | 1559 | [12 empty] | 1559
OPL | [5 empty] | Operator - Loader 1.00 | [16 empty] | 16.00 MH | [7 empty] | 74.56 | [10 empty] | 1559 | [12 empty] | 1559
$17,024.39 1.0810 MH/LF | [22 empty] | 80.00 MH | [7 empty] | [ 78.962 ] | [10 empty] | 6961 | [6 empty] | 6831 |  |  |  | 3233 |  | 17024
596.02 HSFTB ENCASED DUCT BANK (4-5" FIBERGLAS Quan: | [33 empty] | 74.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 8.00 CH | [33 empty] | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
4ELEC | [5 empty] | Electrical sub 1.00 | [16 empty] | 74.00 LF | [7 empty] | 520 | [23 empty] | 38480 |  | 38480
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 8.00 HR | [7 empty] | 51.051 | [17 empty] | 408 | [7 empty] | 408
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 8.00 HR | [7 empty] | 52.3 | [17 empty] | 418 | [7 empty] | 418
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 8.00 MH | [7 empty] | 77.06 | [10 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 16.00 MH | [7 empty] | 52.91 | [10 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 8.00 MH | [7 empty] | 74.56 | [10 empty] | 780 | [14 empty] | 780
$42,007.75 0.4324 MH/LF | [22 empty] | 32.00 MH | [7 empty] | [ 30.615 ] | [10 empty] | 2701 | [6 empty] | 827 | [5 empty] | 38480 |  | 42008
596.03 | [5 empty] | BACKFILL DUCT BANK | [24 empty] | Quan: 74.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew 8.00 | [24 empty] | CH Prod: 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 596 CLIENT# = 596 Land Item SCHEDULE: 1 100
Description = HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS Unit = | [32 empty] | LF Takeoff Quan: 74.000 Engr Quan: 74.000
2CRLSFTB LOW STRENGHT FTB 1.00 138.00 CY 107.150 14,787 14,787
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 8.00 HR | [9 empty] | 51.051 | [11 empty] | 408 | [9 empty] | 408
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [9 empty] | 52.3 | [11 empty] | 418 | [9 empty] | 418
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [9 empty] | 77.06 | [6 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [9 empty] | 52.91 | [6 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [9 empty] | 74.56 | [6 empty] | 780 | [14 empty] | 780
$18,314.45 0.4324 MH/LF | [22 empty] | 32.00 MH | [9 empty] | [ 30.615 ] | [6 empty] | 2701 |  |  |  |  | 14787 |  |  |  | 827 | [5 empty] | 18314
=====> Item Totals: 596 - HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS
$77,346.59 1.9459 MH/LF 144.00 MH | [32 empty] | [ 140.191 ] | [6 empty] | 12363 |  |  |  |  | 14787 |  |  |  | 6831 |  |  |  | 4886 |  | 38480 |  | 77347
1,045.224 74 LF | [39 empty] | 167.07 |  |  |  |  | 199.82 |  |  |  | 92.3 |  |  |  | 66.03 |  | 520 |  | 1045.22
BID ITEM = 597 CLIENT# = 597 Land Item SCHEDULE: 1 100 Description = HSFTB ENCASED DUCT BANK (2-4" PVC) Unit = LF Takeoff Quan: 72.000 Engr Quan: 72.000
597.01 | [5 empty] | HSFTB ENCASED DUCT BANK (2-4" PVC) | [24 empty] | Quan: |  | 72.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [18 empty] | 8 | [5 empty] | CH |  | Prod: | [8 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 64.00 TCY 24.500 | [23 empty] | 1568 | [7 empty] | 1568
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 8.00 HR 52.300 | [27 empty] | 418 |  |  |  | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 8.00 HR 68.251 | [27 empty] | 546 |  |  |  | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 8.00 HR 81.500 | [27 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 8.00 MH 77.060 | [16 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 16.00 MH 52.910 | [16 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 8.00 MH 74.560 | [16 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 8.00 MH 74.560 | [16 empty] | 780 | [14 empty] | 780
$6,664.95 0.5555 MH/LF | [24 empty] | 40.00 MH [ 40.578 ] | [16 empty] | 3481 | [6 empty] | 1568 |  |  |  | 1616 |  |  |  | 6665
597.02 HSFTB ENCASED DUCT BANK (2-4" PVC) Quan: 72.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 72.00 LF | [7 empty] | 140.000 10,080 10,080
597.03 | [5 empty] | BACFILL DUCT BANK | [24 empty] | Quan: |  | 72.00 LF | [8 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DBC | [5 empty] | DUCTBANK CREW | [13 empty] | 4 | [10 empty] | CH |  | Prod: | [8 empty] | 4.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CRLSFTB | [5 empty] | LOW STRENGHT FTB | [13 empty] | 1 |  |  | 33.00 CY | [5 empty] | 107.150 3,536 3,536
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [5 empty] | 52.3 | [15 empty] | 209 | [9 empty] | 209
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [5 empty] | 68.251 | [15 empty] | 273 | [9 empty] | 273
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [5 empty] | 81.5 | [15 empty] | 326 | [9 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [5 empty] | 77.06 | [12 empty] | 403 | [12 empty] | 403
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 8.00 MH | [5 empty] | 52.91 | [12 empty] | 558 | [12 empty] | 558
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [5 empty] | 74.56 | [12 empty] | 390 | [12 empty] | 390
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [5 empty] | 74.56 | [12 empty] | 390 | [12 empty] | 390
$6,084.42 0.2777 MH/LF | [22 empty] | 20.00 MH | [5 empty] | [ 20.289 ] | [12 empty] | 1740 |  |  | 3536 |  |  |  | 808 | [5 empty] | 6084
=====> Item Totals: 597 - HSFTB ENCASED DUCT BANK (2-4" PVC)
$22,829.37 0.8333 MH/LF 60.00 MH | [28 empty] | [ 60.867 ] | [12 empty] | 5221 |  |  | 3536 |  |  |  | 1568 |  |  |  | 2425 |  | 10080 |  | 22829
317.075 72 LF | [41 empty] | 72.51 |  |  | 49.11 |  |  |  | 21.78 |  |  |  | 33.68 |  | 140 |  | 317.07
BID ITEM = 598 CLIENT# = 598 Land Item SCHEDULE: 1 100
| Description = |  |  |  |  | HSFTB ENCASED DUCT BANK (4-4" PVC) | [24 empty] | Unit = |  | LF Takeoff Quan: 10.000 Engr Quan: 10.000
| 598.01 |  |  |  |  | HSFTB ENCASED DUCT BANK (4-4" PVC) | [24 empty] | Quan: |  | 10.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 598 CLIENT# = 598 Land Item SCHEDULE: 1 100 Description = HSFTB ENCASED DUCT BANK (4-4" PVC) Unit = LF Takeoff Quan: 10.000 Engr Quan: 10.000 DBC DUCTBANK CREW 8.00 CH Prod: 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CRLSFTB | [5 empty] | LOW STRENGHT FTB | [13 empty] | 1 |  |  | 8.00 CY | [7 empty] | 107.150 857 857
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 12.00 TCY | [7 empty] | 24.5 | [13 empty] | 294 | [11 empty] | 294
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 10.00 LF | [7 empty] | 1220 | [23 empty] | 12200 |  | 12200
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 52.3 | [21 empty] | 418 |  |  |  | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 68.251 | [21 empty] | 546 |  |  |  | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 81.5 | [21 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 77.06 | [6 empty] | 805 | [18 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [7 empty] | 52.91 | [6 empty] | 1116 | [18 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [18 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [18 empty] | 780
$18,448.15 4.0000 MH/LF 40.00 MH [ 292.161 ] 3,481 | [44 empty] | 857 |  |  |  | 294 |  |  |  | 1616 |  | 12200 |  | 18448
=====> Item Totals: 598 - HSFTB ENCASED DUCT B $18,448.15 4.0000 MH/LF 40.00 MH | [30 empty] | ANK (4-4" PVC [ 292.161 ] | [6 empty] | ) 3,481 | [6 empty] | 857 |  |  |  | 294 |  |  |  | 1616 |  | 12200 |  | 18448
1,844.815 10 LF | [37 empty] | 348.06 | [6 empty] | 85.72 |  |  |  | 29.4 |  |  |  | 161.64 |  | 1220 |  | 1844.82
BID ITEM = 599 CLIENT# = 599 Land Item SCHEDULE: 1 100
Description = | [5 empty] | HSFTB ENCASED DUCT BANK (4-5" FIBERGLASS | [24 empty] | Unit = LF Takeoff Quan: 12.000 Engr Quan: 12.000
599.01 DBC 2CRLSFTB | [5 empty] | HSFTB ENCASED DUCT BANK (4-5" FIBERGLAS DUCTBANK CREW 8.00 LOW STRENGHT FTB 1.00 10.00 CY | [24 empty] | Quan: 12.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG CH Prod: 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 107.150 1,072 1,072
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 14.00 TCY | [7 empty] | 24.5 | [13 empty] | 343 | [11 empty] | 343
4ELEC | [5 empty] | Electrical sub | [13 empty] | 1 |  |  | 12.00 LF | [7 empty] | 1730 | [23 empty] | 20760 |  | 20760
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 52.3 | [21 empty] | 418 |  |  |  | 418
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 68.251 | [21 empty] | 546 |  |  |  | 546
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR | [7 empty] | 81.5 | [21 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 77.06 | [6 empty] | 805 | [18 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [7 empty] | 52.91 | [6 empty] | 1116 | [18 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [18 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 74.56 | [6 empty] | 780 | [18 empty] | 780
$27,271.45 3.3333 MH/LF | [22 empty] | 40.00 MH | [7 empty] | [ 243.468 ] | [6 empty] | 3481 | [6 empty] | 1072 |  |  |  | 343 |  |  |  | 1616 |  | 20760 |  | 27271
=====> Item Totals: 599 - HSFTB ENCASED DUCT B $27,271.45 3.3333 MH/LF 40.00 MH | [30 empty] | ANK (4-5" FIBE [ 243.468 ] | [6 empty] | RGLASS 3,481 | [6 empty] | 1072 |  |  |  | 343 |  |  |  | 1616 |  | 20760 |  | 27271
2,272.621 12 LF | [37 empty] | 290.05 | [6 empty] | 89.29 |  |  |  | 28.58 |  |  |  | 134.7 |  | 1730 |  | 2272.62
BID ITEM = 600 CLIENT# = 600 Land Item SCHEDULE: 1 100 Description = CONDUIT 2-4" PVC DIRECT BURY Unit = LF Takeoff Quan: 38.000 Engr Quan: 38.000
600.01 | [5 empty] | CONDUIT 2-4" PVC DIRECT BURY | [24 empty] | Quan: |  |  | 38.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [12 empty] | 8 | [11 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
4ELEC | [5 empty] | Electrical sub | [12 empty] | 1.00 38.00 LF | [9 empty] | 60 | [25 empty] | 2280 |  | 2280
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [12 empty] | 1.00 8.00 HR | [9 empty] | 51.051 | [23 empty] | 408 |  |  |  | 408
8EX100 | [5 empty] | 100 Excavator | [12 empty] | 1.00 8.00 HR | [9 empty] | 52.3 | [23 empty] | 418 |  |  |  | 418
FOCI | [5 empty] | Civil Forman | [12 empty] | 1.00 8.00 MH | [9 empty] | 77.06 | [12 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [12 empty] | 2.00 16.00 MH | [9 empty] | 52.91 | [12 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1.00 8.00 MH | [9 empty] | 74.56 | [12 empty] | 780 | [14 empty] | 780
$5,807.75 0.8421 MH/LF | [18 empty] | 32.00 MH | [9 empty] | [ 59.618 ] | [12 empty] | 2701 | [10 empty] | 827 |  | 2280 |  | 5808
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 600 CLIENT# = 600 Land Item SCHEDULE: 1 100 Description = CONDUIT 2-4" PVC DIRECT BURY Unit = LF Takeoff Quan: 38.000 Engr Quan: 38.000 =====> Item Totals: 600 - CONDUIT 2-4" PVC DIRECT BURY $5,807.75 0.8421 MH/LF 152.836 38 LF
32.00 MH | [30 empty] | [ 59.618 ] | [8 empty] | 2701 | [12 empty] | 827 |  | 2280 |  | 5808
[40 empty] | 71.08 | [12 empty] | 21.76 |  | 60 |  | 152.84
BID ITEM = 601 CLIENT# = 601 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ENLARGED VAULT ROOF OPENING | [23 empty] | Unit = EA Takeoff Quan: 7.000 Engr Quan: 7.000
601.01 | [5 empty] | ENLARGED VAULT ROOF OPENING | [23 empty] | Quan: 7.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS 2CPSC42 | [5 empty] | Earthwork 4 Man Crew 42 INCH SCL VAULT CA | [13 empty] | 1 |  |  | 56. 7.00 EA | [6 empty] | 00 CH Prod: 56.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 1,400.000 9,800 9,800
2CPVSLAB | [5 empty] | PRECAST VAULT LID SL | [13 empty] | 1 |  |  | 7.00 EA | [6 empty] | 1,000.000 7,000 7,000
2CR040 | [5 empty] | 4000LB READY MIX | [13 empty] | 1 |  |  | 14.00 CY | [6 empty] | 121.150 1,696 1,696
4SAWC | [5 empty] | Sawcutting | [13 empty] | 1 |  |  | 7.00 EA | [7 empty] | 0.68 | [23 empty] | 5 |  | 5
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 56.00 HR | [7 empty] | 51.051 | [18 empty] | 2859 | [6 empty] | 2859
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 56.00 HR | [7 empty] | 52.3 | [18 empty] | 2929 | [6 empty] | 2929
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 56.00 MH | [7 empty] | 77.06 | [8 empty] | 5636 | [16 empty] | 5636
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 112.00 MH | [7 empty] | 52.91 | [8 empty] | 7813 | [16 empty] | 7813
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 56.00 MH | [7 empty] | 74.56 | [8 empty] | 5457 | [16 empty] | 5457
$43,195.11 32.0000 MH/EA 224.00 MH | [30 empty] | [ 2265.473 ] | [8 empty] | 18907 |  |  |  |  | 18496 |  |  |  |  | 5788 |  |  |  |  | 5 |  | 43195
=====> Item Totals: 601 - ENLARGED VAULT ROOF OPENING $43,195.11 32.0000 MH/EA 224.00 MH [ 2265.473 ] 18,907 18,496 5,788 5 43,195 6,170.730 7 EA 2,700.94 2,642.30 826.81 0.68 6,170.73
BID ITEM = 602 CLIENT# = 602 Land Item SCHEDULE: 1 100
Description = | [5 empty] | VAULT 133M013 ACCESS MODIFICATION | [22 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
602.01 | [5 empty] | VAULT 133M013 ACCESS MODIFICATION | [22 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 16 |  | CH | Prod: | [8 empty] | 16.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSC42 | [5 empty] | 42 INCH SCL VAULT CA | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 1400 | [15 empty] | 1400 | [9 empty] | 1400
2CPVSLAB | [5 empty] | PRECAST VAULT LID SL | [13 empty] | 1 |  |  | 1.00 EA | [5 empty] | 1000 | [15 empty] | 1000 | [9 empty] | 1000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 51.051 | [19 empty] | 817 | [5 empty] | 817
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [5 empty] | 52.3 | [19 empty] | 837 | [5 empty] | 837
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 77.06 | [11 empty] | 1610 | [13 empty] | 1610
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 32.00 MH | [5 empty] | 52.91 | [11 empty] | 2232 | [13 empty] | 2232
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [5 empty] | 74.56 | [11 empty] | 1559 | [13 empty] | 1559
$9,455.49 64.0000 MH/EA 64.00 MH | [28 empty] | [ 4530.95 ] | [11 empty] | 5402 |  |  |  | 2400 |  |  |  | 1654 | [5 empty] | 9455
=====> Item Totals: 602 - VAULT 133M013 ACCESS MODIFICATION $9,455.49 64.0000 MH/EA 64.00 MH [ 4530.95 ] 5,402 2,400 1,654 9,455 9,455.490 1 EA 5,401.89 2,400.00 1,653.60 9,455.49
BID ITEM = 603 CLIENT# = 603 Land Item SCHEDULE: 1 100
Description = |  |  | REPLACE ACCESS FRAME AND COVER | [21 empty] | Unit = EA Takeoff Quan: 17.000 Engr Quan: 17.000
603.01 |  |  | REPLACE ACCESS FRAME AND COVER | [21 empty] | Quan: 17.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS 2CPSC42 |  |  | Earthwork 4 Man Crew 42 INCH SCL VAULT CA 1.00 17.00 EA | [21 empty] | 17.00 CH Prod: 17.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 1,400.000 23,800 23,800
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 603 CLIENT# = 603 Land Item SCHEDULE: 1 100 Description = REPLACE ACCESS FRAME AND COVER Unit = EA Takeoff Quan: 17.000 Engr Quan: 17.000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 17.00 HR | [7 empty] | 51.051 | [13 empty] | 868 | [11 empty] | 868
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 17.00 HR | [7 empty] | 52.3 | [13 empty] | 889 | [11 empty] | 889
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 17.00 MH | [7 empty] | 77.06 | [6 empty] | 1711 | [18 empty] | 1711
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 34.00 MH | [7 empty] | 52.91 | [6 empty] | 2372 | [18 empty] | 2372
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 17.00 MH | [7 empty] | 74.56 | [6 empty] | 1657 | [18 empty] | 1657
$31,296.45 4.0000 MH/EA 68.00 MH | [30 empty] | [ 283.184 ] | [6 empty] | 5740 | [6 empty] | 23800 | [7 empty] | 1757 |  |  |  | 31296
=====> Item Totals: 603 - REPLACE ACCESS FRAME AND COVER $31,296.45 4.0000 MH/EA 68.00 MH [ 283.184 ] 5,740 | [44 empty] | 23800 | [7 empty] | 1757 |  |  |  | 31296
1,840.968 17 EA 337.62 1,400.00 103.35 1,840.97
BID ITEM = 604 CLIENT# = 604 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SCL VAULT, 444-LA | [24 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
604.01 | [5 empty] | SCL VAULT, 444-LA | [24 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS 2CRCDF | [5 empty] | Earthwork 4 Man Crew CDF | [11 empty] | 1 |  |  |  |  | 10.00 CY | [5 empty] | 8 |  | CH Prod: 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 106.150 1,062 1,062
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [11 empty] | 1 |  |  |  |  | 12.00 TCY | [5 empty] | 24.5 | [15 empty] | 294 | [10 empty] | 294
4ELEC | [5 empty] | Electrical sub | [11 empty] | 1 |  |  |  |  | 1.00 EA | [5 empty] | 15000 | [25 empty] | 15000 | 15000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 |  |  |  |  | 8.00 HR | [5 empty] | 51.051 | [23 empty] | 408 |  |  | 408
8EX100 | [5 empty] | 100 Excavator | [11 empty] | 1 |  |  |  |  | 8.00 HR | [5 empty] | 52.3 | [23 empty] | 418 |  |  | 418
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 |  |  |  |  | 8.00 MH | [5 empty] | 77.06 | [8 empty] | 805 | [17 empty] | 805
LAG | [5 empty] | General Laborer | [11 empty] | 2 |  |  |  |  | 16.00 MH | [5 empty] | 52.91 | [8 empty] | 1116 | [17 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 8.00 MH | [5 empty] | 74.56 | [8 empty] | 780 | [17 empty] | 780
$19,883.25 32.0000 MH/EA 32.00 MH | [28 empty] | [ 2265.48 ] | [8 empty] | 2701 | [6 empty] | 1062 |  |  |  | 294 |  |  |  | 827 |  | 15000 | 19883
=====> Item Totals: $19,883.25 | [9 empty] | 604 32.0000 MH/EA | [7 empty] | - SCL VAULT, 444-LA 32.00 MH | [10 empty] | [ 2265.48 ] | [8 empty] | 2701 | [6 empty] | 1062 |  |  |  | 294 |  |  |  | 827 |  | 15000 | 19883
19883.25 | [5 empty] | 1 EA | [11 empty] | 2,700.95 1,061.50 | [30 empty] | 294 |  |  |  | 826.8 |  | 15000 | 19883.25
BID ITEM = 605 CLIENT# = 605 Land Item SCHEDULE: 1 100
Description = | [5 empty] | SCL VAULT, 712-LA | [11 empty] | Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
605.01 | [5 empty] | SCL VAULT, 712-LA | [11 empty] | Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS 2CRCDF | [5 empty] | Earthwork 4 Man Crew CDF | [11 empty] | 1 |  |  |  |  | 12.0 71.00 CY | [6 empty] | 0 CH Prod: 12.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 106.150 7,537 7,537
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [11 empty] | 1 |  |  |  |  | 133.00 TCY | [6 empty] | 24.5 | [14 empty] | 3259 | [10 empty] | 3259
4ELEC | [5 empty] | Electrical sub | [11 empty] | 1 |  |  |  |  | 1.00 EA | [6 empty] | 25000 | [24 empty] | 25000 | 25000
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 |  |  |  |  | 12.00 HR | [6 empty] | 51.051 | [22 empty] | 613 |  |  | 613
8EX100 | [5 empty] | 100 Excavator | [11 empty] | 1 |  |  |  |  | 12.00 HR | [6 empty] | 52.3 | [22 empty] | 628 |  |  | 628
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 |  |  |  |  | 12.00 MH | [6 empty] | 77.06 | [7 empty] | 1208 | [17 empty] | 1208
LAG | [5 empty] | General Laborer | [11 empty] | 2 |  |  |  |  | 24.00 MH | [6 empty] | 52.91 | [7 empty] | 1674 | [17 empty] | 1674
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 12.00 MH | [6 empty] | 74.56 | [7 empty] | 1169 | [17 empty] | 1169
$41,086.76 48.0000 MH/EA 48.00 MH | [29 empty] | [ 3398.2 ] | [7 empty] | 4051 | [6 empty] | 7537 |  |  |  | 3259 |  |  |  | 1240 |  | 25000 | 41087
=====> Item Totals: | [9 empty] | 605 | [7 empty] | - SCL VAULT, 712-LA
41086.76 | [9 empty] | 48.0000 MH/EA | [7 empty] | 48.00 MH | [11 empty] | [ 3398.2 ] | [7 empty] | 4051 | [6 empty] | 7537 |  |  |  | 3259 |  |  |  | 1240 |  | 25000 | 41087
41086.76 | [5 empty] | 1 EA | [11 empty] | 4,051.41 7,536.65 | [30 empty] | 3258.5 |  |  |  | 1240.2 |  | 25000 | 41086.76
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  | Unit Cost | [9 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 606 CLIENT# = 606 L CONSTRUCTION SURVEYING-ADDITIVE | [23 empty] | and Item SCHEDULE: 1 100 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
606.01 | [5 empty] | CONSTRUCTION SURVEYING-ADDITIVE | [23 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4SURV | [5 empty] | Surveying sub | [13 empty] | 1 |  |  | 1.00 LS | [6 empty] | 4850 | [9 empty] | 4850 | [16 empty] | 4850
BID ITEM = 607 CLIENT# = 607 Land Item SCHEDULE: 1 100 Description = CRITICAL PATH SCHEDULE UPDATE, MIN. BID Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
607.01 CRITICAL PATH SCHEDULE UPDATE, MIN. BID Quan: 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3CPM CPM SCHEDULE UPDAT 1.00 1.00 EA 2,500.000 2,500 | [52 empty] | 2500
=====> Item Totals $2,500.00 | [8 empty] | : 607 - CRITICAL PATH | [17 empty] | SCHEDULE UPDATE, M [ ] | [10 empty] | IN. BID 2,500 | [14 empty] | 2500
2500 | [8 empty] | 1 EA | [28 empty] | 2500 | [14 empty] | 2500
BID ITEM = 608 CLIENT# = 608 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MOBILIZATION-SCHEDULE 3 | [16 empty] | Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
608.01 | [5 empty] | MOBILIZATION-SCHEDULE 3 | [16 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3ADOHML | [5 empty] | ADDITIVE MANAGMEN | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 26530 | [8 empty] | 26530 | [12 empty] | 26530
3ADOHPA | [5 empty] | ADDITIVE PROJECT AD | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 79000 | [8 empty] | 79000 | [12 empty] | 79000
3ADOHPM | [5 empty] | ADDITIVE PROJECT MA | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 131279 | [8 empty] | 131279 | [12 empty] | 131279
3ADOHVC | [5 empty] | ADDITIVE VEHICLE COS | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 95000 | [8 empty] | 95000 | [12 empty] | 95000
3ADOHVF | [5 empty] | ADDITIVE VEHICLE FUE | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 32000 | [8 empty] | 32000 | [12 empty] | 32000
3ADPHTR | [5 empty] | ADDITIVE PROJECT TR | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 24144 | [8 empty] | 24144 | [12 empty] | 24144
387953 | [30 empty] | [ ] | [8 empty] | 387953 | [12 empty] | 387953
608.02 ADDITIVE CIVIL SUPERINTENDENTS Quan: 120.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZSUP ==> Superintendent 1.00 $59,100.42 5.3333 MH/SHIF
640.00 MH | [30 empty] | 72 | [8 empty] | 59100 | [12 empty] | 59100
640.00 MH | [30 empty] | [ 384 ] | [8 empty] | 59100 | [12 empty] | 59100
608.03 ADDITIVE CONCRETE SUPERINTENDENTS Quan: 80.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZSUP ==> Superintendent 1.00 $59,100.42 8.0000 MH/SHIF
640.00 MH | [30 empty] | 72 | [8 empty] | 59100 | [12 empty] | 59100
640.00 MH | [30 empty] | [ 576 ] | [8 empty] | 59100 | [12 empty] | 59100
608.04 ADDITIVE FIELD ENGINEERING Quan: 80.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
ZENF ==> Field Enjineer 1.00 640.00 MH | [26 empty] | 57.82 | [7 empty] | 44363 | [14 empty] | 44363
$44,363.08 8.0000 MH/SHIF 640.00 MH | [26 empty] | [ 462.56 ] | [7 empty] | 44363 | [14 empty] | 44363
608.05 |  |  | ADDITIVE MINI EX | [23 empty] | Quan: 40.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
8EX035 |  |  | ==> 35 Excavator | [10 empty] | 1 |  |  | 320.00 HR | [9 empty] | 28.830 9,226 9,226
608.06 |  |  | WATER TRUCK | [23 empty] | Quan: 20.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
8TRW |  |  | ==> Water Truck | [10 empty] | 1 |  |  | 160.00 HR | [9 empty] | 70.000 11,200 11,200
608.07 |  |  | SUB MOB | [23 empty] | Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 608 CLIENT# = 608 Land Item SCHEDULE: 1 100 Description = MOBILIZATION-SCHEDULE 3 Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000 4LAND Landscape sub 1.00 1.00 LS 0.001
=====> Item Totals: 608 - MOBILIZATION-SCHEDULE 3 387,953 20,426 570,943 387,953.00 20,425.60 570,942.52
570942.52 | [5 empty] | 1,920.0000 MH/LS | [16 empty] | 1,920.00 MH | [7 empty] | [ 129164.8 ] 162,564
570942.52 | [5 empty] | 1 LS | [24 empty] | 162563.92
BID ITEM = 609 CLIENT# = 609 Land Item SCHEDULE: 1 100
Description = |  |  | MAINTENANCE AND PROTECTION OF TRAFFIC CO | [23 empty] | Unit = |  |  | LS Takeoff Quan: | [15 empty] | 1 | [5 empty] | Engr Quan: |  |  | 1
609.01 |  |  | ADDITIVE TCS | [23 empty] | Quan: |  |  | 48.00 SHIF Hrs/Shft: | [14 empty] | 10 | Cal: 710 | [5 empty] | WC: WAAVG
LAFT ==> Traffic Control Supervi 1.00 640.00 MH | [26 empty] | 52.81 | [7 empty] | 51862 | [9 empty] | 51862
$51,862.26 13.3333 MH/SHIF 640.00 MH | [26 empty] | [ 905.304 ] | [7 empty] | 51862 | [9 empty] | 51862
609.02 ADDITIVE FLAGGERS Quan: 48.00 SHIF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
LAF ==> Flager 1.00 $28,530.73 10.0000 MH/SHIF
480.00 MH | [30 empty] | 44.84 | [8 empty] | 28531 | [12 empty] | 28531
480.00 MH | [30 empty] | [ 493.24 ] | [8 empty] | 28531 | [12 empty] | 28531
=====> Item Totals: 609 - MAINTENANCE AND PROTECTION OF TRAFFIC CO
80392.99 | [5 empty] | 1,120.0000 MH/LS | [16 empty] | 1,120.00 MH | [7 empty] | [ 67130.12 ] | [6 empty] | 80393 | [14 empty] | 80393
80392.99 | [5 empty] | 1 LS | [31 empty] | 80392.99 | [14 empty] | 80392.99
BID ITEM = 610 CLIENT# = 610 Land Item SCHEDULE: 1 100
Description = | [5 empty] | CLEARING & GRUBBING | [13 empty] | Unit = SF Takeoff Quan: 800.000 Engr Quan: 800.000
610.01 | [5 empty] | CLEARING & GRUBBING | [24 empty] | Quan: |  |  | 89.00 SY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 1.4 | [10 empty] | CH |  |  | Prod: | [7 empty] | 1.4000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3DEDU02S | [5 empty] | SOD DISPOSAL | [13 empty] | 1 |  |  | 17.00 TCY | [5 empty] | 28 | [19 empty] | 476 | [7 empty] | 476
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 1.40 HR | [5 empty] | 51.051 | [23 empty] | 71 |  |  |  | 71
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 1.40 HR | [5 empty] | 52.3 | [23 empty] | 73 |  |  |  | 73
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 1.40 MH | [5 empty] | 77.06 | [12 empty] | 141 | [14 empty] | 141
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 2.80 MH | [5 empty] | 52.91 | [12 empty] | 195 | [14 empty] | 195
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 1.40 MH | [5 empty] | 74.56 | [12 empty] | 136 | [14 empty] | 136
$1,093.33 0.0629 MH/SY 5.60 MH [ 4.454 ] | [41 empty] | 473 | [6 empty] | 476 |  |  |  | 145 |  |  |  | 1093
=====> Item Totals: 610 - CLEARING & GRUBBING $1,093.33 0.0070 MH/SF 5.60 MH [ 0.496 ] | [37 empty] | 473 | [10 empty] | 476 |  |  |  | 145 |  |  |  | 1093
1.367 800 SF | [37 empty] | 0.59 | [10 empty] | 0.6 |  |  |  | 0.18 |  |  |  | 1.37
BID ITEM = 611 CLIENT# = 611 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE CEMENT CONCRETE SIDEWALK | [22 empty] | Unit = SY Takeoff Quan: 500.000 Engr Quan: 500.000
611.01 | [5 empty] | REMOVE CEMENT CONCRETE SIDEWALK | [22 empty] | Quan: 500.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [22 empty] | 21 |  | CH |  |  | Prod: | [6 empty] | 21.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 106.00 TCY | [5 empty] | 29 | [19 empty] | 3074 | [5 empty] | 3074
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 21.00 HR | [5 empty] | 51.051 | [23 empty] | 1072 |  | 1072
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 21.00 HR | [5 empty] | 52.3 | [23 empty] | 1098 |  | 1098
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 21.00 MH | [5 empty] | 77.06 | [11 empty] | 2239 | [13 empty] | 2239
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 611 CLIENT# = 611 Land Item SCHEDULE: 1 100 Description = REMOVE CEMENT CONCRETE SIDEWALK Unit = SY Takeoff Quan: 500.000 Engr Quan: 500.000
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 42.00 MH | [5 empty] | 52.91 | [12 empty] | 3102 | [14 empty] | 3102
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 21.00 MH | [5 empty] | 74.56 | [12 empty] | 2168 | [14 empty] | 2168
12753.59 | [5 empty] | 0.1680 MH/SY | [16 empty] | 84.00 MH | [5 empty] | [ 12.615 ] | [12 empty] | 7509 | [6 empty] | 3074 |  |  |  | 2170 |  |  |  | 12754
611.02 | [5 empty] | GRADING SIDEWALKS | [24 empty] | Quan: |  |  | 500.00 SY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [13 empty] | 8 | [10 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 51.051 | [19 empty] | 408 | [7 empty] | 408
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 8.00 HR | [5 empty] | 52.3 | [19 empty] | 418 | [7 empty] | 418
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 77.06 | [12 empty] | 805 | [14 empty] | 805
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 16.00 MH | [5 empty] | 52.91 | [12 empty] | 1116 | [14 empty] | 1116
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH | [5 empty] | 74.56 | [12 empty] | 780 | [14 empty] | 780
3527.75 | [5 empty] | 0.0640 MH/SY | [16 empty] | 32.00 MH | [5 empty] | [ 4.531 ] | [12 empty] | 2701 | [6 empty] | 827 | [7 empty] | 3528
=====> Item Totals: 611 - REMOVE CEMENT CONCRETE SIDEWA $16,281.34 0.2320 MH/SY 116.00 MH [ 17.146 ] | [37 empty] | LK 10,210 | [10 empty] | 3074 |  |  |  | 2997 |  |  |  | 16281
32.563 500 SY | [37 empty] | 20.42 | [10 empty] | 6.15 |  |  |  | 5.99 |  |  |  | 32.56
BID ITEM = 612 CLIENT# = 612 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT Unit = SY Takeoff Quan: 3,108.000 Engr Quan: 3,108.000
612.01 | [5 empty] | REMOVE PAVEMENT | [24 empty] | Quan: |  |  | 3,108.00 SY | [7 empty] | Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew 95.77 | [24 empty] | CH |  |  | Prod: | [7 empty] | 95.7734 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
3DEDU02C | [5 empty] | Concrete Trucking and Du 1.00 | [16 empty] | 2,010.00 TCY | [7 empty] | 29 | [17 empty] | 58290 | [7 empty] | 58290
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 95.77 HR | [7 empty] | 68.251 | [21 empty] | 6536 |  |  |  | 6536
8EX200 | [5 empty] | 200 Excavator 1.00 | [16 empty] | 95.77 HR | [7 empty] | 78 | [21 empty] | 7470 |  |  |  | 7470
8LO950 | [5 empty] | 950 Loader 1.00 | [16 empty] | 95.77 HR | [7 empty] | 81.5 | [21 empty] | 7805 |  |  |  | 7805
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 95.77 MH | [7 empty] | 77.06 | [6 empty] | 10211 | [18 empty] | 10211
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 191.55 MH | [7 empty] | 52.91 | [6 empty] | 14149 | [18 empty] | 14149
OPE | [5 empty] | Operator - Excavator 2.00 | [16 empty] | 191.55 MH | [7 empty] | 74.56 | [6 empty] | 19774 | [18 empty] | 19774
$124,235.73 0.1540 MH/SY 478.87 MH [ 11.936 ] | [37 empty] | 44134 | [10 empty] | 58290 |  |  |  | 21812 |  |  |  | 124236
=====> Item Totals: 612 - REMOVE PAVEMENT $124,235.73 0.1540 MH/SY 478.87 MH [ 11.936 ] | [37 empty] | 44134 | [10 empty] | 58290 |  |  |  | 21812 |  |  |  | 124236
39.973 3108 SY | [37 empty] | 14.2 | [10 empty] | 18.75 |  |  |  | 7.02 |  |  |  | 39.97
BID ITEM = 613 CLIENT# = 613 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC Unit = SY Takeoff Quan: 1,242.000 Engr Quan: 1,242.000
613.01 REMOVE PAVEMENT, OVER 14 INCH DEPTH, IN Quan: 1,242.00 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 74.42 | [10 empty] | CH |  |  | Prod: | [5 empty] | 74.4270 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 1,238.00 TCY | [7 empty] | 29 | [17 empty] | 35902 | [5 empty] | 35902
3RAILDIS | [5 empty] | DISPOSAL OF RAIL | [13 empty] | 1 |  |  | 2,211.88 LF | [7 empty] | 2 | [17 empty] | 4424 | [5 empty] | 4424
3TIEDIS | [5 empty] | DISPOSAL RAIL TIE | [13 empty] | 1 |  |  | 552.78 LF | [7 empty] | 2 | [17 empty] | 1106 | [5 empty] | 1106
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 74.43 HR | [7 empty] | 68.251 | [21 empty] | 5080 |  | 5080
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 74.43 HR | [7 empty] | 78 | [21 empty] | 5806 |  | 5806
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 74.43 HR | [7 empty] | 81.5 | [21 empty] | 6066 |  | 6066
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 74.43 MH | [7 empty] | 77.06 | [8 empty] | 7936 | [14 empty] | 7936
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 148.85 MH | [7 empty] | 52.91 | [8 empty] | 10995 | [14 empty] | 10995
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 148.85 MH | [7 empty] | 74.56 | [8 empty] | 15366 | [14 empty] | 15366
$92,679.51 0.2996 MH/SY | [22 empty] | 372.13 MH | [7 empty] | [ 23.211 ] | [8 empty] | 34297 | [8 empty] | 41431 |  |  |  | 16951 |  | 92680
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 613 CLIENT# = 613 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC Unit = SY Takeoff Quan: 1,242.000 Engr Quan: 1,242.000 =====> Item Totals: 613 - REMOVE PAVEMENT, OVER 14 INCH DEPTH, INC $92,679.51 0.2996 MH/SY 74.621 1242 SY
372.13 MH | [30 empty] | [ 23.211 ] | [8 empty] | 34297 | [8 empty] | 41431 |  |  |  | 16951 |  |  |  | 92680
[40 empty] | 27.61 | [8 empty] | 33.36 |  |  |  | 13.65 |  |  |  | 74.62
BID ITEM = 614 CLIENT# = 614 Land Item SCHEDULE: 1 100 Description = REMOVE PIPE Unit = LF Takeoff Quan: 325.000 Engr Quan: 325.000
614.01 | [5 empty] | REMOVE PIPE | [24 empty] | Quan: |  |  | 325.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man 22.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 22.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3PIPEDIS | [5 empty] | PIPE DISPOSAL 1.00 | [16 empty] | 325.00 LF | [5 empty] | 2 | [19 empty] | 650 | [7 empty] | 650
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 22.00 HR | [5 empty] | 51.051 | [23 empty] | 1123 |  |  |  | 1123
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 22.00 HR | [5 empty] | 52.3 | [23 empty] | 1151 |  |  |  | 1151
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 22.00 MH | [5 empty] | 77.06 | [12 empty] | 2214 | [14 empty] | 2214
LAP | [5 empty] | Labor Underground Water 1.00 | [16 empty] | 22.00 MH | [5 empty] | 53.88 | [12 empty] | 1562 | [14 empty] | 1562
OPB | [5 empty] | Operator - Backhoe 1.00 | [16 empty] | 22.00 MH | [5 empty] | 74.56 | [12 empty] | 2144 | [14 empty] | 2144
OPE | [5 empty] | Operator - Excavator 1.00 | [16 empty] | 22.00 MH | [5 empty] | 74.56 | [12 empty] | 2144 | [14 empty] | 2144
$10,987.77 0.2707 MH/LF 88.00 MH [ 20.854 ] | [41 empty] | 8064 | [6 empty] | 650 |  |  |  | 2274 |  |  |  | 10988
=====> Item Totals: 614 - REMOVE PIPE $10,987.77 0.2707 MH/LF 88.00 MH | [28 empty] | [ 20.854 ] | [8 empty] | 8064 | [10 empty] | 650 |  |  |  | 2274 |  |  |  | 10988
33.809 325 LF | [37 empty] | 24.81 | [10 empty] | 2 |  |  |  | 7 |  |  |  | 33.81
BID ITEM = 615 CLIENT# = 615 Land Item SCHEDULE: 1 100
Description = | [6 empty] | REMOVE GATE VALVE | [11 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
615.01 | [6 empty] | REMOVE GATE VALVE | [11 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 3.00 CH Prod: 3.0000 CH Lab Pcs: 5.00 Eqp Pcs: | [56 empty] | 3
8EX135A | [6 empty] | 135 Excavator W/Attach | [11 empty] | 1 |  |  |  | 3.00 HR | [7 empty] | 68.251 | [21 empty] | 205 |  |  |  | 205
8EX200 | [6 empty] | 200 Excavator | [11 empty] | 1 |  |  |  | 3.00 HR | [7 empty] | 78 | [21 empty] | 234 |  |  |  | 234
8LO950 | [6 empty] | 950 Loader | [11 empty] | 1 |  |  |  | 3.00 HR | [7 empty] | 81.5 | [21 empty] | 244 |  |  |  | 244
FOCI | [6 empty] | Civil Forman | [11 empty] | 1 |  |  |  | 3.00 MH | [7 empty] | 77.06 | [6 empty] | 302 | [18 empty] | 302
LAP | [6 empty] | Labor Underground Water | [11 empty] | 2 |  |  |  | 6.00 MH | [7 empty] | 53.88 | [6 empty] | 426 | [18 empty] | 426
OPE | [6 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  | 3.00 MH | [7 empty] | 74.56 | [6 empty] | 292 | [18 empty] | 292
OPL | [6 empty] | Operator - Loader | [11 empty] | 1 |  |  |  | 3.00 MH | [7 empty] | 74.56 | [6 empty] | 292 | [18 empty] | 292
$1,995.88 5.0000 MH/EA 15.00 MH | [30 empty] | [ 367.337 ] | [6 empty] | 1313 | [14 empty] | 683 |  |  |  | 1996
=====> Item $1,995.88 | [6 empty] | Totals: 615 - 5.0000 MH/EA | [11 empty] | REMOVE GATE VALVE 15.00 MH [ 367.337 ] | [18 empty] | 1313 | [14 empty] | 683 |  |  |  | 1996
665.293 | [6 empty] | 3 EA | [30 empty] | 437.55 | [14 empty] | 227.74 |  |  |  | 665.29
BID ITEM = 616 CLIENT# = 616 Land Item SCHEDULE: 1 100 Description = REMOVE HYDRANT Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
616.01 | [5 empty] | REMOVE HYDRANT | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man 3.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 3.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme 1.00 | [16 empty] | 3.00 HR | [5 empty] | 51.051 | [23 empty] | 153 |  |  |  | 153
8EX100 | [5 empty] | 100 Excavator 1.00 | [16 empty] | 3.00 HR | [5 empty] | 52.3 | [23 empty] | 157 |  |  |  | 157
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 3.00 MH | [5 empty] | 77.06 | [12 empty] | 320 | [14 empty] | 320
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [6 empty] | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 616 CLIENT# = 616 Land Item SCHEDULE: 1 100
Description = | [5 empty] | REMOVE HYDRANT | [24 empty] | Unit = |  |  | EA |  |  |  | Takeoff Quan: | [10 empty] | 1 |  |  |  | Engr Quan: |  |  |  | 1
LAP | [5 empty] | Labor Underground Water | [11 empty] | 1 |  |  |  |  | 3.00 MH | [10 empty] | 53.88 |  |  |  | 226 | [18 empty] | 226
OPB | [5 empty] | Operator - Backhoe | [11 empty] | 1 |  |  |  |  | 3.00 MH | [10 empty] | 74.56 |  |  |  | 310 | [18 empty] | 310
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 3.00 MH | [10 empty] | 74.56 |  |  |  | 310 | [18 empty] | 310
$1,474.84 12.0000 MH/EA 12.00 MH | [30 empty] | [ 980.25 ] | [6 empty] | 1165 | [10 empty] | 310 | [7 empty] | 1475
=====> Item Totals: $1,474.84 | [9 empty] | 616 12.0000 MH/EA | [7 empty] | - REMOVE HYDRANT 12.00 MH | [12 empty] | [ 980.25 ] | [6 empty] | 1165 | [10 empty] | 310 | [7 empty] | 1475
1474.84 | [9 empty] | 1 EA | [27 empty] | 1164.81 | [10 empty] | 310.03 | [7 empty] | 1474.84
BID ITEM = 617 Land Item SCHEDULE: 1 100 Description = REMOVE PAVEMENT RAIL AND CAR SYSTEM Unit = SY Takeoff Quan: 360.000 Engr Quan: 360.000
617.01 REMOVE PAVEMENT RAIL AND CAR SYSTEM Quan: 360.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
DEM | [5 empty] | Demo 5 Man Crew | [13 empty] | 33.5 | [10 empty] | CH |  |  | Prod: | [6 empty] | 33.5000 CH | [7 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
3DEDU02C | [5 empty] | Concrete Trucking and Du | [13 empty] | 1 |  |  | 344.00 TCY | [7 empty] | 29 | [17 empty] | 9976 | [5 empty] | 9976
3RAILDIS | [5 empty] | DISPOSAL OF RAIL | [13 empty] | 1 |  |  | 720.00 LF | [7 empty] | 2 | [17 empty] | 1440 | [5 empty] | 1440
3TIEDIS | [5 empty] | DISPOSAL RAIL TIE | [13 empty] | 1 |  |  | 360.00 LF | [7 empty] | 2 | [17 empty] | 720 | [5 empty] | 720
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 33.50 HR | [7 empty] | 68.251 | [21 empty] | 2286 |  | 2286
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 33.50 HR | [7 empty] | 78 | [21 empty] | 2613 |  | 2613
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 33.50 HR | [7 empty] | 81.5 | [21 empty] | 2730 |  | 2730
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 33.50 MH | [7 empty] | 77.06 | [9 empty] | 3372 | [13 empty] | 3372
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  | 67.00 MH | [7 empty] | 52.91 | [9 empty] | 4674 | [13 empty] | 4674
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  | 67.00 MH | [7 empty] | 74.56 | [9 empty] | 6529 | [13 empty] | 6529
$34,340.41 0.4652 MH/SY | [22 empty] | 167.50 MH | [7 empty] | [ 33.984 ] | [9 empty] | 14575 | [7 empty] | 12136 |  |  |  | 7630 |  | 34340
=====> Item Totals: 617 - REMOVE PAVEMENT RAIL AND CAR SYSTEM
$34,340.41 0.4652 MH/SY 167.50 MH | [30 empty] | [ 33.984 ] | [9 empty] | 14575 | [7 empty] | 12136 |  |  |  | 7630 |  | 34340
95.390 360 SY | [40 empty] | 40.49 | [7 empty] | 33.71 |  |  |  | 21.19 |  | 95.39
BID ITEM = 618 CLIENT# = 618 Land Item SCHEDULE: 1 100 EA Takeoff Quan: 3.000 Engr Quan: 3.000
Description = |  |  | REMOVE TREE | [23 empty] | Unit =
618.01 |  |  | REMOVE TREE | [23 empty] | Quan:
3TREEREM |  |  | TREE REMOVAL | [10 empty] | 1 |  |  | 3.00 EA | [9 empty] | 2
350 | [37 empty] | 7050 | [14 empty] | 7050
[ ] | [37 empty] | 7050 | [14 empty] | 7050
[38 empty] | 2350 | [14 empty] | 2350
=====> Item Totals: 618 - REMOVE TREE $7,050.00 2,350.000 3 EA
BID ITEM = 619 CLIENT# = 619 Land Item SCHEDULE: 1 100 Description = REMOVE VALVE CHAMBER Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
619.01 | [5 empty] | REMOVE VALVE CHAMBER | [24 empty] | Quan: |  |  | 2.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 4 | [7 empty] | CH |  |  | Prod: | [7 empty] | 4.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR 68.251 | [29 empty] | 273 |  |  |  | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR 78.000 | [29 empty] | 312 |  |  |  | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR 81.500 | [29 empty] | 326 |  |  |  | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH 77.060 | [18 empty] | 403 | [14 empty] | 403
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 619 CLIENT# = 619 Land Item SCHEDULE: 1 100 Description = REMOVE VALVE CHAMBER Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
LAP |  |  |  |  | Labor Underground Water | [13 empty] | 2 |  |  |  | 8.00 MH | [7 empty] | 53.88 | [8 empty] | 568 | [12 empty] | 568
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [12 empty] | 390
OPL |  |  |  |  | Operator - Loader | [13 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [12 empty] | 390
$2,661.19 10.0000 MH/EA 20.00 MH | [30 empty] | [ 734.66 ] | [8 empty] | 1750 | [12 empty] | 911 |  |  |  | 2661
=====> Item Totals: 619 - REMOVE VALVE CHAMBER
2661.19 |  |  |  |  | 10.0000 MH/EA | [13 empty] | 20.00 MH | [11 empty] | [ 734.66 ] | [8 empty] | 1750 | [12 empty] | 911 |  |  |  | 2661
1330.595 |  |  |  |  | 2 EA | [34 empty] | 875.1 | [12 empty] | 455.5 |  |  |  | 1330.6
BID ITEM = 620 CLIENT# = 620 Land Item SCHEDULE: 1 100
| Description = |  |  |  | SAWCUT RIGID PAVEMENT, FULL DEPTH | [25 empty] | Unit = |  |  | LF Takeoff Quan: 234.000 Engr Quan: 234.000
| 620 |  |  |  | SAWCUT RIGID PAVEMENT, FULL DEPTH | [25 empty] | Quan: |  |  | 3,954.34 INFT Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4SAWC Sawcutting 1.00 3,954.34 INFT 0.680 2,689 2,689
BID ITEM = 621 CLIENT# = 621 Land Item SCHEDULE: 1 100 Description = ABANDON VALVE CHAMBER Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
621.01 |  |  |  |  | ABANDON VALVE CHAMBER | [25 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM |  |  |  |  | Unerground Utilities 6 Man | [19 empty] | 1 | [5 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2AGS17 |  |  |  |  | SEATTLE TYPE 1@110.2 | [13 empty] | 1 | [5 empty] | 2.00 TON 25.750 57 57
8EX135A |  |  |  |  | 135 Excavator W/Attach | [13 empty] | 1 | [5 empty] | 1.00 HR 68.251 | [19 empty] | 68 | [11 empty] | 68
8EX200 |  |  |  |  | 200 Excavator | [13 empty] | 1 | [5 empty] | 1.00 HR 78.000 | [19 empty] | 78 | [11 empty] | 78
8LO950 |  |  |  |  | 950 Loader | [13 empty] | 1 | [5 empty] | 1.00 HR 81.500 | [19 empty] | 81 | [11 empty] | 81
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 | [5 empty] | 1.00 MH 77.060 | [16 empty] | 101 | [14 empty] | 101
LAP |  |  |  |  | Labor Underground Water | [13 empty] | 2 | [5 empty] | 2.00 MH 53.880 | [16 empty] | 142 | [14 empty] | 142
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 | [5 empty] | 1.00 MH 74.560 | [16 empty] | 97 | [14 empty] | 97
OPL |  |  |  |  | Operator - Loader | [13 empty] | 1 | [5 empty] | 1.00 MH 74.560 | [16 empty] | 97 | [14 empty] | 97
$722.07 5.0000 MH/EA 5.00 MH | [24 empty] | [ 367.35 ] | [16 empty] | 438 |  |  | 57 | [7 empty] | 228 |  |  |  | 722
=====> Ite $722.07 |  |  |  |  | m Totals: 621 - 5.0000 MH/EA | [13 empty] | ABANDON VALVE C 5.00 MH | [5 empty] | HAMBER [ 367.35 ] | [12 empty] | 438 | [6 empty] | 57 | [7 empty] | 228 |  |  |  | 722
722.07 |  |  |  |  | 1 EA | [32 empty] | 437.56 | [6 empty] | 56.78 | [7 empty] | 227.73 |  |  |  | 722.07
BID ITEM = 623 CLIENT# = 623 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL MOSAIC TILE Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
623.01 REMOVE, STORE AND REINSTALL MOSAIC TIL Quan: | [33 empty] | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 1.50 CH | [33 empty] | Prod: | [7 empty] | 1.5000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 1.50 HR | [10 empty] | 51.051 | [18 empty] | 77 |  |  |  | 77
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 1.50 HR | [10 empty] | 52.3 | [18 empty] | 78 |  |  |  | 78
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 1.50 MH | [10 empty] | 77.06 | [7 empty] | 151 | [14 empty] | 151
LAG |  |  |  |  | General Laborer | [13 empty] | 2 |  |  |  | 3.00 MH | [10 empty] | 52.91 | [7 empty] | 209 | [14 empty] | 209
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 1.50 MH | [10 empty] | 74.56 | [7 empty] | 146 | [14 empty] | 146
$661.45 6.0000 MH/EA 6.00 MH | [33 empty] | [ 424.77 ] | [7 empty] | 506 | [10 empty] | 155 |  |  |  | 661
=====> Item Totals: 623 - REMOVE, STORE AND REINSTALL MOSAIC TILE $661.45 6.0000 MH/EA 6.00 MH [ 424.77 ] 506 155 661
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 623 CLIENT# = 623 Land Item SCHEDULE: 1 100 Description = REMOVE, STORE AND REINSTALL MOSAIC TILE Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000 661.450 1 EA 506.44 155.01 661.45
BID ITEM = 624 CLIENT# = 624 Land Item SCHEDULE: 1 100 Description = REMOVE CURB, GRANITE W/ SALVAGE Unit = LF Takeoff Quan: 730.000 Engr Quan: 730.000
624.01 | [5 empty] | REMOVE CURB, GRANITE W/ SALVAGE | [24 empty] | Quan: |  |  | 730.00 LF | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 37 | [5 empty] | CH |  |  | Prod: | [7 empty] | 37.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 37.00 HR 51.051 | [27 empty] | 1889 |  |  |  | 1889
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 37.00 HR 52.300 | [27 empty] | 1935 |  |  |  | 1935
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 37.00 MH 77.060 | [16 empty] | 3724 | [14 empty] | 3724
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 74.00 MH 52.910 | [16 empty] | 5162 | [14 empty] | 5162
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 37.00 MH 74.560 | [16 empty] | 3606 | [14 empty] | 3606
$16,315.83 0.2027 MH/LF 148.00 MH [ 14.353 ] 12,492 | [52 empty] | 3824 |  |  |  | 16316
=====> Item Totals: 624 - REMOVE CURB, GRANITE W/ SALVAGE $16,315.83 0.2027 MH/LF 22.350 730 LF
148.00 MH | [30 empty] | [ 14.353 ] | [8 empty] | 12492 | [12 empty] | 3824 |  |  |  | 16316
[40 empty] | 17.11 | [12 empty] | 5.24 |  |  |  | 22.35
BID ITEM = 625 CLIENT# = 625 Land Item SCHEDULE: 1 100 Description = COMMON EXCAVATION Unit = CY Takeoff Quan: 794.000 Engr Quan: 794.000
625.01 | [5 empty] | COMMON EXCAVATION | [24 empty] | Quan: |  |  | 794.00 CY | [7 empty] | Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
GRM | [5 empty] | Grading 5 Man Crew 34.00 | [24 empty] | CH |  |  | Prod: | [7 empty] | 34.0000 CH Lab Pcs: 5.00 Eqp Pcs: 4.00
3DEDU02D | [5 empty] | Dirt Trucking and Dump 1.00 | [16 empty] | 952.19 TCY | [7 empty] | 24.5 | [17 empty] | 23329 | [7 empty] | 23329
8DO0450 | [5 empty] | JD 450 Dozer 1.00 | [16 empty] | 34.00 HR | [7 empty] | 49.5 | [21 empty] | 1683 |  |  |  | 1683
8EX135A | [5 empty] | 135 Excavator W/Attach 1.00 | [16 empty] | 34.00 HR | [7 empty] | 68.251 | [21 empty] | 2321 |  |  |  | 2321
8EX200 | [5 empty] | 200 Excavator 1.00 | [16 empty] | 34.00 HR | [7 empty] | 78 | [21 empty] | 2652 |  |  |  | 2652
8RO84 | [5 empty] | 84 Inch Roller 1.00 | [16 empty] | 34.00 HR | [7 empty] | 55.7 | [21 empty] | 1894 |  |  |  | 1894
FOCI | [5 empty] | Civil Forman 1.00 | [16 empty] | 34.00 MH | [7 empty] | 77.06 | [10 empty] | 3625 | [14 empty] | 3625
LAG | [5 empty] | General Laborer 2.00 | [16 empty] | 68.00 MH | [7 empty] | 52.91 | [10 empty] | 5023 | [14 empty] | 5023
OPE | [5 empty] | Operator - Excavator 2.00 | [16 empty] | 68.00 MH | [7 empty] | 74.56 | [10 empty] | 7020 | [14 empty] | 7020
$47,545.71 0.2141 MH/CY 170.00 MH | [30 empty] | [ 16.587 ] | [6 empty] | 15668 | [10 empty] | 23329 |  |  |  | 8549 |  |  |  | 47546
=====> Item Totals: 625 - COMMON EXCAVATION $47,545.71 0.2141 MH/CY 170.00 MH | [30 empty] | [ 16.587 ] | [6 empty] | 15668 | [10 empty] | 23329 |  |  |  | 8549 |  |  |  | 47546
59.881 794 CY | [37 empty] | 19.73 | [10 empty] | 29.38 |  |  |  | 10.77 |  |  |  | 59.88
BID ITEM = 626 CLIENT# = 626 Land Item SCHEDULE: 1 100 Description = SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN Unit = SF Takeoff Quan: 364.000 Engr Quan: 364.000
626.01 SAFETY SYSTEMS IN TRENCH EXCAVATION, M Quan: 364.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3SHOR SHORING ADDITIVE 1.00 1.00 LS 5,000.000 5,000 5,000
=====> Item Totals: 626 - SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN
5000 | [30 empty] | [ ] | [8 empty] | 5000 | [12 empty] | 5000
13.736 | [5 empty] | 364 SF | [33 empty] | 13.74 | [12 empty] | 13.74
Activity Desc Resource Pcs | [23 empty] | Quantity |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 627 CLIENT# = 62 MINERAL AGGREGATE, TYPE 2 | [17 empty] | 7 Land Item SCHEDULE: 1 100 Unit = TN Takeoff Quan: 1,456.000 Engr Quan: 1,456.000
627.01 | [5 empty] | MINERAL AGGREGATE, TYPE | [17 empty] | 2 Quan: 1,456.00 TN Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
GRM | [5 empty] | Grading 5 Man Crew | [17 empty] | 48 | [6 empty] | CH |  |  | Prod: | [5 empty] | 48.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 4
2AGS02 | [5 empty] | SEATTLE TYPE 2@110.2 | [13 empty] | 1 |  |  |  | 1,456.00 TON | [9 empty] | 29.75 | [5 empty] | 47756 | [16 empty] | 47756
8DO0450 | [5 empty] | JD 450 Dozer | [13 empty] | 1 |  |  |  | 48.00 HR | [6 empty] | 49.5 | [17 empty] | 2376 | [5 empty] | 2376
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  | 48.00 HR | [6 empty] | 68.251 | [17 empty] | 3276 | [5 empty] | 3276
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  | 48.00 HR | [6 empty] | 78 | [17 empty] | 3744 | [5 empty] | 3744
8RO84 | [5 empty] | 84 Inch Roller | [13 empty] | 1 |  |  |  | 48.00 HR | [6 empty] | 55.7 | [17 empty] | 2674 | [5 empty] | 2674
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  | 48.00 MH | [6 empty] | 77.06 | [8 empty] | 5118 | [14 empty] | 5118
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  | 96.00 MH | [6 empty] | 52.91 | [8 empty] | 7091 | [14 empty] | 7091
OPE | [5 empty] | Operator - Excavator | [13 empty] | 2 |  |  |  | 96.00 MH | [6 empty] | 74.56 | [8 empty] | 9910 | [14 empty] | 9910
$81,944.66 0.1648 MH/TN 240.00 MH | [30 empty] | [ 12.77 ] | [8 empty] | 22119 |  |  |  |  | 47756 |  |  |  | 12070 | [5 empty] | 81945
=====> Item Totals: $81,944.66 | [9 empty] | 627 0.1648 MH/TN | [6 empty] | - MINERAL AGGREGATE, TYPE 2 240.00 MH | [16 empty] | [ 12.77 ] |  |  |  | 22119 | [6 empty] | 47756 |  |  |  | 12070 | [5 empty] | 81945
56.281 1456 TN | [37 empty] | 15.19 | [6 empty] | 32.8 |  |  |  | 8.29 | [5 empty] | 56.28
BID ITEM = 628 CLIENT# = 628 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [18 empty] | Unit = TN Takeoff Quan: 107.000 Engr Quan: 107.000
628.01 | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [18 empty] | Quan: 107.00 TN Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS17 | [5 empty] | SEATTLE TYPE 1@110.2 | [13 empty] | 1 |  |  |  |  | 107.00 TON | [5 empty] | 25.75 | [6 empty] | 3038 | [14 empty] | 3038
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 75.19 TCY | [5 empty] | 24.5 | [17 empty] | 1842 |  |  |  | 1842
4879.82 | [30 empty] | [ ] | [6 empty] | 3038 | [10 empty] | 1842 |  |  |  | 4880
=====> Item Totals: $4,879.82 | [10 empty] | 628 |  |  | - MINERAL AGGREGATE, TYPE 17 | [22 empty] | [ ] | 3038 | [10 empty] | 1842 |  |  |  | 4880
45.606 | [13 empty] | 107 TN | [23 empty] | 28.39 | [10 empty] | 17.22 |  |  |  | 45.61
BID ITEM = 629 CLIENT# = 629 Land Item SCHEDULE: 1 100 Description = MINERAL AGGREGATE, TYPE 9 Unit = CY Takeoff Quan: 3.000 Engr Quan: 3.000
629.01 |  |  |  | MINERAL AGGREGATE, TYPE 9 | [26 empty] | Quan: |  |  | 3.00 CY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS |  |  |  | Earthwork 4 Man Crew | [20 empty] | 0.5 | [5 empty] | CH |  |  | Prod: | [7 empty] | 0.5000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
8BA310A |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 | [6 empty] | 0.50 HR 51.051 | [27 empty] | 26 |  |  |  | 26
8EX100 |  |  |  | 100 Excavator | [13 empty] | 1 | [6 empty] | 0.50 HR 52.300 | [27 empty] | 26 |  |  |  | 26
FOCI |  |  |  | Civil Forman | [13 empty] | 1 | [6 empty] | 0.50 MH 77.060 | [16 empty] | 50 | [14 empty] | 50
LAG |  |  |  | General Laborer | [13 empty] | 2 | [6 empty] | 1.00 MH 52.910 | [16 empty] | 70 | [14 empty] | 70
OPE |  |  |  | Operator - Excavator | [13 empty] | 1 | [6 empty] | 0.50 MH 74.560 | [16 empty] | 49 | [14 empty] | 49
$220.47 0.6666 MH/CY 2.00 MH | [24 empty] | [ 47.197 ] | [16 empty] | 169 | [10 empty] | 52 |  |  |  | 220
=====> |  |  |  | Item Totals: | [5 empty] | 629 | [7 empty] | - MINERAL AGGREGATE, TYPE 9
220.47 | [9 empty] | 0.6666 MH/CY | [7 empty] | 2.00 MH | [15 empty] | [ 47.197 ] |  |  |  | 169 | [14 empty] | 52 |  |  |  | 220
73.49 | [9 empty] | 3 CY | [27 empty] | 56.27 | [14 empty] | 17.22 |  |  |  | 73.49
BID ITEM = 630 CLIENT# = 630 Land Item SCHEDULE: 1 100 Description = PAVEMENT PATCH, TEMPORARY Unit = TN Takeoff Quan: 30.000 Engr Quan: 30.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 630 CLIENT# = 630 Land Item SCHEDULE: 1 100 Description = PAVEMENT PATCH, TEMPORARY Unit = TN Takeoff Quan: 30.000 Engr Quan: 30.000
630.01 | [5 empty] | PAVEMENT PATCH, TEMPORARY | [24 empty] | Quan: |  |  | 30.00 TN | [7 empty] | Hrs/Shft: 10.00 Cal: X10 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 5 | [5 empty] | CH |  |  | Prod: | [7 empty] | 5.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
3COLDMIX | [5 empty] | COLD MIX | [13 empty] | 1 |  |  |  |  | 30.00 TN |  |  |  | 110 | [19 empty] | 3300 | [7 empty] | 3300
3DEDU02A | [5 empty] | Asphalt trucking and Dump | [13 empty] | 1 |  |  |  |  | 30.00 TCY |  |  |  | 29 | [19 empty] | 870 | [7 empty] | 870
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 5.00 HR |  |  |  | 51.051 | [23 empty] | 255 |  |  |  | 255
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 5.00 HR |  |  |  | 52.3 | [23 empty] | 261 |  |  |  | 261
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 5.00 MH |  |  |  | 77.06 | [12 empty] | 906 | [14 empty] | 906
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 10.00 MH |  |  |  | 52.91 | [12 empty] | 1251 | [14 empty] | 1251
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 5.00 MH |  |  |  | 74.56 | [12 empty] | 877 | [14 empty] | 877
$7,721.80 0.6666 MH/TN 20.00 MH | [28 empty] | [ 85.813 ] | [12 empty] | 3035 | [6 empty] | 4170 |  |  |  | 517 |  |  |  | 7722
=====> Item Totals: 630 - PAVEMENT PATCH, TEMPORARY
$7,721.80 0.6666 MH/TN 20.00 MH | [28 empty] | [ 85.813 ] | [10 empty] | 3035 | [8 empty] | 4170 |  |  |  | 517 |  |  |  | 7722
257.393 30 TN | [39 empty] | 101.17 | [8 empty] | 139 |  |  |  | 17.22 |  |  |  | 257.39
BID ITEM = 631 CLIENT# = 631 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC, VARIABLE MIXES, 12 IN Unit = SY Takeoff Quan: 2,939.000 Engr Quan: 2,939.000
631.01 ROADWAY CEM CONC, VARIABLE MIXES, 12 IN Quan: 2,939.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 156 | [10 empty] | CH |  |  | Prod: | [5 empty] | 156.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP3D | [5 empty] | 3 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 999.26 CY | [7 empty] | 125.15 | [13 empty] | 137876 | [7 empty] | 137876
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 2,957.00 LF | [7 empty] | 15.75 | [13 empty] | 51346 | [7 empty] | 51346
2JOINT | [5 empty] | JOINT MATERIAL@110.2 | [13 empty] | 1 |  |  | 1,332.00 LF | [7 empty] | 2.75 | [13 empty] | 4038 | [7 empty] | 4038
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 444.00 EA | [7 empty] | 2.94 | [13 empty] | 1439 | [7 empty] | 1439
3SAWSEAL | [5 empty] | SAWING AND SEALING | [13 empty] | 1 |  |  | 2,957.00 LF | [7 empty] | 3.68 | [17 empty] | 10882 |  |  |  | 10882
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 1,248.00 MH | [7 empty] | 64.98 | [8 empty] | 106326 | [12 empty] | 106326
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 156.00 MH | [7 empty] | 68.98 | [8 empty] | 14089 | [12 empty] | 14089
325996.93 | [5 empty] | 0.4777 MH/SY | [16 empty] | 1,404.00 MH | [7 empty] | [ 34.38 ] | [8 empty] | 120415 |  |  |  |  | 194700 |  |  |  | 10882 |  |  |  | 325997
=====> Item Totals: 631 - ROADWAY CEM CONC, VARIABLE MIXES, 12 IN $325,996.93 0.4777 MH/SY 110.921 2939 SY
1,404.00 MH | [30 empty] | [ 34.38 ] 120,415 | [13 empty] | 194700 |  |  |  | 10882 |  |  |  | 325997
[31 empty] | 40.97 | [13 empty] | 66.25 |  |  |  | 3.7 |  |  |  | 110.92
BID ITEM = 632 CLIENT# = 632 Land Item SCHEDULE: 1 100 Description = ROADWAY CEM CONC, HES (24 HR), 12 IN Unit = SY Takeoff Quan: 1,686.000 Engr Quan: 1,686.000
632.01 ROADWAY CEM CONC, HES (24 HR), 12 IN Quan: 1,686.00 SY Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
COL | [5 empty] | Concrete 9 Man Crew | [13 empty] | 89.92 | [10 empty] | CH |  |  | Prod: | [6 empty] | 89.9200 CH | [7 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2CRP1D | [5 empty] | 1 DAY PAVING M@110.2 | [13 empty] | 1.02 |  |  | 562.82 CY | [5 empty] | 187.15 | [15 empty] | 116128 | [7 empty] | 116128
2DOWEL | [5 empty] | DOWELS@110.25% | [13 empty] | 1 |  |  | 1,696.00 LF | [5 empty] | 15.75 | [15 empty] | 29450 | [7 empty] | 29450
2JOINT | [5 empty] | JOINT MATERIAL@110.2 | [13 empty] | 1 |  |  | 762.00 SY | [5 empty] | 2.75 | [15 empty] | 2310 | [7 empty] | 2310
2TIEBAR | [5 empty] | TIE BARS@110.25% | [13 empty] | 1 |  |  | 254.00 EA | [5 empty] | 2.94 | [15 empty] | 823 | [7 empty] | 823
3SAWSEAL | [5 empty] | SAWING AND SEALING | [13 empty] | 1 |  |  | 1,696.00 LF | [5 empty] | 3.68 | [19 empty] | 6241 |  |  |  | 6241
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 719.36 MH | [5 empty] | 64.98 | [11 empty] | 83027 | [11 empty] | 83027
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 89.92 MH | [5 empty] | 68.98 | [11 empty] | 11006 | [11 empty] | 11006
$248,986.19 0.4800 MH/SY 809.28 MH [ 47.106 ] 94,033 | [44 empty] | 148712 |  |  |  | 6241 |  |  |  | 248986
=====> Item Totals: 632 - ROADWAY CEM CONC, HES (24 HR), 12 IN
$248,986.19 0.4800 MH/SY 809.28 MH | [28 empty] | [ 47.106 ] | [11 empty] | 94033 |  |  |  | 148712 |  |  |  | 6241 |  |  |  | 248986
147.679 1686 SY | [40 empty] | 55.77 |  |  |  | 88.2 |  |  |  | 3.7 |  |  |  | 147.68
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 633 CLIENT# = 6 PCCP PANEL REINFORCING | [16 empty] | 33 Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 32.000 Engr Quan: 32.000
633.01 | [5 empty] | PCCP PANEL REINFORCING | [16 empty] | Quan: 32.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
COL Concrete 9 Man Crew 5.12 CH Prod: 5.1200 CH | [48 empty] | Lab Pcs: |  |  |  | 9 |  | Eqp Pcs: |  | 0
2RB05 #5 Rebar@110.25% 1.00 7,872.00 LF 1.000 8,679 | [56 empty] | 8679
CEJ | [5 empty] | Cement Mason | [13 empty] | 8 |  |  | 40.96 MH | [7 empty] | 64.98 | [8 empty] | 3490 | [8 empty] | 3490
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 5.12 MH | [7 empty] | 68.98 | [8 empty] | 462 | [8 empty] | 462
$12,630.98 1.4400 MH/EA 46.08 MH
[ 103.633 ] | [37 empty] | 3952 | [6 empty] | 8679 | [7 empty] | 12631
[ 103.633 ] | [37 empty] | 3952 | [6 empty] | 8679 | [7 empty] | 12631
[38 empty] | 123.5 | [6 empty] | 271.22 | [7 empty] | 394.72
=====> Item Totals: 633 - PCCP PANEL REINFORCING $12,630.98 1.4400 MH/EA 46.08 MH 394.718 32 EA
BID ITEM = 634 CLIENT# = 634 Land Item SCHEDULE: 1 100
Description = | [5 empty] | INLET, TYPE 250B | [13 empty] | Unit = EA Takeoff Quan: 7.000 Engr Quan: 7.000
634.01 | [5 empty] | INLET, TYPE 250B | [13 empty] | Quan: 7.00 EA Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 28 | [10 empty] | CH | Prod: | [8 empty] | 28.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSIN250 | [5 empty] | TYPE 250 INLET@110.25 | [13 empty] | 1 |  |  | 7.00 EA | [5 empty] | 355 | [15 empty] | 2740 | [9 empty] | 2740
2CPSZ263 | [5 empty] | TYPE 263 INLET@110.25 | [13 empty] | 1 |  |  | 7.00 EA | [5 empty] | 700 | [15 empty] | 5402 | [9 empty] | 5402
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 28.00 HR | [5 empty] | 51.051 | [19 empty] | 1429 | [5 empty] | 1429
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 28.00 HR | [5 empty] | 52.3 | [19 empty] | 1464 | [5 empty] | 1464
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 28.00 MH | [5 empty] | 77.06 | [11 empty] | 3822 | [13 empty] | 3822
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 28.00 MH | [5 empty] | 53.88 | [11 empty] | 2690 | [13 empty] | 2690
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 28.00 MH | [5 empty] | 74.56 | [11 empty] | 3700 | [13 empty] | 3700
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 28.00 MH | [5 empty] | 74.56 | [11 empty] | 3700 | [13 empty] | 3700
$24,946.14 16.0000 MH/EA 112.00 MH | [28 empty] | [ 1680.36 ] | [11 empty] | 13910 |  |  |  | 8142 |  |  |  | 2894 | [5 empty] | 24946
=====> Item Totals: 634 - INLET, TYPE 250B $24,946.14 16.0000 MH/EA 112.00 MH [ 1680.36 ] 13,910 8,142 2,894 24,946 3,563.734 7 EA 1,987.19 1,163.14 413.40 3,563.73
BID ITEM = 635 CLIENT# = 635 Land Item SCHEDULE: 1 100 Description = PIPE, CB CONN, D.I., CL 50, 8 IN Unit = LF Takeoff Quan: 64.000 Engr Quan: 64.000
UNS Underground Utilities 4 Man 16.00 CH Prod: 16.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2BI635PIPE BID ITEM 635 P@110.25 1.00 1.00 LS 2,670.980 2,945 | [56 empty] | 2945
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 51.051 | [17 empty] | 817 | [5 empty] | 817
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 16.00 HR | [7 empty] | 52.3 | [17 empty] | 837 | [5 empty] | 837
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 77.06 | [8 empty] | 2184 | [14 empty] | 2184
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 53.88 | [8 empty] | 1537 | [14 empty] | 1537
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 2114 | [14 empty] | 2114
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 16.00 MH | [7 empty] | 74.56 | [8 empty] | 2114 | [14 empty] | 2114
$12,547.13 1.0000 MH/LF 64.00 MH [ 105.023 ] 7,949 | [44 empty] | 2945 |  |  |  | 1654 | [5 empty] | 12547
=====> Item Totals: 635 - PIPE, CB CONN, D.I., CL 50, 8 IN
$12,547.13 1.0000 MH/LF 64.00 MH | [30 empty] | [ 105.023 ] | [8 empty] | 7949 |  |  |  |  | 2945 |  |  |  | 1654 | [5 empty] | 12547
196.049 64 LF | [39 empty] | 124.2 |  |  |  |  | 46.01 |  |  |  | 25.84 | [5 empty] | 196.05
| Activity Desc Resource Pcs | [21 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract Total
BID ITEM = 636 CLIENT# = 636 Land Item SCHEDULE: 1 100
Description = |  |  |  |  | PIPE, INLET CONN, D.I., CL 50, 8 IN | [25 empty] | Unit = LF Takeoff Quan: 116.000 Engr Quan: 116.000
636.01 |  |  |  |  | PIPE, INLET CONN, D.I., CL 50, 8 IN | [25 empty] | Quan: 116.00 LF Hrs/Shft: 10.00 Cal: Z10 WC: WAAVG
UNS 2BI636PIPE |  |  |  |  | Underground Utilities 4 Man BID ITEM 636 P@110.25 1.00 | [20 empty] | 1.00 LS |  |  | 28 |  | CH Prod: 28.0000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00 3,624.280 3,996 3,996
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 28.00 HR | [5 empty] | 51.051 | [15 empty] | 1429 | [11 empty] | 1429
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 28.00 HR | [5 empty] | 52.3 | [15 empty] | 1464 | [11 empty] | 1464
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 28.00 MH | [5 empty] | 77.06 | [10 empty] | 4449 | [16 empty] | 4449
LAP |  |  |  |  | Labor Underground Water | [13 empty] | 1 |  |  |  | 28.00 MH | [5 empty] | 53.88 | [10 empty] | 3128 | [16 empty] | 3128
OPB |  |  |  |  | Operator - Backhoe | [13 empty] | 1 |  |  |  | 28.00 MH | [5 empty] | 74.56 | [10 empty] | 4306 | [16 empty] | 4306
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 28.00 MH | [5 empty] | 74.56 | [10 empty] | 4306 | [16 empty] | 4306
$23,079.33 0.9655 MH/LF 112.00 MH [ 118.301 ] 16,190 | [44 empty] | 3996 | [7 empty] | 2894 |  |  |  | 23079
=====> Item Totals: 636 - PIPE, INLET CONN, D.I., CL 50, 8 IN
$23,079.33 0.9655 MH/LF 112.00 MH | [28 empty] | [ 118.301 ] | [10 empty] | 16190 |  |  |  |  | 3996 | [7 empty] | 2894 |  |  |  | 23079
198.960 116 LF | [39 empty] | 139.57 |  |  |  |  | 34.45 | [7 empty] | 24.95 |  |  |  | 198.96
BID ITEM = 637 CLIENT# = 637 Land Item SCHEDULE: 1 100 Description = 4 INCH DRAIN PIPE, GIP, SCH 40 Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
EAS Earthwork 4 Man Crew 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2BI637PIPE BID ITEM 637 P@110.25 1.00 1.00 LS 162.000 179 | [56 empty] | 179
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 4.00 HR | [7 empty] | 51.051 | [17 empty] | 204 | [5 empty] | 204
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 4.00 HR | [7 empty] | 52.3 | [17 empty] | 209 | [5 empty] | 209
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 77.06 | [6 empty] | 403 | [16 empty] | 403
LAG |  |  |  |  | General Laborer | [13 empty] | 2 |  |  |  | 8.00 MH | [7 empty] | 52.91 | [6 empty] | 558 | [16 empty] | 558
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
$1,942.48 8.0000 MH/EA 16.00 MH | [30 empty] | [ 566.365 ] | [6 empty] | 1350 | [6 empty] | 179 |  |  |  | 413 | [5 empty] | 1942
=====> Ite $1,942.48 |  |  |  |  | m Totals: 637 - 8.0000 MH/EA | [13 empty] | 4 INCH DRAIN PIPE, GIP, 16.00 MH | [11 empty] | SCH 40 [ 566.365 ] | [6 empty] | 1350 | [6 empty] | 179 |  |  |  | 413 | [5 empty] | 1942
971.24 |  |  |  |  | 2 EA | [32 empty] | 675.24 | [6 empty] | 89.31 |  |  |  | 206.7 | [5 empty] | 971.24
BID ITEM = 638 CLIENT# = 638 Land Item SCHEDULE: 1 100
Description = |  |  |  |  | BEDDING, CL B, 8 IN PIPE | [17 empty] | Unit = LF Takeoff Quan: 180.000 Engr Quan: 180.000
638.01 |  |  |  |  | BEDDING, CL B, 8 IN PIPE | [17 empty] | Quan: 180.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS09 |  |  |  |  | SEATTLE TYPE 9@110.2 | [13 empty] | 1 |  |  |  | 136.00 TON | [7 empty] | 29.75 | [6 empty] | 4461 | [14 empty] | 4461
3DEDU02D |  |  |  |  | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  | 96.00 TCY | [7 empty] | 24.5 | [17 empty] | 2352 |  |  |  | 2352
6812.72 | [30 empty] | [ ] | [6 empty] | 4461 | [10 empty] | 2352 |  |  |  | 6813
=====> Item Totals: $6,812.72 | [10 empty] | 638 | [5 empty] | - BEDDING, CL B, 8 IN PIPE | [13 empty] | [ ] | [6 empty] | 4461 | [10 empty] | 2352 |  |  |  | 6813
37.848 | [13 empty] | 180 LF | [23 empty] | 24.78 | [10 empty] | 13.07 |  |  |  | 37.85
BID ITEM = 639 CLIENT# = 639 Land Item SCHEDULE: 1 100 Description = TELEVISION INSPECTION Unit = LF Takeoff Quan: 64.000 Engr Quan: 64.000
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource | [13 empty] | Pcs | [8 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 639 CLIENT# = 639 Land Item SCHEDULE: 1 100
Description = |  |  | TELEVISION INSPECTION | [23 empty] | Unit = LF Takeoff Quan: 64.000 Engr Quan: 64.000
639.01 |  |  | TELEVISION INSPECTION | [23 empty] | Quan: 64.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3CCTV TV INSPECTION 1.00 1.00 LS 2,500.000 | [32 empty] | 2500 | [16 empty] | 2500
=====> Item Totals: 639 - TELEVISION INSPECTION $2,500.00 [ ] | [32 empty] | 2500 | [16 empty] | 2500
39.063 64 LF | [32 empty] | 39.06 | [16 empty] | 39.06
BID ITEM = 640 CLIENT# = 640 Land Item SCHEDULE: 1 100
Description = | [6 empty] | TEE, 8 IN, CUT-IN EXISTING CONC PIPE | [21 empty] | Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
640.01 | [6 empty] | TEE, 8 IN, CUT-IN EXISTING CONC PIPE | [21 empty] | Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [6 empty] | Underground Utilities 4 Man | [21 empty] | 4 |  | CH | Prod: | [8 empty] | 4.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
3SPUCORE | [6 empty] | SPU CORE TAP | [11 empty] | 1 |  |  |  | 2.00 EA | [5 empty] | 150 | [19 empty] | 300 | [5 empty] | 300
8BA310A | [6 empty] | 418 Backhoe W/Attachme | [11 empty] | 1 |  |  |  | 4.00 HR | [5 empty] | 51.051 | [23 empty] | 204 |  | 204
8EX100 | [6 empty] | 100 Excavator | [11 empty] | 1 |  |  |  | 4.00 HR | [5 empty] | 52.3 | [23 empty] | 209 |  | 209
FOCI | [6 empty] | Civil Forman | [11 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 77.06 | [11 empty] | 403 | [13 empty] | 403
LAP | [6 empty] | Labor Underground Water | [11 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 53.88 | [11 empty] | 284 | [13 empty] | 284
OPB | [6 empty] | Operator - Backhoe | [11 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 74.56 | [11 empty] | 390 | [13 empty] | 390
OPE | [6 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 74.56 | [11 empty] | 390 | [13 empty] | 390
$2,179.59 8.0000 MH/EA 16.00 MH | [28 empty] | [ 616.125 ] | [11 empty] | 1466 | [7 empty] | 300 |  |  |  | 413 |  | 2180
=====> Item $2,179.59 | [6 empty] | Totals: 640 - 8.0000 MH/EA | [11 empty] | TEE, 8 IN, CUT-IN EXISTING CONC PIPE 16.00 MH [ 616.125 ] | [18 empty] | 1466 | [10 empty] | 300 |  |  |  | 413 |  | 2180
1089.795 | [6 empty] | 2 EA | [30 empty] | 733.1 | [10 empty] | 150 |  |  |  | 206.7 |  | 1089.8
BID ITEM = 641 CLIENT# = 641 Land Item SCHEDULE: 1 100
Description = | [5 empty] | ADJUST EXISTING MH, CB, OR VC | [18 empty] | Unit = EA Takeoff Quan: 10.000 Engr Quan: 10.000
641.01 | [5 empty] | ADJUST EXISTING MH, CB, OR VC Quan: 10.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS | [5 empty] | Earthwork 4 Man Crew | [18 empty] | 9 | [5 empty] | CH | Prod: | [8 empty] | 9.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 9.00 HR |  |  |  | 51.051 | [19 empty] | 459 | [5 empty] | 459
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  |  |  | 9.00 HR |  |  |  | 52.3 | [19 empty] | 471 | [5 empty] | 471
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 9.00 MH |  |  |  | 77.06 | [11 empty] | 906 | [13 empty] | 906
LAG | [5 empty] | General Laborer | [13 empty] | 2 |  |  |  |  | 18.00 MH |  |  |  | 52.91 | [11 empty] | 1256 | [13 empty] | 1256
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 9.00 MH |  |  |  | 74.56 | [11 empty] | 877 | [13 empty] | 877
$3,968.70 3.6000 MH/EA 36.00 MH | [28 empty] | [ 254.865 ] | [11 empty] | 3039 | [7 empty] | 930 | [5 empty] | 3969
=====> Item Totals: 641 - ADJUST EXISTING MH, CB, OR VC $3,968.70 3.6000 MH/EA 396.870 10 EA
36.00 MH | [30 empty] | [ 254.865 ] | [8 empty] | 3039 | [12 empty] | 930 |  |  |  | 3969
[40 empty] | 303.86 | [12 empty] | 93.01 |  |  |  | 396.87
BID ITEM = 642 CLIENT# = 642 Land Item SCHEDULE: 1 100
Description = |  |  | ADJUST EXISTING HANDHOLE | [23 empty] | Unit = |  |  | EA Takeoff Quan: 1.000 Engr Quan: 1.000
642.01 |  |  | ADJUST EXISTING HANDHOLE | [23 empty] | Quan: |  |  | 1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS Earthwork 4 Man Crew 0.50 CH Prod: 0.5000 CH Lab Pcs: 4.00 Eqp Pcs: 2.00
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit | [6 empty] | Unit Cost |  |  |  | Perm Constr Labor Material Matl/Exp | [14 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM = 642 CLIENT# = 642 Land Item SCHEDULE: 1 10 Description = ADJUST EXISTING HANDHOLE Unit = EA Takeoff Quan: | [49 empty] | 0 1.000 Engr Quan: 1.000
8BA310A |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  |  | 0.50 HR | [10 empty] | 51.051 | [15 empty] | 26 | [6 empty] | 26
8EX100 |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  |  | 0.50 HR | [10 empty] | 52.3 | [15 empty] | 26 | [6 empty] | 26
FOCI |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  |  | 0.50 MH | [10 empty] | 77.06 |  |  |  | 50 | [18 empty] | 50
LAG |  |  |  | General Laborer | [13 empty] | 2 |  |  |  |  | 1.00 MH | [10 empty] | 52.91 |  |  |  | 70 | [18 empty] | 70
OPE |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 0.50 MH | [10 empty] | 74.56 |  |  |  | 49 | [18 empty] | 49
$220.47 2.0000 MH/EA 2.00 MH | [33 empty] | [ 141.59 ] |  |  |  | 169 | [11 empty] | 52 | [6 empty] | 220
=====> $220.47 |  |  |  | Item Totals: | [5 empty] | 642 2.0000 MH/EA | [7 empty] | - ADJUST EXISTING HANDHOLE 2.00 MH | [15 empty] | [ 141.59 ] |  |  |  | 169 | [11 empty] | 52 | [6 empty] | 220
220.47 | [9 empty] | 1 EA | [27 empty] | 168.82 | [11 empty] | 51.65 | [6 empty] | 220.47
BID ITEM = 643 CLIENT# = 643 Land Item SCHEDULE: 1 100 Description = UTILITY CASTING, TYPE 230 Unit = EA Takeoff Quan: 7.000 Engr Quan: 7.000
EAS Earthwork 4 Man Crew 3.50 CH Prod: 3.5000 CH | [48 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2CPSZ230 TYPE 230 CASTI@110.25 1.00 7.00 EA 785.000 6,058 | [56 empty] | 6058
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 3.50 HR | [7 empty] | 51.051 | [17 empty] | 179 | [5 empty] | 179
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 3.50 HR | [7 empty] | 52.3 | [17 empty] | 183 | [5 empty] | 183
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 3.50 MH | [7 empty] | 77.06 | [6 empty] | 352 | [16 empty] | 352
LAG |  |  |  |  | General Laborer | [13 empty] | 2 |  |  |  | 7.00 MH | [7 empty] | 52.91 | [6 empty] | 488 | [16 empty] | 488
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 3.50 MH | [7 empty] | 74.56 | [6 empty] | 341 | [16 empty] | 341
$7,601.63 2.0000 MH/EA 14.00 MH | [30 empty] | [ 141.593 ] | [6 empty] | 1182 | [6 empty] | 6058 |  |  |  | 362 | [5 empty] | 7602
=====> Ite $7,601.63 |  |  |  |  | m Totals: 643 - 2.0000 MH/EA | [13 empty] | UTILITY CASTING, TYPE 14.00 MH | [11 empty] | 230 [ 141.593 ] | [6 empty] | 1182 | [6 empty] | 6058 |  |  |  | 362 | [5 empty] | 7602
1085.947 |  |  |  |  | 7 EA | [32 empty] | 168.81 | [6 empty] | 865.46 |  |  |  | 51.67 | [5 empty] | 1085.95
BID ITEM = 644 CLIENT# = 644 Land Item SCHEDULE: 1 100 LS Takeoff Quan: 1.000 Engr Quan: 1.000
Description = |  |  | EROSION CONTROL | [23 empty] | Unit =
644.01 |  |  | EROSION CONTROL ADDITIVE | [23 empty] | Quan:
3EROSIONAD |  |  | EROSION CONTROL AD 1.00 | [15 empty] | 1.00 LS | [7 empty] | 5
0 | [37 empty] | 5000 | [14 empty] | 5000
[ ] | [37 empty] | 5000 | [14 empty] | 5000
[38 empty] | 5000 | [14 empty] | 5000
=====> Item Totals: | [10 empty] | 644 | [5 empty] | - EROSION CONTROL
5000
5000 | [13 empty] | 1 LS
BID ITEM = 645 CLIENT# = 645 Land Item SCHEDULE: 1 100
Description = |  |  | SEEDED LAWN INSTALATION | [23 empty] | Unit = |  |  | SF Takeoff Quan: 551.000 Engr Quan: 551.000
645.01 |  |  | SEEDED LAWN INSTALLATION | [23 empty] | Quan: |  |  | 551.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND Landscape sub 1.00 551.00 SF 2.000 1,102 1,102
Activity Desc Resource Pcs | [22 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = 646 CLIENT# = 646 TREE, DECIDUOUS, 1-3/4 IN TO 2 IN CAL | [20 empty] | Land Item SCHEDULE: 1 100 Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
646.01 | [5 empty] | TREE, DECIDUOUS, 1-3/4 IN TO 2 IN CAL | [20 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND Landscape sub 1.00 3.00 EA 750.000 2,250 2,250
BID ITEM = 647 CLIENT# = 647 Land Item SCHEDULE: 1 100
Description = |  |  | TOPSOIL, TYPE A | [23 empty] | Unit = CY Takeoff Quan: 20.000 Engr Quan: 20.000
647.01 |  |  | TOPSOIL, TYPE A | [23 empty] | Quan: 20.00 CY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 20.00 CY | [9 empty] | 150.000 3,000 3,000
BID ITEM = 648 CLIENT# = 648 Land Item SCHEDULE: 1 100
Description = |  |  | TREE ROOT BARRIER | [23 empty] | Unit = LF Takeoff Quan: 84.000 Engr Quan: 84.000
648.01 |  |  | TREE ROOT BARRIER | [23 empty] | Quan: 84.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND |  |  | Landscape sub | [10 empty] | 1 |  |  | 84.00 LF | [9 empty] | 20.000 1,680 1,680
BID ITEM = 649 CLIENT# = 649 Land Item SCHEDULE: 1 100 Description = FLEXIBLE POROUS SURFACE TREATMENT Unit = SF Takeoff Quan: 2,335.000 Engr Quan: 2,335.000
COM Concrete 6 Man Crew 55.00 CH Prod: 2FLEXIPAVE FLEXI PAVE MAT@110.2 1.00 1.00 LS 15,714.550
55.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
17325 | [56 empty] | 17325
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 275.00 MH | [7 empty] | 64.98 | [8 empty] | 23429 | [12 empty] | 23429
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 55.00 MH | [7 empty] | 68.98 | [8 empty] | 4967 | [12 empty] | 4967
45721.82 | [5 empty] | 0.1413 MH/SF | [16 empty] | 330.00 MH | [7 empty] | [ 10.205 ] | [8 empty] | 28397 |  |  |  |  | 17325 | [7 empty] | 45722
=====> Item Totals: 649 - FLEXIBLE POROUS SURFACE TREATMENT
$45,721.82 0.1413 MH/SF 330.00 MH | [30 empty] | [ 10.205 ] | [8 empty] | 28397 |  |  |  |  | 17325 | [7 empty] | 45722
19.581 2335 SF | [39 empty] | 12.16 |  |  |  |  | 7.42 | [7 empty] | 19.58
BID ITEM = 650 CLIENT# = 650 Land Item SCHEDULE: 1 100 Description = LANDSCAPE ESTABLISHMENT - BID ADDITIVE, Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
650.01 LANDSCAPE ESTABLISHMENT - BID ADDITIVE, Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
4LAND Landscape sub 1.00 1.00 LS 2,000.000 2,000 2,000
BID ITEM = 651 CLIENT# = 651 Land Item SCHEDULE: 1 100
Description = |  |  | CURB, CEM CONC W/ 25% POZZOLANS | [23 empty] | Unit = |  |  | LF Takeoff Quan: 1,426.000 Engr Quan: 1,426.000
651.01 |  |  | CURB, CEM CONC W/ 25% POZZOLANS | [23 empty] | Quan: |  |  | 1,426.00 LF Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 651 CLIENT# = 651 Land Item SCHEDULE: 1 100 Description = CURB, CEM CONC W/ 25% POZZOLANS Unit = LF Takeoff Quan: 1,426.000 Engr Quan: 1,426.000 COM Concrete 6 Man Crew 64.20 CH Prod: 64.2062 CH Lab Pcs: 6.00 Eqp Pcs: 0.00
2CR025 2500LB READY M@110.2 1.00 13.46 CY | [30 empty] | 115.35 | [6 empty] | 1712 | [14 empty] | 1712
2CRUBHOOP CURB HOOPS@110.25% 1.00 475.33 EA | [30 empty] | 2 | [6 empty] | 1048 | [14 empty] | 1048
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 321.03 MH | [7 empty] | 64.98 | [6 empty] | 28969 | [6 empty] | 28969
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 64.21 MH | [7 empty] | 68.98 | [6 empty] | 6143 | [6 empty] | 6143
$37,871.08 0.2701 MH/LF 385.24 MH [ 20.691 ] 35,111 | [44 empty] | 2760 | [7 empty] | 37871
=====> Item Totals: 651 - CURB, CEM CONC W/ 25% POZZOLANS $37,871.08 0.2701 MH/LF 385.24 MH [ 20.691 ] | [37 empty] | 35111 | [6 empty] | 2760 | [7 empty] | 37871
26.558 1426 LF | [37 empty] | 24.62 | [6 empty] | 1.94 | [7 empty] | 26.56
BID ITEM = 652 CLIENT# = 652 Land Item SCHEDULE: 1 100 Description = RESET MONUMENT AND MONUMENT FRAME AND Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
652.01 RESET MONUMENT AND MONUMENT FRAME A Quan: 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
EAS |  |  |  |  | Earthwork 4 Man Crew | [13 empty] | 4 | [11 empty] | CH | Prod: | [8 empty] | 4.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
4SURV |  |  |  |  | Surveying sub | [13 empty] | 1 |  |  |  | 2.00 EA | [5 empty] | 1500 | [25 empty] | 3000 |  | 3000
8BA310A |  |  |  |  | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  |  | 4.00 HR | [5 empty] | 51.051 | [19 empty] | 204 | [7 empty] | 204
8EX100 |  |  |  |  | 100 Excavator | [13 empty] | 1 |  |  |  | 4.00 HR | [5 empty] | 52.3 | [19 empty] | 209 | [7 empty] | 209
FOCI |  |  |  |  | Civil Forman | [13 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 77.06 | [11 empty] | 403 | [15 empty] | 403
LAG |  |  |  |  | General Laborer | [13 empty] | 2 |  |  |  | 8.00 MH | [5 empty] | 52.91 | [11 empty] | 558 | [15 empty] | 558
OPE |  |  |  |  | Operator - Excavator | [13 empty] | 1 |  |  |  | 4.00 MH | [5 empty] | 74.56 | [11 empty] | 390 | [15 empty] | 390
$4,763.87 8.0000 MH/EA 16.00 MH | [28 empty] | [ 566.365 ] | [11 empty] | 1350 | [7 empty] | 413 | [5 empty] | 3000 |  | 4764
=====> Ite $4,763.87 |  |  |  |  | m Totals: 652 - 8.0000 MH/EA | [13 empty] | RESET MONUMENT 16.00 MH | [9 empty] | AND MONUMENT F [ 566.365 ] | [8 empty] | RAME AND CO 1,350 | [10 empty] | 413 | [5 empty] | 3000 |  | 4764
2381.935 |  |  |  |  | 2 EA | [32 empty] | 675.24 | [10 empty] | 206.7 | [5 empty] | 1500 |  | 2381.94
BID ITEM = 653 CLIENT# = 653 Land Item SCHEDULE: 1 100 Takeoff Quan: 390.000 Engr Quan: 390.000
Description = |  |  | SIDEWALK, CEM CONC W/ 25% POZZOLANS | [23 empty] | Unit = SY
653.01 |  |  | SIDEWALK, CEM CONC W/ 25% POZZOLANS | [23 empty] | Quan: 390.0
COM 2CR025 |  |  | Concrete 6 Man Crew 41.00 2500LB READY M@110.2 1.00 45.00 CY | [23 empty] | CH Pr 115.350
od:
41.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
5723 | [56 empty] | 5723
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 205.00 MH | [7 empty] | 64.98 | [8 empty] | 18499 |  |  |  |  | 18499
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 41.00 MH | [7 empty] | 68.98 | [8 empty] | 3922 |  |  |  |  | 3922
$28,143.52 0.6307 MH/SY 246.00 MH | [30 empty] | [ 48.311 ] 22,421 5,723 28,144
=====> Item Totals: 653 - SIDEWALK, CEM CONC W/ 25% POZZOLANS
$28,143.52 0.6307 MH/SY 246.00 MH | [30 empty] | [ 48.311 ] | [8 empty] | 22421 |  |  |  |  | 5723 | [7 empty] | 28144
72.163 390 SY | [39 empty] | 57.49 |  |  |  |  | 14.67 | [7 empty] | 72.16
BID ITEM | [5 empty] | = |  | 654 | [5 empty] | CLIENT# = | [8 empty] | 654 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | SIDEWALK, THICKENED EDGE W/ 25% | [22 empty] | Unit = |  |  |  |  | LF Takeoff Quan: 1,426.000 Engr Quan: 1,426.000
654.01 | [5 empty] | SIDEWALK, THICKENED EDGE W/ 25% | [22 empty] | Quan: |  |  |  |  | 1,426.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2CR025 2500LB READY M@110.2 1.00 98.38 CY 115.350 12,511 12,511
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 654 CLIENT# = 654 Land Item SCHEDULE: 1 100 Description = SIDEWALK, THICKENED EDGE W/ 25% Unit = LF Takeoff Quan: 1,426.000 Engr Quan: 1,426.000
=====> Item Totals: | [10 empty] | 654 |  |  | - SIDEWALK, THICKENED EDGE W/ 25%
12511.32 | [13 empty] | [ ] | [25 empty] | 12511 | [12 empty] | 12511
8.774 | [13 empty] | 1426 LF | [25 empty] | 8.77 | [12 empty] | 8.77
BID ITEM = 655 CLIENT# = 655 Land Item SCHEDULE: 1 100 Takeoff Quan: 41.000 Engr Quan: 41.000
Description = |  |  | POZZOLANS DRIVEWAY, CEM CONC, HES (24 HR | [23 empty] | Unit = SY
655.01 |  |  | POZZOLANS DRIVEWAY, CEM CONC, HES (24 H | [23 empty] | Quan: 41.0
COM 2CR025 |  |  | Concrete 6 Man Crew 8.00 2500LB READY M@110.2 1.00 8.00 CY | [23 empty] | CH Pro 187.150
d:
8.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 6 |  | Eqp Pcs: |  | 0
1651 | [56 empty] | 1651
CEJ | [5 empty] | Cement Mason | [13 empty] | 5 |  |  | 40.00 MH | [7 empty] | 64.98 | [8 empty] | 4617 |  |  |  |  | 4617
FOCO | [5 empty] | Concrete Forman | [13 empty] | 1 |  |  | 8.00 MH | [7 empty] | 68.98 | [8 empty] | 979 |  |  |  |  | 979
$7,246.55 1.1707 MH/SY 48.00 MH | [30 empty] | [ 115.282 ] 5,596 1,651 7,247
=====> Item Totals: 655 - POZZOLANS DRIVEWAY, CEM CONC, HES (24 HR
$7,246.55 1.1707 MH/SY 48.00 MH | [30 empty] | [ 115.282 ] | [8 empty] | 5596 |  |  |  |  | 1651 | [7 empty] | 7247
176.745 41 SY | [39 empty] | 136.49 |  |  |  |  | 40.26 | [7 empty] | 176.75
BID ITEM = 656 CLIENT# = 656 Land Item SCHEDULE: 1 100
Description = |  |  | MOBILIZATION-SCHEDULE 4 | [23 empty] | Unit = |  |  | LS Takeoff Quan: 1.000 Engr Quan: 1.000
656.01 |  |  | MOBILIZATION-SCHEDULE 4 | [23 empty] | Quan: |  |  | 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
There are no cost resources for this activity.
=====> Item Totals: 656 - MOBILIZATION-SCHEDULE 4 $0.00 [ ] 0.000 1 LS
BID ITEM = 657 CLIENT# = 657 Land Item SCHEDULE: 1 100 Description = SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN Unit = SF Takeoff Quan: 6,725.000 Engr Quan: 6,725.000
657.01 SAFETY SYSTEMS IN TRENCH EXCAVATION, M Quan: 6,725.00 SF Hrs/Shft: 10.00 Cal: 510 | [51 empty] | WC: WAAVG
3SHORING shoring water line 1.00 1.00 LS 10,000.000 10,000 | [54 empty] | 10000
=====> Item Totals: 657 - SAFETY SYSTEMS IN TRENCH EXCAVATION, MIN $10,000.00 [ ] 10,000 | [54 empty] | 10000
1.487 6725 SF 1.49 | [54 empty] | 1.49
BID ITEM = 658 CLIENT# = 658 Land Item SCHEDULE: 1 100
Description = | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [18 empty] | Unit = TN Takeoff Quan: 527.000 Engr Quan: 527.000
658.01 | [5 empty] | MINERAL AGGREGATE, TYPE 17 | [18 empty] | Quan: 527.00 TN Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  |  |  | 527.00 TON | [5 empty] | 25.75 | [8 empty] | 13570 | [12 empty] | 13570
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  |  |  | 327.00 TCY | [5 empty] | 24.5 | [17 empty] | 8012 |  |  |  | 8012
21581.75 | [30 empty] | [ ] | [8 empty] | 13570 | [8 empty] | 8012 |  |  |  | 21582
| Activity Desc Resource Pcs | [21 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
| BID ITEM = 658 CLIENT# = 658 Land Item SCHEDULE: 1 100 Description = MINERAL AGGREGATE, TYPE 17 Unit = TN Takeoff Quan: 527.000 | [51 empty] | Engr Quan: |  |  |  | 527
| =====> Item Totals: 658 - MINERAL AGGREGATE, TYPE 17 $21,581.75 [ ] 13,570 8,012 | [55 empty] | 21582
| 40.952 527 TN 25.75 15.20 | [55 empty] | 40.95
BID ITEM = 659 Land Item SCHEDULE: 1 100 Description = TEMPORARY WATER MAINS AND SERVICES ADDIT Unit = LS Takeoff Quan: 1.000 Engr Quan: 1.000
659.01 PHASE 11 TEMP MAIN Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 24 | [10 empty] | CH | Prod: | [8 empty] | 24.0000 CH | [7 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 24.00 HR | [5 empty] | 51.051 | [19 empty] | 1225 | [5 empty] | 1225
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 24.00 HR | [5 empty] | 52.3 | [19 empty] | 1255 | [5 empty] | 1255
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 77.06 | [11 empty] | 2416 | [13 empty] | 2416
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 53.88 | [11 empty] | 1704 | [13 empty] | 1704
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 74.56 | [11 empty] | 2339 | [13 empty] | 2339
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 74.56 | [11 empty] | 2339 | [13 empty] | 2339
$11,277.57 96.0000 MH/LS | [22 empty] | 96.00 MH | [5 empty] | [ 7393.57 ] | [11 empty] | 8797 | [7 empty] | 2480 | [5 empty] | 11278
659.02 | [5 empty] | PHASE 12 TEMP MAIN | [24 empty] | Quan: |  |  | 1.00 LS | [6 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [13 empty] | 24 | [10 empty] | CH |  |  | Prod: | [6 empty] | 24.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 24.00 HR | [5 empty] | 68.251 | [19 empty] | 1638 | [5 empty] | 1638
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 24.00 HR | [5 empty] | 78 | [19 empty] | 1872 | [5 empty] | 1872
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 24.00 HR | [5 empty] | 81.5 | [19 empty] | 1956 | [5 empty] | 1956
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 77.06 | [11 empty] | 2416 | [13 empty] | 2416
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 48.00 MH | [5 empty] | 53.88 | [11 empty] | 3408 | [13 empty] | 3408
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 74.56 | [11 empty] | 2339 | [13 empty] | 2339
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 24.00 MH | [5 empty] | 74.56 | [11 empty] | 2339 | [13 empty] | 2339
$15,967.19 120.0000 MH/LS | [22 empty] | 120.00 MH | [5 empty] | [ 8816 ] | [11 empty] | 10501 | [7 empty] | 5466 | [5 empty] | 15967
659.03 ADDITIVE TEMP WATER MAIN MATERIAL Quan: 1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2TEMPWATERMADDITIVE TEMP @110.2 1.00 1.00 LS 4,000.000 4,410 4,410
=====> Item Totals: 659 - TEMPORARY WATER MAINS AND SERVICES ADDIT $31,654.76 216.0000 MH/LS 216.00 MH [ 16209.57 ] 19,298 4,410 7,946 31,655 31,654.760 1 LS 19,298.32 4,410.00 7,946.44 31,654.76
BID ITEM | [5 empty] | = |  | 660 | [5 empty] | CLIENT# = | [8 empty] | 659 | [5 empty] | Land Item SCHEDULE: 1 100
Description = | [5 empty] | BEDDING, WATER MAIN, CL B, 12 IN PIPE | [22 empty] | Unit = LF Takeoff Quan: 1,133.000 Engr Quan: 1,133.000
659.01 | [5 empty] | BEDDING, WATER MAIN, CL B, 12 IN PIPE | [22 empty] | Quan: 1,133.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 800.00 TON | [5 empty] | 29.75 | [10 empty] | 23800 | [12 empty] | 23800
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 604.00 TCY | [5 empty] | 24.5 | [19 empty] | 14798 |  |  |  | 14798
38598 | [28 empty] | [ ] | [10 empty] | 23800 | [8 empty] | 14798 |  |  |  | 38598
=====> Item Totals: 660 - BEDDING, WATER MAIN, CL B, 12 IN PIPE
38598 | [19 empty] | [ ] | [19 empty] | 23800 | [8 empty] | 14798 |  |  |  | 38598
34.067 | [5 empty] | 1133 LF | [33 empty] | 21.01 | [8 empty] | 13.06 |  |  |  | 34.07
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource Pcs | [25 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 661 CLIENT# = 660 Land Item SCHEDULE: 1 100 Description = BLOCKING, CEMENT CONCRETE Unit = CY Takeoff Quan: 9.000 Engr Quan: 9.000
660.01 | [5 empty] | BLOCKING, CEMENT CONCRETE | [24 empty] | Quan: |  |  | 9.00 CY | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [12 empty] | 8 | [11 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2CR040 | [5 empty] | 4000LB READY MIX | [12 empty] | 1.00 9.00 CY | [9 empty] | 121.150 1,090 1,090
8EX135A | [5 empty] | 135 Excavator W/Attach | [12 empty] | 1.00 8.00 HR | [9 empty] | 68.251 | [15 empty] | 546 | [11 empty] | 546
8EX200 | [5 empty] | 200 Excavator | [12 empty] | 1.00 8.00 HR | [9 empty] | 78 | [15 empty] | 624 | [11 empty] | 624
8LO950 | [5 empty] | 950 Loader | [12 empty] | 1.00 8.00 HR | [9 empty] | 81.5 | [15 empty] | 652 | [11 empty] | 652
FOCI | [5 empty] | Civil Forman | [12 empty] | 1.00 8.00 MH | [9 empty] | 77.06 | [12 empty] | 805 | [14 empty] | 805
LAP | [5 empty] | Labor Underground Water | [12 empty] | 2.00 16.00 MH | [9 empty] | 53.88 | [12 empty] | 1136 | [14 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [12 empty] | 1.00 8.00 MH | [9 empty] | 74.56 | [12 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader | [12 empty] | 1.00 8.00 MH | [9 empty] | 74.56 | [12 empty] | 780 | [14 empty] | 780
$6,412.75 4.4444 MH/CY 40.00 MH | [28 empty] | [ 326.52 ] | [12 empty] | 3500 |  |  | 1090 | [7 empty] | 1822 |  |  |  | 6413
=====> Item Totals: 661 - BLOCKING, CEMENT CONCRETE
6412.75 | [5 empty] | 4.4444 MH/CY | [12 empty] | 40.00 MH | [9 empty] | [ 326.52 ] | [10 empty] | 3500 |  |  |  |  | 1090 | [7 empty] | 1822 |  |  |  | 6413
712.528 | [5 empty] | 9 CY | [33 empty] | 388.93 |  |  |  |  | 121.15 | [7 empty] | 202.44 |  |  |  | 712.53
BID ITEM = 662 CLIENT# = 661 Land Item SCHEDULE: 1 100
Description = | [5 empty] | STATION, ELECTROLYSIS TEST | [24 empty] | Unit = EA Takeoff Quan: 3.000 Engr Quan: 3.000
661.01 | [5 empty] | STATION, ELECTROLYSIS TEST | [24 empty] | Quan: 3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 6 |  | CH Prod: 6.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2STELTEST | [5 empty] | STATION ELECTROLOSI 1.00 | [18 empty] | 3.00 EA | [5 empty] | 1,483.620 4,451 4,451
3CERTTEST | [5 empty] | CERTIFIED TESTER | [13 empty] | 1 |  |  |  |  | 3.00 EA |  |  |  | 3897 | [15 empty] | 11691 | [11 empty] | 11691
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  |  |  | 6.00 HR |  |  |  | 68.251 | [23 empty] | 409 |  |  |  | 409
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  |  |  | 6.00 HR |  |  |  | 78 | [23 empty] | 468 |  |  |  | 468
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  |  |  | 6.00 HR |  |  |  | 81.5 | [23 empty] | 489 |  |  |  | 489
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  |  |  | 6.00 MH |  |  |  | 77.06 | [10 empty] | 604 | [16 empty] | 604
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  |  |  | 12.00 MH |  |  |  | 53.88 | [10 empty] | 852 | [16 empty] | 852
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  |  |  | 6.00 MH |  |  |  | 74.56 | [10 empty] | 585 | [16 empty] | 585
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  |  |  | 6.00 MH |  |  |  | 74.56 | [10 empty] | 585 | [16 empty] | 585
$20,133.65 10.0000 MH/EA 30.00 MH | [28 empty] | [ 734.673 ] | [10 empty] | 2625 |  |  |  |  | 4451 |  |  |  | 11691 |  |  |  | 1366 |  |  |  | 20134
=====> Item Totals: 662 - STATION, ELECTROLYSIS TEST $20,133.65 10.0000 MH/EA 30.00 MH [ 734.673 ] 2,625 4,451 11,691 1,366 20,134 6,711.217 3 EA 875.10 1,483.62 3,897.00 455.50 6,711.22
BID ITEM = 663 CLIENT# = 662 Land Item SCHEDULE: 1 100 Description = SACRIFICIAL ANODE BONDED TO PIPE Unit = EA Takeoff Quan: 64.000 Engr Quan: 64.000
662.01 | [5 empty] | SACRIFICIAL ANODE BONDED TO PIPE | [24 empty] | Quan: |  |  | 64.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [16 empty] | 8 | [7 empty] | CH |  |  | Prod: | [7 empty] | 8.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2ANOD | [5 empty] | ANODES | [13 empty] | 1 |  |  | 64.00 EA 271.680 17,388 17,388
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 8.00 HR 68.251 | [29 empty] | 546 |  |  |  | 546
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 8.00 HR 78.000 | [29 empty] | 624 |  |  |  | 624
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 8.00 HR 81.500 | [29 empty] | 652 |  |  |  | 652
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 8.00 MH 77.060 | [18 empty] | 805 | [14 empty] | 805
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 16.00 MH 53.880 | [18 empty] | 1136 | [14 empty] | 1136
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 8.00 MH 74.560 | [18 empty] | 780 | [14 empty] | 780
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 8.00 MH 74.560 | [18 empty] | 780 | [14 empty] | 780
Activity Desc | [16 empty] | Quantity | [9 empty] | Unit | [7 empty] | Perm Constr | [14 empty] | Equip Sub-
Resource Pcs | [22 empty] | Unit |  |  |  | Cost | [7 empty] | Labor Material Matl/Exp | [14 empty] | Ment Contract |  |  |  |  | Total
BID ITEM = 663 CLIENT# = 662 Land Item SCHEDULE: 1 100 Description = SACRIFICIAL ANODE BONDED TO PIPE Unit = EA Takeoff Quan: 64.000 Engr Quan: 64.000 $22,709.92 0.6250 MH/EA 40.00 MH [ 45.917 ] 3,500 17,388 1,822 22,710
=====> Item Totals: 663 - SACRIFICIAL ANODE BONDED TO PIPE $22,709.92 0.6250 MH/EA 354.843 64 EA
40.00 MH | [30 empty] | [ 45.917 ] | [8 empty] | 3500 |  |  |  |  | 17388 | [7 empty] | 1822 |  |  |  | 22710
[40 empty] | 54.69 |  |  |  |  | 271.68 | [7 empty] | 28.47 |  |  |  | 354.84
BID ITEM = 664 CLIENT# = 663 Land Item SCHEDULE: 1 100 Description = SUPPORT SPU WITH CUT, CAP, AND CONNECT Unit = EA Takeoff Quan: 9.000 Engr Quan: 9.000
663.01 SUPPORT SPU WITH CUT, CAP, AND CONNECT Quan: 9.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [13 empty] | 72 | [10 empty] | CH | Prod: | [7 empty] | 72.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
2AGS07 | [5 empty] | SEATTLE TYPE 7 | [13 empty] | 1 |  |  | 40.00 TON | [7 empty] | 29.75 | [13 empty] | 1190 | [9 empty] | 1190
2AGS17 | [5 empty] | SEATTLE TYPE 17 | [13 empty] | 1 |  |  | 90.00 TON | [7 empty] | 25.75 | [13 empty] | 2318 | [9 empty] | 2318
2BI663PIPE | [5 empty] | BID ITEM 663 P@110.25 | [13 empty] | 1 |  |  | 1.00 LS | [7 empty] | 15802 | [13 empty] | 17422 | [9 empty] | 17422
3DEDU02D | [5 empty] | Dirt Trucking and Dump | [13 empty] | 1 |  |  | 90.00 TCY | [7 empty] | 24.5 | [17 empty] | 2205 | [5 empty] | 2205
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 72.00 HR | [7 empty] | 51.051 | [21 empty] | 3676 |  | 3676
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 72.00 HR | [7 empty] | 52.3 | [21 empty] | 3766 |  | 3766
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 77.06 | [8 empty] | 7247 | [14 empty] | 7247
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 53.88 | [8 empty] | 5112 | [14 empty] | 5112
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 74.56 | [8 empty] | 7016 | [14 empty] | 7016
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 72.00 MH | [7 empty] | 74.56 | [8 empty] | 7016 | [14 empty] | 7016
56966.95 | [5 empty] | 32.0000 MH/EA | [13 empty] | 288.00 MH | [10 empty] | [ 2464.528 ] | [8 empty] | 26391 |  |  |  |  | 20929 |  |  |  | 2205 |  |  |  | 7441 |  | 56967
=====> Item Totals: 664 - SUPPORT SPU WITH CUT, CAP, AND CONNECT $56,966.95 32.0000 MH/EA 288.00 MH [ 2464.528 ] 26,391 20,929 2,205 7,441 56,967 6,329.661 9 EA 2,932.39 2,325.47 245.00 826.81 6,329.66
BID ITEM | [5 empty] | = |  | 665 | [6 empty] | CLIENT# = | [7 empty] | 664 | [5 empty] | Land Item |  |  |  |  | SCHEDULE: | [10 empty] | 1 100
Description = | [5 empty] | PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL | [22 empty] | Unit = |  |  |  |  | LF Takeoff Quan: 1,133.000 Engr Quan: 1,133.000
664.01 | [5 empty] | PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL | [22 empty] | Quan: |  |  |  |  | 1,133.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM 2BI664PIPE | [5 empty] | Unerground Utilities BID ITEM 664 PIPE | [8 empty] | 6 Man 1.00 | [7 empty] | 1 1.00 LS | [5 empty] | 20.00 CH Prod: 120.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00 89,317.460 89,317 89,317
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 120.00 HR | [5 empty] | 68.251 | [23 empty] | 8190 |  |  |  | 8190
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 120.00 HR | [5 empty] | 78 | [23 empty] | 9360 |  |  |  | 9360
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 120.00 HR | [5 empty] | 81.5 | [23 empty] | 9780 |  |  |  | 9780
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 120.00 MH | [5 empty] | 77.06 | [10 empty] | 12078 | [16 empty] | 12078
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 240.00 MH | [5 empty] | 53.88 | [10 empty] | 17040 | [16 empty] | 17040
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 120.00 MH | [5 empty] | 74.56 | [10 empty] | 11694 | [16 empty] | 11694
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 120.00 MH | [5 empty] | 74.56 | [10 empty] | 11694 | [16 empty] | 11694
169153.49 | [5 empty] | 0.5295 MH/LF | [16 empty] | 600.00 MH | [5 empty] | [ 38.906 ] | [10 empty] | 52506 |  |  |  |  | 89317 | [7 empty] | 27330 |  |  |  | 169153
664.02 | [5 empty] | FLUSHING AND TESTING ADDITIVE | [24 empty] | Quan: |  |  | 2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [22 empty] | 32 |  | CH |  |  | Prod: 32.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 68.251 | [15 empty] | 2184 | [11 empty] | 2184
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 78 | [15 empty] | 2496 | [11 empty] | 2496
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 32.00 HR | [5 empty] | 81.5 | [15 empty] | 2608 | [11 empty] | 2608
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 77.06 | [10 empty] | 3221 | [16 empty] | 3221
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 64.00 MH | [5 empty] | 53.88 | [10 empty] | 4544 | [16 empty] | 4544
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [10 empty] | 3118 | [16 empty] | 3118
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 32.00 MH | [5 empty] | 74.56 | [10 empty] | 3118 | [16 empty] | 3118
| Activity Desc Resource Pcs | [21 empty] | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  | Total
| BID ITEM = 665 CLIENT# = 664 Land Item SCHEDULE: 1 10 Description = PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL Unit = LF Takeoff Quan: | [48 empty] | 0 1,133.000 |  |  | Engr Quan: |  |  | 1133
| $21,289.60 80.0000 MH/EA 160.00 MH [ 5877.34 ] 14,002 | [51 empty] | 7288 |  |  | 21290
=====> Item Totals: 665 - PIPE, WM, D.I. CL 53 MIN, 12 IN, RJ, POL
| $190,443.09 0.6707 MH/LF 760.00 MH | [29 empty] | [ 49.28 ] | [8 empty] | 66507 |  |  |  |  | 89317 |  |  |  |  | 34618 | [5 empty] | 190443
| 168.087 1133 LF | [38 empty] | 58.7 |  |  |  |  | 78.83 |  |  |  |  | 30.55 | [5 empty] | 168.09
BID ITEM = 666 CLIENT# = 665 Land Item SCHEDULE: 1 100 Description = DAILY BLOCK, CEMENT CONCRETE, PRECAST Unit = EA Takeoff Quan: 2.000 Engr Quan: 2.000
665.01 DAILY BLOCK, CEMENT CONCRETE, PRECAST Quan: | [33 empty] | 2.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM Unerground Utilities 6 Man 4.50 CH | [33 empty] | Prod: | [7 empty] | 4.5000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2AGS02 | [5 empty] | SEATTLE TYPE 2 | [13 empty] | 1 |  |  | 20.00 TON | [10 empty] | 29.75 | [10 empty] | 595 | [11 empty] | 595
2CPSDAILY | [5 empty] | DAILY BLOCK | [13 empty] | 1 |  |  | 2.00 EA | [10 empty] | 750 | [10 empty] | 1500 | [11 empty] | 1500
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.50 HR | [10 empty] | 68.251 | [18 empty] | 307 |  |  |  | 307
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.50 HR | [10 empty] | 78 | [18 empty] | 351 |  |  |  | 351
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.50 HR | [10 empty] | 81.5 | [18 empty] | 367 |  |  |  | 367
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.50 MH | [10 empty] | 77.06 | [7 empty] | 453 | [14 empty] | 453
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 9.00 MH | [10 empty] | 53.88 | [7 empty] | 639 | [14 empty] | 639
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.50 MH | [10 empty] | 74.56 | [7 empty] | 439 | [14 empty] | 439
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.50 MH | [10 empty] | 74.56 | [7 empty] | 439 | [14 empty] | 439
$5,088.84 11.2500 MH/EA 22.50 MH | [33 empty] | [ 826.5 ] | [7 empty] | 1969 |  |  | 2095 | [7 empty] | 1025 |  |  |  | 5089
=====> Item Totals: 666 - DAILY BLOCK, CEMENT CONCRETE, PRECAST $5,088.84 11.2500 MH/EA 22.50 MH [ 826.5 ] 1,969 2,095 1,025 5,089 2,544.420 2 EA 984.50 1,047.50 512.43 2,544.42
BID ITEM = 667 CLIENT# = 666 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 6 IN Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
666.01 | [5 empty] | VALVE, GATE, 6 IN | [24 empty] | Quan: |  |  | 1.00 EA | [7 empty] | Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNM | [5 empty] | Unerground Utilities 6 Man | [10 empty] | 1 | [13 empty] | CH |  |  | Prod: | [7 empty] | 1.0000 CH Lab Pcs: 5.00 Eqp Pcs: 3.00
2BI666PIPE | [5 empty] | BID ITEM 666 PIPE | [10 empty] | 1 | [5 empty] | 1.00 LS | [5 empty] | 2,944.660 2,945 2,945
8EX135A | [5 empty] | 135 Excavator W/Attach | [10 empty] | 1 | [5 empty] | 1.00 HR | [5 empty] | 68.251 | [15 empty] | 68 | [11 empty] | 68
8EX200 | [5 empty] | 200 Excavator | [10 empty] | 1 | [5 empty] | 1.00 HR | [5 empty] | 78 | [15 empty] | 78 | [11 empty] | 78
8LO950 | [5 empty] | 950 Loader | [10 empty] | 1 | [5 empty] | 1.00 HR | [5 empty] | 81.5 | [15 empty] | 81 | [11 empty] | 81
FOCI | [5 empty] | Civil Forman | [10 empty] | 1 | [5 empty] | 1.00 MH | [5 empty] | 77.06 | [12 empty] | 101 | [14 empty] | 101
LAP | [5 empty] | Labor Underground Water | [10 empty] | 2 | [5 empty] | 2.00 MH | [5 empty] | 53.88 | [12 empty] | 142 | [14 empty] | 142
OPE | [5 empty] | Operator - Excavator | [10 empty] | 1 | [5 empty] | 1.00 MH | [5 empty] | 74.56 | [12 empty] | 97 | [14 empty] | 97
OPL | [5 empty] | Operator - Loader | [10 empty] | 1 | [5 empty] | 1.00 MH | [5 empty] | 74.56 | [12 empty] | 97 | [14 empty] | 97
$3,609.95 5.0000 MH/EA 5.00 MH | [28 empty] | [ 367.35 ] | [12 empty] | 438 |  |  | 2945 | [7 empty] | 228 |  |  |  | 3610
=====> Item Totals: $3,609.95 | [9 empty] | 667 5.0000 MH/EA | [6 empty] | - VALVE, GATE, 6 IN 5.00 MH | [11 empty] | [ 367.35 ] | [8 empty] | 438 | [6 empty] | 2945 | [7 empty] | 228 |  |  |  | 3610
3,609.950 1 EA 437.56 2,944.66 227.73 3,609.95
BID ITEM = 668 CLIENT# = 667 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 12 IN Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
| Activity Desc | [21 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 668 CLIENT# = 667 Land Item SCHEDULE: 1 100 Description = VALVE, GATE, 12 IN Unit = EA Takeoff Quan: 4.000 Engr Quan: 4.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI667PIPE BID ITEM 667 PIPE 1.00 1.00 LS 14,955.000 14,955 | [56 empty] | 14955
8EX135A | [5 empty] | 135 Excavator W/Attach | [11 empty] | 1 |  |  |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [11 empty] | 1 |  |  |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [11 empty] | 1 |  |  |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [11 empty] | 1 |  |  |  |  | 4.00 MH | [7 empty] | 77.06 | [6 empty] | 403 | [16 empty] | 403
LAP | [5 empty] | Labor Underground Water | [11 empty] | 2 |  |  |  |  | 8.00 MH | [7 empty] | 53.88 | [6 empty] | 568 | [16 empty] | 568
OPE | [5 empty] | Operator - Excavator | [11 empty] | 1 |  |  |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
OPL | [5 empty] | Operator - Loader | [11 empty] | 1 |  |  |  |  | 4.00 MH | [7 empty] | 74.56 | [6 empty] | 390 | [16 empty] | 390
$17,616.19 5.0000 MH/EA 20.00 MH | [30 empty] | [ 367.33 ] | [6 empty] | 1750 | [6 empty] | 14955 |  |  |  | 911 | [5 empty] | 17616
=====> Item Totals: $17,616.19 | [9 empty] | 668 5.0000 MH/EA | [7 empty] | - VALVE, GATE, 12 IN 20.00 MH | [12 empty] | [ 367.33 ] | [6 empty] | 1750 | [6 empty] | 14955 |  |  |  | 911 | [5 empty] | 17616
4,404.048 4 EA 437.55 3,738.75 227.75 4,404.05
BID ITEM = 669 CLIENT# = 668 Land Item SCHEDULE: 1 100 Description = VALVE BOX, CAST IRON Unit = EA Takeoff Quan: 5.000 Engr Quan: 5.000
UNM Unerground Utilities 6 Man 2.00 CH Prod: 2.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI668PIPE BID ITEM 668 PIPE 1.00 1.00 LS 1,486.650 1,487 | [56 empty] | 1487
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 68.251 | [17 empty] | 136 | [5 empty] | 136
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 78 | [17 empty] | 156 | [5 empty] | 156
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 2.00 HR | [7 empty] | 81.5 | [17 empty] | 163 | [5 empty] | 163
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 77.06 | [8 empty] | 201 | [14 empty] | 201
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 4.00 MH | [7 empty] | 53.88 | [8 empty] | 284 | [14 empty] | 284
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [8 empty] | 195 | [14 empty] | 195
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 2.00 MH | [7 empty] | 74.56 | [8 empty] | 195 | [14 empty] | 195
$2,817.23 2.0000 MH/EA 10.00 MH | [30 empty] | [ 146.932 ] | [8 empty] | 875 |  |  |  |  | 1487 |  |  |  | 455 | [5 empty] | 2817
=====> Item Totals: 669 - VALVE BOX, CAST IRON
2817.23 | [5 empty] | 2.0000 MH/EA | [13 empty] | 10.00 MH | [10 empty] | [ 146.932 ] | [8 empty] | 875 |  |  |  |  | 1487 |  |  |  | 455 | [5 empty] | 2817
563.446 | [5 empty] | 5 EA | [33 empty] | 175.02 |  |  |  |  | 297.33 |  |  |  | 91.1 | [5 empty] | 563.45
BID ITEM = 670 CLIENT# = 669 Land Item SCHEDULE: 1 100 Description = HYDRANT, 6 IN CONN, TYPE 311 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000
UNM Unerground Utilities 6 Man 4.00 CH Prod: 4.0000 CH | [48 empty] | Lab Pcs: |  |  |  | 5 |  | Eqp Pcs: |  | 3
2BI669PIPE BID ITEM 669 PIPE 1.00 1.00 LS 7,567.640 7,568 | [56 empty] | 7568
8EX135A | [5 empty] | 135 Excavator W/Attach | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 68.251 | [17 empty] | 273 | [5 empty] | 273
8EX200 | [5 empty] | 200 Excavator | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 78 | [17 empty] | 312 | [5 empty] | 312
8LO950 | [5 empty] | 950 Loader | [13 empty] | 1 |  |  | 4.00 HR | [7 empty] | 81.5 | [17 empty] | 326 | [5 empty] | 326
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 77.06 | [8 empty] | 403 | [14 empty] | 403
LAP | [5 empty] | Labor Underground Water | [13 empty] | 2 |  |  | 8.00 MH | [7 empty] | 53.88 | [8 empty] | 568 | [14 empty] | 568
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
OPL | [5 empty] | Operator - Loader | [13 empty] | 1 |  |  | 4.00 MH | [7 empty] | 74.56 | [8 empty] | 390 | [14 empty] | 390
$10,228.83 20.0000 MH/EA 20.00 MH | [30 empty] | [ 1469.32 ] | [8 empty] | 1750 |  |  |  |  | 7568 |  |  |  | 911 | [5 empty] | 10229
| Activity |  |  |  |  | Desc | [16 empty] | Quantity | [7 empty] | Unit | [8 empty] | Perm Constr | [12 empty] | Equip Sub-
| Resource | [18 empty] | Pcs | [6 empty] | Unit |  |  |  | Cost | [8 empty] | Labor Material Matl/Exp | [12 empty] | Ment Contract |  |  |  | Total
BID ITEM = 670 CLIENT# = 669 Land Item SCHEDULE: 1 100 Description = HYDRANT, 6 IN CONN, TYPE 311 Unit = EA Takeoff Quan: 1.000 Engr Quan: 1.000 =====> Item Totals: 670 - HYDRANT, 6 IN CONN, TYPE 311 $10,228.83 20.0000 MH/EA 20.00 MH [ 1469.32 ] 1,750 7,568 911 10,229 10,228.830 1 EA 1,750.19 7,567.64 911.00 10,228.83
BID ITEM = 671 CLIENT# = 670 Land Item SCHEDULE: 1 100 Description = SUPPORT SPU WITH SERVICE TRANSFER OR REN Unit = EA Takeoff Quan: 21.000 Engr Quan: 21.000
670.01 SUPPORT SPU WITH SERVICE TRANSFER OR R Quan: 21.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
UNS | [5 empty] | Underground Utilities 4 Man | [22 empty] | 55 |  | CH |  |  | Prod: | [5 empty] | 55.0000 CH | [8 empty] | Lab Pcs: |  |  |  | 4 |  | Eqp Pcs: |  | 2
8BA310A | [5 empty] | 418 Backhoe W/Attachme | [13 empty] | 1 |  |  | 55.00 HR | [10 empty] | 51.051 | [18 empty] | 2808 |  |  |  | 2808
8EX100 | [5 empty] | 100 Excavator | [13 empty] | 1 |  |  | 55.00 HR | [10 empty] | 52.3 | [18 empty] | 2876 |  |  |  | 2876
FOCI | [5 empty] | Civil Forman | [13 empty] | 1 |  |  | 55.00 MH | [10 empty] | 77.06 | [5 empty] | 5536 | [16 empty] | 5536
LAP | [5 empty] | Labor Underground Water | [13 empty] | 1 |  |  | 55.00 MH | [10 empty] | 53.88 | [5 empty] | 3905 | [16 empty] | 3905
OPB | [5 empty] | Operator - Backhoe | [13 empty] | 1 |  |  | 55.00 MH | [10 empty] | 74.56 | [5 empty] | 5360 | [16 empty] | 5360
OPE | [5 empty] | Operator - Excavator | [13 empty] | 1 |  |  | 55.00 MH | [10 empty] | 74.56 | [5 empty] | 5360 | [16 empty] | 5360
25844.45 | [5 empty] | 10.4761 MH/EA | [16 empty] | 220.00 MH | [10 empty] | [ 806.84 ] | [5 empty] | 20160 | [12 empty] | 5684 |  |  |  | 25844
=====> Item Totals: 671 - SUPPORT SPU WITH SERVICE TRANSFER OR REN
25844.45 | [5 empty] | 10.4761 MH/EA | [13 empty] | 220.00 MH | [8 empty] | [ 806.84 ] | [10 empty] | 20160 | [8 empty] | 5684 | [5 empty] | 25844
1230.688 | [5 empty] | 21 EA | [33 empty] | 960.01 | [8 empty] | 270.68 | [5 empty] | 1230.69
$62,286,298.89 *** Report Totals *** 180,159.77 MH 15,857,899 11,779,587 9,592,374 2,511,818 22,544,620 62,286,299
>>> indicates Non Additive Activity ------Report Notes:------ The estimate was prepared with TAKEOFF Quantities. This report shows TAKEOFF Quantities with the resources.
Bid Date: Owner: Engineering Firm: Estimator-In-Charge:
JOB NOTES Estimate created on: 05/21/2021 by User#: 0 - Source estimate used: C:\HEAVYBID\EST\ESTMAST
* on units of MH indicate average labor unit cost was used rather than base rate. [ ] in the Unit Cost Column = Labor Unit Cost Without Labor Burdens In equipment resources, rent % and EOE % not = 100% are represented as XXX%YYY where XXX=Rent% and YYY=EOE% ------Calendar Codes------
410 |  |  |  | 40 Hour Week - (4@10)
508 |  |  |  | 40 Hour Week - (5@8)
509 |  |  |  | 45 Hour Week - (5@9)
510 |  |  |  | 50 Hour Week - (5@10) (Default Calendar)
512 |  |  |  | 60 Hour Week(5@12)
518 |  |  |  | 58 Hour Week(5@10+Sat@8)
609 |  |  |  | 54 Hour Week(6@9)
610 |  |  |  | 60 Hour Week - (6@10)
612 |  |  |  | 72 Hour Week - (6@12)
709 |  |  |  | 63 Hour Week - (7@9)
710 |  |  |  | 70 Hour Week - (7@10)
712 |  |  |  | 84 Hour Week - (7@12)
Activity Resource | [5 empty] | Desc | [13 empty] | Pcs |  |  | Quantity |  |  |  | Unit |  |  |  | Unit Cost | [8 empty] | Perm Constr Labor Material Matl/Exp | [12 empty] | Equip Sub- Ment Contract |  |  |  | Total
BID ITEM Description = | [5 empty] | = |  | 671 CLIENT# = 670 Land Item SCHEDULE: 1 100 SUPPORT SPU WITH SERVICE TRANSFER OR REN Unit = EA Takeoff Quan: | [42 empty] | 21 |  | Engr Quan: |  |  |  | 21
S08 S10 S12 X08 X10 X12 Z08 Z10 Z12 | [7 empty] | Saturday Only - 8 Hour shift Saturday Only - 10 Hr Shift Saturday Only - 12 Hr Shift Sunday Only - 8 Hr Shift Sunday Only - 10 Hr Shift Sunday Only - 12 Hr Shift Sat & Sun Only - 8 Hr shifts Sat & Sun Only - 10Hr Shifts Sat &Sun Only - 12 Hr Shifts
001.01
CONSTRUCTION SURVEYING
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 LS
0 EA
007.02
TRAFFIC CONTROL MATERIAL
Quan:
1.00 LS
1.00 LS
1,568.00 SHIF Hrs/Shft: 10.00 Cal: 710 WC: WAAVG
039.01
REMOVE LUMINAIRE, ROADWAY
Quan: 77.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
045.01
REMOVE POLE, STREET LIGHT
Quan: 31.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
046.01
REMOVE POLE, STEEL MAST ARM
Quan: 19.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
047.01
REMOVE POLE, PEDESTRIAN LIGHT
Quan:
2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
053.01
REMOVE SIGN, ILLUMINATED SIGN
Quan:
5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
056.01
REMOVE SIGN, OVERHEAD
Quan: 12.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
53.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
063.01
REMOVE VEHICLE SIGNAL HEAD
Quan: 200.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
072.01
ABANDON CATCH BASIN
Quan:
2.00 EA Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
081.01
REMOVE, STORE AND REINSTALL LITTER REC Quan: 14.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
092.01
ABANDON MONITORING WELL
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
110.01
SURFACE PREP, PRELEVEL
Quan: 49.00 TN Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
111.01
SURFACE PREP, PLANE BITUMINOUS PAVEME Quan: 14,240.00 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
120.01
AREAWAY PROTECTION ZONE 1
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
121.01
AREAWAY PROTECTION ZONE 2
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
146.01
FLOW CONTROL DEVICE ASSEMBLY
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
151.01
FLOW SPLITTER DEVICE ASSEMBLY
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
162.01
PIPE, PS or PSS, PVC, D3034 SDR 35, 8 IN
Quan: 12.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
165.01
CASING PIPE, PVC C905 DR 14, 18 IN
Quan: 18.00 LF Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
167.01
TEE, PVC, 10 IN
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
182.01
EROSION CONTROL, HYDRO-SEEDING
Quan: 5,510.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
183.01
TREE, DECIDUOUS, 1-1/2 IN TO 1-3/4 IN CA
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
184.01
TREE, DECIDUOUS, 1-3/4 IN TO 2 IN CAL
Quan: 85.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
185.01
SHRUB, DECIDUOUS, 5 GAL
Quan: 450.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
201.01
FLEXIBLE DELINEATOR POST, 28"
Quan: 110.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
204.01
PLASTIC CURB WITH POST
Quan: 141.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
207.01
DETECTABLE WARNING PLATE RETROFIT
Quan: 13.00 SF Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
0 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
218.01
SIGN, TRAFFIC
Quan: 446.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
225.01
POST, TRAFFIC SIGN
Quan: 223.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
233.01
PAVEMENT MARKING, THERMOPLASTIC, 8 IN Quan: 44,997.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
246.01
LUMINAIRE, LED, COLLECTOR ARTERIAL
Quan: 65.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
247.01
LUMINAIRE, LED, PRINCIPAL ARTERIAL
Quan: 31.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
291.01
BICYCLE PUSHBUTTON ASSEMBLY
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
292.01
APS PEDESTRIAN PUSHBUTTON ASSEMBLY
Quan: 242.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
294.01
DETECTOR LOOP, 6 FT DIA.
Quan: 184.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
295.01
DETECTOR LOOP, PREFORMED, 6 FT DIA
Quan: 135.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
299.01
INTERCONNECT CABLE, AERIAL
Quan: 235.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
300.01
INTERCONNECT CABLE, UNDERGROUND
Quan: 175.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
303.01
RELOCATE PEDESTRIAN SIGNAL HEAD
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
304.01
RELOCATE CCTV CAMERA
Quan:
2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
307.01
VIDEO DETECTION CAMERA
Quan:
4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
310.01
WIRELESS SENSOR ACCESS POINT
Quan: 38.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
311.01
WIRELESS SENSOR REPEATER
Quan: 25.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
321.01
SERVICE WIRING (MADISON-15TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
322.01
SERVICE WIRING (MADISON-16TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
323.01
SERVICE WIRING (MADISON-17TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
324.01
SERVICE WIRING (MADISON-18TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
325.01
SERVICE WIRING (MADISON-19TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
328.01
SERVICE WIRING (MADISON-JOHN)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
329.01
SERVICE WIRING (MADISON-MLK WAY)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
330.01
SERVICE WIRING (MLK WAY-HARRISON)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
331.01
SERVICE WIRING (UNION-19TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
333.01
SIGNAL WIRING (SPRING-1ST)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
334.01
SIGNAL WIRING (SPRING-2ND)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
335.01
SIGNAL WIRING (SPRING-3RD)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
336,01
SIGNAL WIRING (SPRING-4TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
337.01
SIGNAL WIRING (SPRING-5TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
339.01
SIGNAL WIRING (SPRING-7TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
340.01
SIGNAL WIRING (SPRING-8TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
341.01
SIGNAL WIRING (SPRING-9TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
342.01
SIGNAL WIRING (MADISON-1ST)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
343.01
SIGNAL WIRING (MADISON-2ND)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
345.01
SIGNAL WIRING (MADISON-4TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
346.01
SIGNAL WIRING (MADISON-6TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
347.01
SIGNAL WIRING (MADISON-7TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
348.01
SIGNAL WIRING (MADISON-8TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
349.01
SIGNAL WIRING (MADISON-9TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
351.01
SIGNAL WIRING (MADISON-BOREN)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
352.01
SIGNAL WIRING (MADISON-MINOR)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
253.01
SIGNAL WIRING (MADISON-SUMMIT)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
154.01
SIGNAL WIRING (MADISON-BOYLSTON)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
355.01
SIGNAL WIRING (MADISON-BROADWAY)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
357.01
SIGNAL WIRING (MADISON-12TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
358.01
SIGNAL WIRING (MADISON-13TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
359.01
SIGNAL WIRING (MADISON-14TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
360.01
SIGNAL WIRING (MADISON-15TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
361.01
SIGNAL WIRING (MADISON-16TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
363.01
SIGNAL WIRING (MADISON-18TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
364.01
SIGNAL WIRING (MADISON-19TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
365.01
SIGNAL WIRING (MADISON-20TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
366.01
SIGNAL WIRING (MADISON-E DENNY WAY)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
367.01
SIGNAL WIRING (MADISON-23RD)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
369.01
SIGNAL WIRING (MADISON-MLK WAY)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
370.01
SIGNAL WIRING (MLK WAY-HARRISON)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
371.01
SIGNAL WIRING (UNION-19TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
372.01
SIGNAL WIRING (MADISON-10TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
373.01
TEMPORARY SIGNAL (SPRING-1ST)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
375.01
TEMPORARY SIGNAL (SPRING-5TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
376.01
TEMPORARY SIGNAL (SPRING-7TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
377.01
TEMPORARY SIGNAL (MADISON-1ST)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
378.01
TEMPORARY SIGNAL (MADISON-3RD)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
379.01
TEMPORARY SIGNAL (MADISON-6TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
381.01
TEMPORARY SIGNAL (MADISON-8TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
382.01
TEMPORARY SIGNAL (MADISON-9TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
383.01
TEMPORARY SIGNAL (MADISON-TERRY)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
384.01
TEMPORARY SIGNAL (MADISON-BOREN)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
385.01
TEMPORARY SIGNAL (MADISON-MINOR)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
393.01
TEMPORARY SIGNAL (MADISON-15TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
394.01
TEMPORARY SIGNAL (MADISON-16TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
395.01
TEMPORARY SIGNAL (MADISON-17TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
396.01
TEMPORARY SIGNAL (MADISON-19TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
397.01
TEMPORARY SIGNAL (MADISON-20TH)
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
411.01
PEDESTAL, ALUMINUM, 12 FT
Quan: 20.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
412.01
PEDESTAL, ALUMINUM, 14 FT
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
413.01
MAST ARM, 30 FT AND LESS
Quan: 43.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
414.01
MAST ARM, 31 FT TO 40 FT
Quan: 18.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
415.01
MAST ARM, 41 FT TO 50 FT
Quan:
6.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
423.01
FOUNDATION, POLE TYPE X
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
424.01
FOUNDATION, POLE TYPE Z
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
426.01
FOUNDATION, STREET LIGHT POLE
Quan: 20.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
427.01
FOUNDATION, PEDESTAL
Quan: 55.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
443.01
ALADDIN BRACKET ARM ASSEMBLY, 8 FT
Quan:
4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
444.01
BRACKET ARM, 6 FT, STEEL
Quan: 14.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
447.01
BRACKET ARM, 12 FT, STEEL
Quan:
4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
448.01
FOUNDATION, BICYCLE PUSHBUTTON POST Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
449.01
BICYCLE PUSHBUTTON POST
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
450.01
FOUNDATION, POLE, JU/STEEL MAST ARM
Quan: 30.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
451.01
POLE, KCM SA-201X/SA-201X(C)
Quan: 26.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
455.01
FOUNDATION, KCM SA-213D
Quan: 26.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
456.01
FOUNDATION, KCM SA-213F
Quan: 41.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
457.01
FOUNDATION, KCM SA-213H
Quan:
8.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
486.01
LID, HANDHOLE, TYPE 6
Quan:
5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
487.01
LID, HANDHOLE, TYPE 5
Quan:
4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
488.01
CONDUIT ENCASEMENT SYSTEM
Quan: 458.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
489.01
CONDUIT, RGS, 3 IN, AREAWAY
Quan: 20.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
490.01
UTILITY VAULT, FURNISH AND INSTALL
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 SY Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
501.01
TRUNKATED DOME
Quan: 99.00 SF Hrs/Sh
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
504.01
TRUNCATED DOMES
Quan: 74.00 SF Hrs/Sh
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
: 10.00
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
512.01
FURNISH AND INSTALL RAPIDRIDE SHELTER, Quan:
5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
538.01
KCM STATION WIRING, MADISON & E DENNY Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
539.01
KCM STATION WIRING, MADISON & 23RD AVE Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
540.01
KCM STATION WIRING, MADISON & 24TH AVE Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
542.01
KCM STATION WIRING, MADISON & 27TH AVE Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
544.01
YELLOW DETECTABLE GUIDANCE STRIP
Quan: 134.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
546.01
ARTWORK FOUNDATION
Quan:
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
571.01
VALVE, GATE, 8 IN
Quan:
5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
573.01
VALVE, BUTTERFLY, 16 IN
Quan:
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
574.01
VALVE, BUTTERFLY, 20 IN
Quan:
2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
578.01
HYDRANT, 6 IN CONN, TYPE 311
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
588.01
PIPE, SD, D.I., CL 50, 8 IN
Quan: 12.00 LF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
3.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
635.01
PIPE, CB CONN, D.I., CL 50, 8 IN
Quan: 64.00 LF Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
637.01
4 INCH DRAIN PIPE, GIP, SCH 40
Quan:
2.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
643.01
UTILITY CASTING, TYPE 230
Quan:
7.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
1.00 LS Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
649.01
FLEXIBLE POROUS SURFACE TREATMENT
Quan: 2,335.00 SF Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
0 SY Hrs/Shft: 10.00 Cal: 610 WC: WAAVG
0 SY Hrs/Shft: 10.00 Cal: S10 WC: WAAVG
667.01
VALVE, GATE, 12 IN
Quan:
4.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
668.01
VALVE BOX, CAST IRON
Quan:
5.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG
669.01
HYDRANT, 6 IN CONN, TYPE 311
Quan:
1.00 EA Hrs/Shft: 10.00 Cal: 510 WC: WAAVG