TRAINING GUIDE

Identifying Contractor-Caused Delays from Daily Reports

For Use in Concurrent Delay Analysis  |  RapidRide J Line BRT Project

# 1. Purpose

This guide is intended to help staff reviewing daily reports, inspector diaries, and field records identify and classify delays attributable to the Contractor. The goal is to systematically flag contractor-caused delays that may contribute to concurrent delays during periods where owner-caused delays are also being claimed.

# 2. Contract Basis

The following contract provisions define and frame the Contractor’s scheduling and delay obligations:

- Section 1-08.4: The Contractor must diligently pursue the Work to the Physical Completion Date. The Contractor must not voluntarily shut down or slow Work operations without requesting and obtaining prior approval of the Engineer.

- Section 1-08.8(1): The Contractor must show that a claimed delay had a specific impact on the critical path, was the sole cause of such impact (except in concurrent delay), and could not have been avoided by resequencing of the Work or other reasonable alternative.

- Section 1-08.8(2) - Non-Excusable Delays: Delays caused by factors within the Contractor’s control that could have been foreseen or avoided had the Contractor exercised due care, prudence, foresight, or diligence and pursued the Work vigorously and without unauthorized interruption.

# 3. What Is a Contractor-Caused Delay?

A contractor-caused delay is any act, omission, failure, or inefficiency by the Contractor (including its subcontractors, suppliers, and agents) that prevents or slows progress on the Work, and for which the Owner bears no responsibility. These delays are non-excusable, and the Contractor is not entitled to a time extension.

The core test is: Was the delay within the Contractor’s control, and could it have been foreseen or avoided through due care, prudence, foresight, or diligence?

# 4. Categories of Contractor-Caused Delays

The following tables organize the most common types of contractor-caused delays into categories. For each type, the table describes what to look for in daily reports and how to classify the observation.

## 4.1 Resource & Staffing Failures

| RESOURCE & STAFFING FAILURES |  |  |
| --- | --- | --- |
| Delay Type / Indicator | What to Look For in Daily Reports | Classification |
| Insufficient crew size | Crew counts below what is needed for the planned activity. Compare daily crew numbers against schedule activity durations and planned production rates. Eg: “3 laborers on site” when activity requires 5+. | Contractor Delay |
| Key personnel absent | Superintendent, foreman, or specialty trade lead not on site. Look for entries like “waiting for foreman” or “no direction from Jansen superintendent.” | Contractor Delay |
| Late start / early quit | Crew arriving significantly after normal start time or leaving early without justification. Check sign-in times vs. standard work hours. | Contractor Delay |
| Crew standing idle (no owner cause) | Workers on site but not performing productive work. If no owner-caused hold, restriction, or access issue is noted, this is a contractor efficiency issue. | Contractor Delay |

## 4.2 Subcontractor & Supplier Failures

| SUBCONTRACTOR & SUPPLIER FAILURES |  |  |
| --- | --- | --- |
| Delay Type / Indicator | What to Look For in Daily Reports | Classification |
| Subcontractor no-show | Scheduled subcontractor did not mobilize. Entries like “electrical sub not on site” or “waiting on electrical crew.” The general contractor is responsible for managing its subs. | Contractor Delay |
| Material/concrete delivery failure | Planned materials did not arrive or arrived late causing work interruption. Example: concrete truck delayed 1.5 hours causing potential cold joint. Supplier delays are attributable to the Contractor. | Contractor Delay |
| Wrong material delivered | Material arrived but was incorrect specification, size, or type. Requires reorder and impacts scheduled installation. | Contractor Delay |
| Sub performing work out of sequence | Subcontractor working in an area or on an activity not aligned with the current schedule update (unless revised on the schedule to reflect the revised sequencing), causing cascading impacts to other trades. | Contractor Delay |

## 4.3 Quality Deficiencies & Rework

| QUALITY DEFICIENCIES & REWORK |  |  |
| --- | --- | --- |
| Delay Type / Indicator | What to Look For in Daily Reports | Classification |
| Defective work / NCR-related rework | Work rejected by inspector, failed test, or non-conformance report (NCR) issued. Examples: “Jansen removing and replacing curb section,” “rebuilding riser due to being 2” too high,” “regrading subgrade for 4+ hours to correct elevations.” | Contractor Delay |
| Signal head / equipment misalignment (NCR) | SDOT-issued NCR for non-conforming installation. Example: signal heads not aligning with TCP, requiring Transcon to adjust at Jansen’s cost. | Contractor Delay |
| Cold joints in concrete placement | Disruption in concrete pour sequence. Flag as potential NCR even if not yet formally issued. May require panel removal and replacement. | Contractor Delay (Potential) |
| Incomplete work blocking successors | Predecessor activity not finished to the level required for the next trade to begin. Example: operations shut down because Howe intersection section has not passed compaction testing. | Contractor Delay |
| Temporary protection deficiencies | Temp asphalt, sheeting, or barricades not providing adequate pedestrian/traffic protection. Likely requires rework to bring into compliance. | Contractor Delay |

## 4.4 Planning, Coordination & Sequencing Failures

| PLANNING, COORDINATION & SEQUENCING FAILURES |  |  |
| --- | --- | --- |
| Delay Type / Indicator | What to Look For in Daily Reports | Classification |
| Forgotten or missed work | Inspector notes that contractor is returning to perform work that was missed or forgotten. Example: “Trenching for the conduit run that they forgot.” Requires remobilization and disrupts sequence. | Contractor Delay |
| Work out of sequence vs. schedule | Crew working on activities not on the current schedule update or performing work in a different zone/location than planned (unless revised on the schedule to reflect the revised sequencing). | Contractor Delay |
| Diverting resources to non-project scope | Contractor performing work not in the contract scope. Example: “Not the project’s scope but here is a photo.” Question why resources are being diverted. | Contractor Delay |
| Double handling of materials | Loading, moving, and re-loading material unnecessarily. Classify as contractor delay only if the double handling was not anticipated in the baseline schedule and reflects an inefficiency. | Contractor Delay (Conditional) |
| Failure to request timely inspections | Work was ready for inspection but contractor did not provide required notice. | Contractor Delay |
| Late or incomplete submittals | Submittals not provided per the schedule or returned for correction due to incomplete/non-conforming content. | Contractor Delay |

## 4.5 Equipment Failures & Utility Strikes

| EQUIPMENT FAILURES & UTILITY STRIKES |  |  |
| --- | --- | --- |
| Delay Type / Indicator | What to Look For in Daily Reports | Classification |
| Equipment breakdown | Critical equipment non-operational. “Backhoe down; waiting for mechanic.” Unless caused by an unforeseen site condition that falls into an accepted Differing Site Condition (DSC). | Contractor Delay |
| Utility strike on known utility | Contractor strikes a utility that was shown on plans or previously located/marked. Example: “Civil crew has struck known 6” concrete storm drainpipe.” Damage to known utilities is a contractor-caused event. | Contractor Delay |
| Equipment not mobilized | Planned activity requires equipment that has not been brought to the site. | Contractor Delay |

# 5. What Is NOT a Contractor-Caused Delay

It is equally important to correctly exclude events that are not the Contractor’s fault. The following are generally NOT contractor-caused delays:

- Differing Site Conditions (DSCs): Work under accepted DSCs is NOT a contractor-caused delay. Example: water service labeled as ¾” in plans found to be 4” cast iron in the field (DSC 294). A full list of accepted DSCs will be maintained for reference.

- Unforeseen underground conditions: Encountering roots, unmarked utilities, or unexpected existing electrical conduits in a trench that were not shown in the contract documents. Example: large roots encountered at WS-301 requiring vactor truck. For Utilities unless they are classified as Utility Strike

- Failed tests due to existing soil conditions: Compaction tests that fail due to heterogeneous in-situ material are not contractor error. The proctor value may not represent the actual soil characteristics at the test location.

- Owner-directed work suspensions: Field Memoranda directing suspension of specific activities (e.g., FM 152) due to reasons other than safety etc. Suspension of work or specific activities due to safety reasons ARE Contractor-Caused Delay.

- Design errors, omissions, or late design changes: SDOT-issued design revisions, RFI responses that change scope.

- Third-party delays beyond contractor control: Utility company failing to relocate on schedule, permit authority delays; but only if the contractor timely initiated the process.

- Unusually severe weather: Only if declared an Unworkable Day by the Engineer per Section 1-08.5.

Important: If an owner-caused event occurs but the Contractor fails to pursue available work elsewhere on the project, the period of inactivity in the unaffected areas may still be classified as a contractor-caused delay. The Contractor’s obligation under Section 1-08.4 to diligently pursue the Work applies at all times.

# 6. Decision Framework - Quick Reference

When reviewing a daily report entry and you are unsure whether to classify an event as a contractor-caused delay, work through these questions:

| Daily Report Scenario | Key Question to Ask | If YES | If NO |
| --- | --- | --- | --- |
| Crew arrived late to work area | Was the late arrival caused by an owner-directed restriction, traffic control issue managed by SDOT, or permit condition? | Owner Delay or Shared | Contractor Delay |
| Work stopped for part of the day | Was the stoppage directed by the Engineer, caused by a utility conflict, differing site condition, or third-party (not sub)? | Potentially Owner Delay | Contractor Delay |
| Material not available on site | Was the material shortage caused by an SDOT design change, late approval, or procurement delay on an owner-furnished item? | Owner Delay | Contractor Delay |
| Rework performed | Was the rework caused by a design error, changed condition, or SDOT-directed revision? | Owner Delay | Contractor Delay (NCR) |
| Low crew count or no work in an area | Was an SDOT restriction, permit limitation, or utility conflict preventing access to the work area? | Owner Delay | Contractor Delay (Staffing) |
| Equipment breakdown | Was the breakdown caused by an unforeseen site condition (e.g., hitting unmarked utility)? | Potentially Shared | Contractor Delay |
| Subcontractor did not show up | Was the sub’s absence caused by an owner-directed suspension, permit issue, or design hold? | Owner Delay | Contractor Delay |
| Weather day claimed but crew worked elsewhere | Did SDOT declare the day an Unworkable Day per Section 1-08.5? | Non-Compensable (Weather) | Contractor Delay if work was feasible |

# 7. Worked Examples from Inspector Daily Reports

The following examples are drawn from actual project inspector daily reports (IDRs). Each example shows the original report language, the correct analysis, and the proper classification. Use these as a reference when you encounter similar entries.

## 7.1 Contractor-Caused Delay Events

| Example A: Subgrade Rework - Regrading Due to Incorrect Elevations |  |
| --- | --- |
| Daily Report Excerpt: | The 7:00 AM crew arrived on site and removed all plastic sheeting from the subgrade between Boston and Newton streets. Multiple areas were identified where the planned concrete depth would exceed the specified maximum of 13.5 inches. Civil Crew #3 spent more than four hours regarding the subgrade between Boston and Newton to achieve the required elevations. Operations were shut down at approximately 10:00 AM for the remainder of the day. The primary reason for the early shutdown was that the section at Howe intersection has not yet been completed and has not passed compaction testing. |
| Analysis: | This entry contains two distinct contractor-caused delays. First, the subgrade was not graded to the correct elevations before concrete placement was scheduled, requiring 4+ hours of rework. Second, operations were shut down entirely because a predecessor activity (Howe intersection compaction) was not complete. Both are planning and quality failures within the Contractor’s control. |
| Classification: | CONTRACTOR DELAY - Rework + Incomplete predecessor blocking successor |

| Example B: Utility Strike on Known Storm Drain |  |
| --- | --- |
| Daily Report Excerpt: | UTILITY STRIKE: West Roosevelt at (N) NE 43rd Avenue. Civil crew has struck known 6” concrete storm drainpipe during excavator operations south of Trinity Apartments parking lot driveway. AAR QC James Russo was informed of the event for documentation and CM team was informed as well as Akana SPU inspector Scott Henderson. |
| Analysis: | The key word is “known.” The utility was identified in the contract documents. Striking a known utility during excavation reflects a failure to exercise due care during operations. The time spent on damage assessment, repair coordination, and any work stoppage is a contractor-caused delay. |
| Classification: | CONTRACTOR DELAY - Utility strike on known utility |

| Example C: Concrete Delivery Delay Causing Cold Joint |  |
| --- | --- |
| Daily Report Excerpt: | At 10:00 AM, Heidelberg Concrete arrived on-site. The first truck was tested for Alkali-Aggregate Reactivity (AAR), met the minimum requirements, and was approved for placement. The first two trucks were delivered without issues. However, the third truck arrived after a delay of approximately 1 hour and 24 minutes, potentially resulting in a cold joint. |
| Analysis: | Supplier delivery delays are attributable to the Contractor. Jansen is responsible for managing its concrete supplier’s delivery schedule. The 1.5-hour gap between trucks disrupted the pour and created a potential cold joint, which may require panel removal and replacement (further contractor delay if an NCR is issued). |
| Classification: | CONTRACTOR DELAY - Supplier failure + potential NCR |

| Example D: Forgotten Conduit Run |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Trenching for the conduit run that they (Jansen) forgot. |
| Analysis: | The word “forgot” indicates Jansen missed this work during the planned sequence and had to remobilize a crew to perform it out of order. This requires re-excavation, trenching, and likely traffic control that was not in the original sequence. The remobilization effort and any disruption to other activities is contractor-caused. |
| Classification: | CONTRACTOR DELAY - Missed work requiring remobilization |

| Example E: Signal Head NCR and Rework |  |
| --- | --- |
| Daily Report Excerpt: | SDOT issued a non-conformance for the alignment of the signal heads at Allison intersection not lining up with what is shown in TCP 352-1. Transcon adjusted signal heads at no cost to the City. The cost is on Jansen. |
| Analysis: | Transcon is Jansen’s subcontractor. Signal heads were installed non-conforming to the traffic control plan, SDOT issued an NCR, and Transcon had to rework the installation. Subcontractor rework is attributable to the general contractor. |
| Classification: | CONTRACTOR DELAY - Subcontractor NCR rework |

| Example F: Riser Rebuild Due to Dimensional Error |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Jansen having to rebuild this riser due to being 2” too high. |
| Analysis: | The riser was constructed outside of specified tolerances. Jansen is responsible for verifying dimensions during construction. The time spent demolishing and rebuilding the riser is rework attributable to the Contractor. |
| Classification: | CONTRACTOR DELAY - Rework due to construction error |

| Example G: Transcon Signal Head Rework (Separate Incident) |  |
| --- | --- |
| Daily Report Excerpt: | At 08:50 am Transcon is installing an additional signal head on the wood pole for southbound traffic, this is to alleviate confusion due to one of the through motion signal heads is too close to the left turn signal head. Once complete with the installation of this signal head, they will bag the one causing the confusion and move to shifting signal heads at Allison and Eastlake. |
| Analysis: | Transcon (Jansen’s subcontractor) is performing corrective work to fix a signal head placement issue that should have been done correctly the first time. The effort to add a new head, bag the problematic one, and then shift heads at another location represents multiple crew-hours of rework. |
| Classification: | CONTRACTOR DELAY - Subcontractor rework, should have been done right the first time |

| Example H: Temporary Asphalt Deficiency |  |
| --- | --- |
| Daily Report Excerpt: | Temp asphalt appears to not provide positive protection for pedestrians. |
| Analysis: | Temporary pedestrian protection is the Contractor’s responsibility. This deficiency will likely require additional temporary asphalt placement to achieve compliance, consuming crew time and materials that should have been applied correctly initially. |
| Classification: | CONTRACTOR DELAY - Deficient temp protection requiring rework |

| Example I: Resources Diverted to Non-Project Scope |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Not the project’s scope but here is a photo from my site visit. Refer to the email sent to Paki, Scott, Matt, Chris, and Jon. |
| Analysis: | If Jansen is directing labor, equipment, or supervision to work that is outside the contract scope, those resources are being diverted from contract work. The question to raise is: why are resources being directed to non-project work, and is this causing or contributing to delay on contract activities? |
| Classification: | CONTRACTOR DELAY (POTENTIAL) - Resource diversion to out-of-scope work |

## 7.2 Events That Are NOT Contractor-Caused Delays

| Example J: Failed Compaction Test Due to Soil Conditions |  |
| --- | --- |
| Daily Report Excerpt: | He can’t get tests passing due to the heterogeneous material in this location. Seems firm and unyielding. No pumping is observed. |
| Analysis: | A compaction test on subgrade may not pass due to heterogeneous in-situ material since the proctor value used may not represent the characteristics of the soil at the exact test location. The inspector notes the ground is firm with no pumping. This is a soil condition issue, not a contractor error in compaction methods. |
| Classification: | NOT A CONTRACTOR DELAY - Existing soil condition |

| Example K: Differing Site Condition - Water Service Size Discrepancy (DSC 294) |  |
| --- | --- |
| Daily Report Excerpt: | DSC 294 - WS-1211 and WS-1210 Size Discrepancy: In the plans WS-1211 is labeled as a ¾” service connection, in the field it was found to be a 4” cast iron service. In the plans WS-1210 is labeled as a 4” service connection, in the field it was found to be a ¾” service. |
| Analysis: | This is a Differing Site Condition (DSC). The field conditions do not match the contract documents. Work performed under accepted DSCs is NOT a contractor-caused delay. Always cross-reference the accepted DSC list before classifying. |
| Classification: | NOT A CONTRACTOR DELAY - Accepted Differing Site Condition |

| Example L: Tree Roots Encountered During Excavation |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Immediately after removing curb from the roadway island at WS-301 (WM STA 10+29), large roots were encountered. Jansen directed to utilize Vactor Truck tomorrow to remove dirt and find a path for the 2” water service, while minimizing tree root removal. |
| Analysis: | The Contractor has no control over roots existing at the location where the water service must pass. This is an existing site condition. The need to use specialized equipment (vactor truck) to navigate around roots is not a contractor efficiency failure. |
| Classification: | NOT A CONTRACTOR DELAY - Existing site condition beyond Contractor’s control |

| Example M: Existing Electrical Conduits in Trench |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Civil Crew #5 removing additional pavement at WS-1212 (WM STA 58+64) due to existing electrical conduits in the same trench as the water services and main. ESO (Jesse Daurie) on site during excavation. |
| Analysis: | This is an existing condition that the Contractor had no control over or contribution to. The presence of electrical conduits in the same trench as the planned water work was not shown in the contract documents. This is potentially a Differing Site Condition - check the accepted DSC list. |
| Classification: | NOT A CONTRACTOR DELAY - Existing condition, potentially a DSC |

## 7.3 Gray Areas Requiring Verification

| Example N: Damaged Water Service - DSC or Utility Strike? |  |
| --- | --- |
| Daily Report Excerpt: | Comment: Flattened and broken ¾” service. Water shut off by SPU at main and hole dewatered prior to this photo. |
| Analysis: | This needs verification. If the service was shown on the plans at its actual location and the Contractor struck it through careless excavation, it is a utility strike (contractor delay). If the service was not shown or was in an unexpected location, it may qualify as a Differing Site Condition. Flag as a potential contractor-caused delay pending DSC determination. |
| Classification: | FLAG FOR VERIFICATION - Cross-reference DSC list and plan documents |

| Example O: Irrigation Line Strike - DSC or Contractor Error? |  |
| --- | --- |
| Daily Report Excerpt: | Subject: T-211-08. Location: 11th between 42nd/43rd. Badger truck boom struck a 1” irrigation line. Jansen will repair the line under appropriated bid item. |
| Analysis: | Similar to Example N. If the irrigation line was shown on plans and Jansen struck it, this is a contractor-caused delay. If not shown on plans, it may be a DSC. The fact that Jansen is repairing under a bid item suggests it may be covered, but the delay impact of the strike itself needs to be classified separately. |
| Classification: | FLAG FOR VERIFICATION - Verify if DSC or contractor-caused strike |

| Example P: Survey Challenges - Not Yet a Delay |  |
| --- | --- |
| Daily Report Excerpt: | Trying to put stringlines on a slope with two breaks in the panels with only one survey point. Trying to get a survey point from behind a wall of removed ties. |
| Analysis: | This is not a good construction practice and may lead to non-compliant slope and elevation in the finished pavement. At this stage it is not a delay event. However, if the Contractor places the pavement with incorrect slope or elevation and this becomes an NCR, the corrective action requiring rework would then be a contractor-caused delay. Flag for monitoring. |
| Classification: | NOT YET A DELAY - Monitor for potential NCR and rework |

| Example Q: Double Handling of Spoil Material |  |
| --- | --- |
| Daily Report Excerpt: | Loading spoil material and dumping it in another location just to load it up again for removal to off site. |
| Analysis: | Double handling can be a delay event if it was not planned in the baseline schedule. If the Contractor’s original means and methods (as reflected in the baseline schedule) already included double handling at this location, then it is baked into the planned durations and is not an additional delay. If it was not planned and reflects an inefficiency, classify as contractor delay. Check baseline schedule activity assumptions. |
| Classification: | CONDITIONAL - Contractor delay only if not anticipated in baseline schedule |

# 8. Gray Areas & Borderline Scenarios

Some situations do not fit neatly into “contractor delay” or “not contractor delay.” The following scenarios are commonly encountered on urban corridor projects like RRJ and require additional context before classification.

| Scenario 1: Owner Event in One Zone, Contractor Idle in Other Zones |  |
| --- | --- |
| Situation: | FM 152 directed Jansen to stop drainage structure installation on Fairview due to a duct bank conflict. During the same period, the Contractor reduced or ceased activity in the South Lake Union, Eastlake, and U-District operational areas even though those areas were accessible and unrestricted. |
| Why It’s Gray: | The Contractor may argue the entire project was affected. However, FM 152 only suspended specific work within Zone 4 and explicitly directed Jansen to “revise your work plan and resequence activities as necessary to maintain progress.” The contract (Section 1-08.4) requires diligent prosecution of all available work. |
| How to Classify: | The inactivity in the non-affected zones is a contractor-caused delay for concurrent delay analysis purposes. Document the available-but-idle work areas for each day during the FM 152 period. The delay in the directly affected Fairview drainage activities may be owner-attributable, but the failure to prosecute work elsewhere is contractor-attributable. |

| Scenario 2: Utility Strike - Known vs. Unknown Utility |  |
| --- | --- |
| Situation: | Contractor strikes a utility during excavation. The daily report says “damage was noted to 6” concrete known storm drains from excavator bucket strike.” |
| Why It’s Gray: | If the utility was “known” (shown on plans, previously potholed, or identified through utility locates), the strike is contractor negligence. If the utility was “unknown” (not shown on plans, not in utility records), it may be a Differing Site Condition. |
| How to Classify: | Always check: (1) Was the utility shown on the contract drawings? (2) Was it included in utility locate tickets? (3) Had it been previously potholed or exposed? If yes to any, classify as contractor delay. If no to all, flag for DSC evaluation. The word “known” in the inspector’s report is a strong indicator of contractor responsibility. |

| Scenario 3: Slow Production vs. Delay |  |
| --- | --- |
| Situation: | Inspector notes that Civil Crew #3 placed 150 LF of curb over a full shift. The schedule assumes 300 LF/day production rate for this activity. |
| Why It’s Gray: | Slow production alone is not necessarily a discrete “delay event” in the same way a utility strike or NCR is. However, sustained low productivity extends activity durations on the schedule and can consume available float. |
| How to Classify: | Document the production rate observed vs. the scheduled rate. If the low production is sustained over multiple days and is not attributable to any owner-caused restriction, it supports a finding that the Contractor is not diligently prosecuting the Work per Section 1-08.4. Note it as a contractor efficiency issue for the concurrent delay record. |

| Scenario 4: Rework Caused by Design Change vs. Contractor Error |  |
| --- | --- |
| Situation: | Inspector reports that Jansen is removing and rebuilding a section of work. The daily report does not state whether this is due to an NCR or a design revision. |
| Why It’s Gray: | If the rework was directed by SDOT due to a design change, it is an owner-caused event. If the rework is correcting defective work, it is contractor-caused. The daily report language alone may not be sufficient. |
| How to Classify: | Cross-reference the NCR log and the change order / RFI log for the same date and location. If an NCR exists for that work, classify as contractor delay. If a design change or RFI response drove the rework, classify as owner delay. If neither record exists, flag for further investigation. |

| Scenario 5: Subcontractor Delay During Owner-Caused Suspension |  |
| --- | --- |
| Situation: | During a period when SDOT has suspended work in one area, a subcontractor scheduled for a different, unaffected area fails to show up. |
| Why It’s Gray: | The Contractor may try to attribute the subcontractor’s absence to the owner suspension. However, if the subcontractor was scheduled for work in an area unaffected by the suspension, the no-show is a contractor/subcontractor management issue. |
| How to Classify: | Classify the subcontractor no-show as contractor delay if the work area was accessible. The existence of an owner suspension in a different area does not excuse the Contractor from managing its subcontractors in unaffected areas. |

# 9. Inspector Writing Guidance for Daily Reports

The value of a daily report for delay analysis depends entirely on the specificity and clarity of the inspector’s language. Vague entries are unclassifiable. This section provides guidance on writing daily report entries that can be accurately interpreted by both human reviewers and AI-assisted sorting tools.

## 9.1 The Three Essential Elements

Every daily report entry describing work activity or inactivity should answer three questions:

- WHAT: What specific work was performed, or what specific condition prevented work? Use activity descriptions, not generic terms.

- WHERE: What is the specific location? Include station numbers, zone/operational area, street names, intersection references, or water service IDs (e.g., WS-1212, WM STA 58+64).

- WHY: If work was delayed, stopped, or deviated from the plan, state the reason. Was it an equipment issue? Crew shortage? Owner directive? Design issue? Material delivery?

If any of these three elements is missing, the entry becomes difficult or impossible to classify for delay analysis.

## 9.2 Bad vs. Good Wording - Side-by-Side Examples

The following table shows common vague entries and how they should be rewritten for clarity:

| Bad Wording (Vague) | Why It’s a Problem | Better Wording (Specific) |
| --- | --- | --- |
| “Miscellaneous tasks” | Completely unclassifiable. No way to determine if productive work occurred or what activity was affected. | “Foreman Austin Waldrop and 1 operator performing cleanup of Stage 5 WM excavation site and relocating spoil pile to staging area at [location].” |
| “Waiting on material” | Does not identify what material, who is responsible for delivery, or whether an owner action caused the delay. | “Civil Crew #3 idle from 7:00–11:30 AM waiting on 8” DI pipe delivery from [supplier]. Pipe was scheduled for delivery at 7:00 AM per Jansen’s procurement schedule.” |
| “No work today” | Does not explain why. Was it weather? Owner suspension? Contractor decision? Crew shortage? | “No Jansen crews mobilized to Eastlake operational area. Area is accessible with no active restrictions. Jansen superintendent stated crews are allocated to Fairview.” |
| “Rework in progress” | Does not explain what is being reworked, why, or whether it is due to an NCR or design change. | “Jansen removing and replacing 40 LF of curb at STA 12+50 to STA 13+30 per NCR-087 (non-conforming alignment). Civil Crew #2, 4 laborers, started 8:00 AM.” |
| “Slow day” | Subjective and unquantifiable. Does not describe what work occurred or what caused the reduced pace. | “Civil Crew #5 placed 120 LF of sidewalk (vs. 280 LF/day scheduled rate). Crew of 3 laborers on site; foreman reports 2 laborers called in sick.” |
| “Contractor working in the area” | Does not identify what activity, which crew, or what progress was made. | “Jansen Civil Crew #7 (1 operator, 2 laborers) excavating for electrical conduit on westside of Roosevelt at NE 43rd. Approximately 80 LF trenched by end of shift.” |
| “Issue with the pour” | Does not describe the issue, its cause, or its consequence. | “Third concrete truck from Heidelberg arrived 1 hr 24 min after second truck. Potential cold joint at Panel 7 (see attached drawing). First two trucks placed without issue.” |
| “Equipment problems” | Does not identify which equipment, whose equipment, what failed, or how long work was affected. | “Jansen’s CAT 320 excavator hydraulic failure at 9:15 AM at STA 25+00. Crew #4 idle remainder of day. Mechanic dispatched, ETA tomorrow AM.” |

## 9.3 Vague Words and Phrases to Avoid

The following terms are “red flags” that signal an entry may be too vague for classification. When reviewing your own entries, replace these with specific descriptions:

| Vague Term | Problem | Replace With |
| --- | --- | --- |
| “Miscellaneous tasks” | Unclassifiable | Name the specific tasks |
| “Various activities” | Unclassifiable | List each activity performed |
| “Some issues” / “problems” | Nature unknown | Describe the specific issue |
| “Working in the area” | No activity identified | Name the CPM activity or work type |
| “Slow day” / “quiet day” | Subjective, no data | State crew count + production achieved |
| “Waiting” (without explanation) | Cause unknown | State what they are waiting for and who is responsible |
| “Delay” (without cause) | Attribution impossible | State the cause: material, equipment, crew, owner directive |
| “Cleanup” (alone) | May mask idle time | Describe what is being cleaned and why |
| “Standby” (without reason) | Cannot classify | State why the crew is on standby and for how long |
| “General work” | Meaningless for analysis | Describe the specific work being performed |

## 9.4 Documenting Idle Time, Partial Days, and No-Work Conditions

Idle time and partial work days are among the most important entries for concurrent delay analysis, yet they are the most frequently under-documented. Follow these guidelines:

Full Idle Day (No Work Performed):

- State clearly that no work occurred: “No Jansen crews on site today.”

- State the reasons if known: owner directive, weather, contractor decision, crew shortage.

- State whether the work area was accessible: “Eastlake operational area accessible with no active restrictions.”

- If the Contractor claims weather, note whether the Engineer declared an Unworkable Day.

Partial Day (Early Shutdown or Late Start):

- Record the actual hours worked: “Crew arrived 9:30 AM (1.5 hrs late), departed 2:00 PM.”

- State the reason for the shortened day if known.

- Quantify the lost time: “Approximately 4.5 hours of the 8-hour shift were unproductive.”

Crew on Site But Idle:

- Record how many workers were idle, for how long, and the stated reason.

- Distinguish between owner-caused idle (waiting for inspection, access restriction) and contractor-caused idle (waiting for materials, equipment down, no foreman direction).

- Example: “6 laborers on site from 7:00 AM, idle until 10:30 AM waiting for concrete delivery. Heidelberg truck arrived 10:30 AM.”

Multiple Zones - Activity vs. Inactivity:

- When reporting on multiple work areas, note both where work IS occurring and where it is NOT.

- Example: “Jansen active in U-District (Civil Crew #7 trenching). No crews mobilized to Eastlake or South Lake Union operational areas. Both areas accessible.”

- This documentation is critical for demonstrating concurrent contractor delays when Jansen claims delay only in the restricted zone.

# 10. How to Document Your Findings

When you identify a potential contractor-caused delay in a daily report, record the following:

- Date: The date of the daily report.

- Source: Which daily report, inspector diary, or field record contains the observation (include report number/author).

- Zone/Location: Where on the project the delay occurred (operational area + specific location).

- Activity Affected: Which CPM schedule activity (by activity ID if possible) was impacted.

- Description: A brief factual description using the report’s own language where possible.

- Duration: Estimated time lost (full day, half day, or hours if identifiable).

- Concurrent Owner Event: Note whether an owner-caused delay was also occurring on the same date in the same or different area.

# 11. Common Pitfalls to Avoid

- Do not assume weather = no contractor delay. If the weather did not prevent all work and the contractor chose not to work in available areas, the inactivity is contractor-caused.

- Do not ignore partial days. A crew that works 4 hours and leaves early has a partial-day contractor delay for the remaining hours (unless an owner event caused the early departure). Partial days should be documented in hours and evaluated cumulatively in the schedule as described under Section 9.4 herein this document.

- Do not conflate “owner event in one zone” with “project-wide excuse.” If SDOT suspended work in Zone 4 but other operational areas were fully accessible, the contractor’s failure to work in those areas is a contractor-caused delay.

- Do not classify slow production as owner delay. If the contractor is working but at a pace significantly below what the schedule requires, that is a contractor efficiency issue unless an owner action directly caused the reduced productivity.

- Do not overlook submittal and procurement delays. If a material delivery is late because the contractor submitted late or submitted non-conforming documents, the resulting delay is contractor-caused.

- Watch for “voluntary shutdown.” Section 1-08.4 prohibits the Contractor from voluntarily shutting down or slowing operations without Engineer approval.

- Do not assume utility strikes are always contractor delays. Check whether the utility was “known” (shown on plans) or “unknown” (potential DSC). The word “known” in the report is a strong indicator.

- Always cross-reference the DSC list. Work under accepted DSCs is not contractor-caused. Do not classify DSC-related work as contractor delay without checking.

# 12. Guiding Principle

The fundamental question is always: Was the Contractor doing everything within its power to diligently prosecute the Work on this day? If the answer is no, and the reason is not an owner-caused event, force majeure, or declared unworkable day; then the period of inactivity or inefficiency is a contractor-caused delay and should be documented for the concurrent delay analysis.

This guide is prepared for internal use to support consistent application and understanding of specific contract provisions in the context of schedule delay analysis on the RapidRide J Line BRT Project. It reflects internal analytical guidance only and is not a formal interpretation of the contract. It does not create new obligations, expand existing rights or alter the risk allocation established by the contract. The contract documents remain the sole governing authority.

QUICK-REFERENCE CHEAT SHEET: Contractor-Caused Delay Identification

| IS A CONTRACTOR DELAY. - Insufficient crews / late start / early quit - No crew in available, unrestricted and scheduled work area - Subcontractor no-show or supplier late delivery - Rework from NCR / defective work / dimensional error requiring rework - Utility strike on KNOWN/MARKED utility - Equipment breakdown (contractor’s equipment) - Forgotten/missed work requiring remobilization - Cold joint from late concrete delivery - Resources diverted to out-of-scope work - Work out of sequence vs. CPM schedule - Temp protection deficiency requiring rework. NOT A CONTRACTOR DELAY. - Accepted Differing Site Conditions (DSCs) - Unforeseen roots, unmarked utilities, soil conditions - Failed compaction from heterogeneous in-situ material - Owner-directed suspension (e.g., FM 152) - Design changes / late RFI responses by SDOT - Engineer-declared Unworkable Days (weather) - Third-party delays (utility co., permits) if Contractor initiated timely. FLAG FOR VERIFICATION. - Utility strike - unknown if utility was on plans - Rework - unclear if NCR or design change - Double handling - check baseline schedule - Bad practice not yet causing delay (monitor for NCR). | THE CORE TEST Was the Contractor doing everything within its power to diligently prosecute the Work on this day? If NO (and not owner-caused) = Contractor Delay. KEY QUESTIONS FOR EVERY ENTRY. - Was the delay within the Contractor’s control? - Could it have been avoided with due care? - Was the utility “known” or “unknown”? - Is there an accepted DSC for this location? - Was rework from an NCR or a design change? - Were other zones available but idle?. EVERY DAILY REPORT ENTRY NEEDS. - WHAT: Specific activity or condition - WHERE: Station, zone, street, WS/WM ID - WHY: Cause if delayed or deviated - DURATION: How long was work affected? - WHO: Crew number, foreman, sub name. RED FLAG WORDS – TOO VAGUE. “Miscellaneous tasks” • “Various activities” • “Slow day” • “Working in the area” • “Some issues” • “Waiting” (no reason) • “General work” • “Cleanup” (alone) • “Standby” (no reason) • “No work today” (no reason). KEY CONTRACT SECTIONS. 1-08.4: Diligent prosecution of Work 1-08.8(1): Time extension requirements 1-08.8(2): Non-excusable delays defined 1-08.8(4): Concurrent delay – no payment to either party. |
| --- | --- |